## 01_chart_of_accounts
account_number | name | account_type | sub_type | description
1000 | Cash & Equivalents | asset | current_asset | Operating cash and short-term deposits
1005 | Grant Funds - Federal | asset | current_asset | Federal grant funds received and held
1006 | Grant Funds - State | asset | current_asset | State appropriation funds held
1010 | Accounts Receivable | asset | current_asset | Amounts owed by government clients
1015 | Government Contract Receivable | asset | current_asset | Amounts due under government prime contracts
1020 | Retainage Receivable | asset | current_asset | Retained amounts held by government owner
1025 | Sales Tax Receivable | asset | current_asset | Recoverable input tax on purchases
1030 | Costs in Excess of Billings | asset | current_asset | Underbillings on government contracts
1040 | Prepaid Expenses | asset | current_asset | Prepaid insurance bonds and permits
1050 | Inventory & Materials on Site | asset | current_asset | Stored materials approved for payment
1100 | Property & Equipment | asset | fixed_asset | Construction equipment and vehicles
1110 | Accumulated Depreciation | asset | fixed_asset | Contra account for accumulated depreciation
1200 | Deposits | asset | other_asset | Security deposits and bid bonds
2000 | Accounts Payable | liability | current_liability | Amounts owed to vendors and subcontractors
2010 | Subcontractor Payable | liability | current_liability | Amounts owed to subcontractors
2020 | Retainage Payable | liability | current_liability | Amounts withheld from subcontractors
2030 | Billings in Excess of Costs | liability | current_liability | Overbillings on government contracts
2040 | Accrued Wages & Benefits | liability | current_liability | Payroll and benefits accrued not yet paid
2050 | Accrued Taxes | liability | current_liability | Federal state and payroll taxes payable
2055 | Sales Tax Payable | liability | current_liability | Sales and use tax collected
2060 | Performance Bond Liability | liability | current_liability | Performance and payment bond obligations
2070 | Workers Comp Reserve | liability | current_liability | Self-insured workers compensation reserve
2080 | Notes Payable - Equipment | liability | long_term_liability | Equipment financing notes
2090 | Deferred Revenue - Grants | liability | long_term_liability | Grant funding received but not yet earned
3000 | Common Stock | equity | equity | Common stock issued
3010 | Retained Earnings | equity | equity | Cumulative retained earnings
3020 | Current Year Net Income | equity | equity | Current year net income
4000 | Contract Revenue - Government | revenue | revenue | Prime contract revenue from government projects
4010 | Federal Grant Revenue | revenue | revenue | Revenue recognized from federal grants
4020 | State Appropriation Revenue | revenue | revenue | Revenue recognized from state appropriations
4030 | Change Order Revenue | revenue | revenue | Approved change order revenue
4040 | Bond Premium Revenue | revenue | revenue | Premium on performance and payment bonds
4050 | Equipment Rental Revenue | revenue | revenue | Revenue from equipment rental to project
5000 | Direct Labor | expense | cost_of_revenue | Field labor wages and burden
5010 | Subcontractor Costs | expense | cost_of_revenue | Payments to subcontractors
5020 | Materials & Supplies | expense | cost_of_revenue | Direct materials incorporated into project
5030 | Equipment Costs | expense | cost_of_revenue | Equipment rental and depreciation on project
5040 | Other Direct Costs | expense | cost_of_revenue | Permits fees testing and inspections
5050 | Davis-Bacon Compliance Costs | expense | cost_of_revenue | Prevailing wage compliance and reporting
5060 | Section 3 Compliance Costs | expense | cost_of_revenue | HUD Section 3 compliance and reporting
6000 | Project Management | expense | operating_expense | PM superintendent and field staff salaries
6010 | General & Administrative | expense | operating_expense | Office salaries overhead and admin
6020 | Insurance | expense | operating_expense | General liability umbrella workers comp premiums
6030 | Bonds | expense | operating_expense | Performance payment and bid bond premiums
6040 | Depreciation | expense | operating_expense | Depreciation on company owned equipment
6050 | Professional Fees | expense | operating_expense | Legal accounting and consulting
6060 | Marketing & Business Development | expense | operating_expense | Proposal costs and business development
6070 | Office & Facilities | expense | operating_expense | Rent utilities and office expenses
6080 | Vehicle & Travel | expense | operating_expense | Company vehicles and travel expenses
6090 | IT & Software | expense | operating_expense | Technology and software subscriptions
7000 | Interest Expense | expense | other_expense | Interest on equipment notes and credit lines

## 02_bank_accounts
name | bank_name | account_type | account_number_last4 | routing_number_last4 | current_balance
General Operating | Bank of America | checking | 4421 | 0560 | 3850000
Payroll Account | Bank of America | checking | 4422 | 0560 | 925000
Federal Grant Restricted - GSA | Bank of America | checking | 4423 | 0560 | 2200000
State Appropriation Restricted | Wells Fargo | checking | 7751 | 1210 | 4100000
CDBG Grant Restricted | Wells Fargo | checking | 7752 | 1210 | 350000
Retainage Reserve | Bank of America | savings | 4424 | 0560 | 3490000

## 03_projects
name | code | status | project_type | address | city | state | zip | client_name | client_email | client_phone | budget | estimated_cost | start_date | end_date | description | completion_pct
Federal District Courthouse & Public Safety Complex | FDC-2024 | active | government | 1500 Constitution Ave NW | Washington | DC | 20001 | U.S. General Services Administration | t.jefferson@gsa.gov | 202-555-0201 | 68500000 | 64200000 | 2024-02-01 | 2026-09-30 | New 12-story federal courthouse with 24 courtrooms district attorney and public defender suites secure holding facility and 850-space parking structure. Funded through GSA appropriations CDBG grant and state public safety bond. Davis-Bacon prevailing wage and Section 3 hiring requirements apply. LEED Gold certification target. | 52

## 04_contacts
first_name | last_name | contact_type | email | phone | company_name | job_title
James | Whitfield | employee | j.whitfield@fcdgov.com | 202-555-0101 | Federal Construction Dynamics | CEO & President
Sandra | Okafor | employee | s.okafor@fcdgov.com | 202-555-0102 | Federal Construction Dynamics | Chief Financial Officer
Marcus | Delaney | employee | m.delaney@fcdgov.com | 202-555-0103 | Federal Construction Dynamics | VP of Operations
Patricia | Nguyen | employee | p.nguyen@fcdgov.com | 202-555-0104 | Federal Construction Dynamics | Project Executive
Warren | Collins | employee | w.collins@fcdgov.com | 202-555-0105 | Federal Construction Dynamics | Project Executive
Daniel | Hargrove | employee | d.hargrove@fcdgov.com | 202-555-0106 | Federal Construction Dynamics | Senior Project Manager
Linda | Castillo | employee | l.castillo@fcdgov.com | 202-555-0107 | Federal Construction Dynamics | Project Manager
Kevin | Osei | employee | k.osei@fcdgov.com | 202-555-0108 | Federal Construction Dynamics | Senior Superintendent
Raymond | Torres | employee | r.torres@fcdgov.com | 202-555-0109 | Federal Construction Dynamics | Safety Director
Angela | Petrov | employee | a.petrov@fcdgov.com | 202-555-0110 | Federal Construction Dynamics | Project Controller
Brenda | Walsh | employee | b.walsh@fcdgov.com | 202-555-0111 | Federal Construction Dynamics | Compliance Officer
Derek | Simmons | employee | d.simmons@fcdgov.com | 202-555-0112 | Federal Construction Dynamics | Quality Control Manager
Amara | Nwosu | employee | a.nwosu@fcdgov.com | 202-555-0113 | Federal Construction Dynamics | BIM/VDC Coordinator
Carlos | Reyes | employee | c.reyes@fcdgov.com | 202-555-0114 | Federal Construction Dynamics | Project Engineer - Structural
Jennifer | Pak | employee | j.pak@fcdgov.com | 202-555-0115 | Federal Construction Dynamics | Project Engineer - MEP
Gregory | Hoffman | employee | g.hoffman@fcdgov.com | 202-555-0116 | Federal Construction Dynamics | Assistant Superintendent
Tamika | Robinson | employee | t.robinson@fcdgov.com | 202-555-0117 | Federal Construction Dynamics | Office Manager
Michael | Brennan | employee | m.brennan@fcdgov.com | 202-555-0118 | Federal Construction Dynamics | Field Supervisor - Concrete
Russell | Yamamoto | employee | r.yamamoto@fcdgov.com | 202-555-0119 | Federal Construction Dynamics | Field Supervisor - Steel
Antonio | Delgado | employee | a.delgado@fcdgov.com | 202-555-0120 | Federal Construction Dynamics | Field Supervisor - MEP
Diane | Washington | employee | d.washington@fcdgov.com | 202-555-0121 | Federal Construction Dynamics | Field Supervisor - Finishes
Robert | Kim | employee | r.kim@fcdgov.com | 202-555-0122 | Federal Construction Dynamics | Field Supervisor - Enclosure
Nicole | Andersen | employee | n.andersen@fcdgov.com | 202-555-0123 | Federal Construction Dynamics | Document Control Specialist
Terrence | Ogundimu | employee | t.ogundimu@fcdgov.com | 202-555-0124 | Federal Construction Dynamics | Section 3 Outreach Coordinator
Sharon | Levine | employee | s.levine@fcdgov.com | 202-555-0125 | Federal Construction Dynamics | Cost Estimator
Thomas | Jefferson | client | t.jefferson@gsa.gov | 202-555-0201 | U.S. General Services Administration | Contracting Officer
Diane | Kaminski | client | d.kaminski@gsa.gov | 202-555-0202 | U.S. General Services Administration | Contracting Officer Representative
Robert | Greenfield | client | r.greenfield@statearch.gov | 202-555-0203 | State Dept of Public Works | Deputy Director
Michelle | Obi | client | m.obi@hud.gov | 202-555-0204 | U.S. Dept of Housing & Urban Development | Grant Administrator
Frank | Sloane | client | f.sloane@hud.gov | 202-555-0205 | CDBG Office | Program Manager
Richard | Thornton | client | r.thornton@thorntonarch.com | 202-555-0206 | Thornton Hartman Architects | Principal Architect of Record
Catherine | Pryor | client | c.pryor@fedprojectrep.com | 202-555-0207 | Federal Project Representation LLC | Owners Representative

## 05_vendors
company_name | first_name | last_name | email | phone | job_title
Eagle Excavation LLC | Harold | Nkemelu | h.nkemelu@eagleexcavation.com | 202-555-0305 | Operations Manager
Nationwide Concrete Inc | Tonya | Bassett | t.bassett@nationwideconcrete.com | 202-555-0306 | Regional Manager
Federal Steel Erectors | Jerome | Kessler | j.kessler@federalsteel.com | 202-555-0303 | Estimator
Patriot Electrical Contractors | Sylvia | Drummond | s.drummond@patriotelectric.com | 202-555-0304 | President
Capital MEP Group | Constance | Merritt | c.merritt@capitalmep.com | 202-555-0302 | Project Manager
Monument Masonry Corp | Denise | Altman | d.altman@monumentmasonry.com | 202-555-0310 | VP Estimating
Capitol Roofing Systems | Lisa | Vandenberg | l.vandenberg@capitolroofing.com | 202-555-0308 | Project Manager
Union Drywall & Framing | Victor | Asamoah | v.asamoah@uniondrywall.com | 202-555-0307 | Estimator
SafeGuard Security Integration | Phillip | Monroe | p.monroe@safeguardsec.com | 202-555-0311 | Federal Projects Director
Apex Fire Protection LLC | George | Flanagan | g.flanagan@apexfire.com | 202-555-0309 | Project Manager
Potomac Elevator Co | Martin | Cruz | m.cruz@potomacelevator.com | 202-555-0316 | Project Manager
Huang Structural Engineering | Walter | Huang | w.huang@huangstructural.com | 202-555-0301 | Principal Engineer
Davis-Bacon Compliance Consulting | Angela | Reeves | a.reeves@dbcomplianceco.com | 202-555-0312 | Lead Auditor
National Testing Laboratory | Heather | Brooks | h.brooks@nationaltestlab.com | 202-555-0314 | Lab Director
DC Building Materials Supply | Curtis | Park | c.park@dcbuildsupply.com | 202-555-0313 | Account Manager
Acme Temporary Fencing & Site Services | Barry | Croft | b.croft@acmesite.com | 202-555-0315 | Regional Manager
Thornton Hartman Architects | Richard | Thornton | r.thornton@thorntonarch.com | 202-555-0206 | Principal Architect

## 06_equipment
name | equipment_type | make | model | serial_number | status | purchase_cost | hourly_rate | purchase_date | last_maintenance_date | next_maintenance_date
CAT 336 Next Gen Excavator | excavator | Caterpillar | 336 GC | CAT336GC-44102 | in_use | 0 | 225 | 2021-03-10 | 2025-12-18 | 2026-03-18
Manitowoc 3900W Tower Crane | crane | Manitowoc | 3900W | MAN3900W-88301 | in_use | 0 | 450 | 2019-09-15 | 2026-01-04 | 2027-01-04
CAT D6 XE Dozer | other | Caterpillar | D6 XE | CATD6XE-22948 | available | 0 | 195 | 2020-11-20 | 2025-10-15 | 2026-04-15
Mack Granite Dump Truck 1 | truck | Mack | Granite 64FR | MACK64FR-55001 | in_use | 0 | 95 | 2022-01-08 | 2025-12-10 | 2026-12-10
Mack Granite Dump Truck 2 | truck | Mack | Granite 64FR | MACK64FR-55002 | in_use | 0 | 95 | 2022-01-08 | 2025-12-10 | 2026-12-10
JLG 600S Boom Lift | other | JLG | 600S | JLG600S-11422 | in_use | 0 | 85 | 2021-07-14 | 2025-11-30 | 2026-11-30
Multiquip Generator 400kW | other | Multiquip | DCA400SSK | MQ400SSK-66180 | in_use | 0 | 65 | 2020-05-22 | 2025-09-15 | 2026-03-15
Putzmeister 58Z Concrete Pump | other | Putzmeister | 58Z Meter | PUT58Z-33901 | in_use | 0 | 280 | 2022-06-30 | 2026-01-07 | 2026-04-07

## 07_phases
name | color | start_date | end_date | project_name
Preconstruction & Permitting | #6b7280 | 2024-01-01 | 2024-01-31 | Federal District Courthouse & Public Safety Complex
Site Preparation & Mobilization | #92400e | 2024-02-01 | 2024-03-31 | Federal District Courthouse & Public Safety Complex
Earthwork & Underground Utilities | #b45309 | 2024-03-01 | 2024-09-30 | Federal District Courthouse & Public Safety Complex
Foundation & Substructure | #d97706 | 2024-06-01 | 2024-12-31 | Federal District Courthouse & Public Safety Complex
Structural Concrete & Steel | #ca8a04 | 2024-10-01 | 2025-09-30 | Federal District Courthouse & Public Safety Complex
Enclosure & Facade | #65a30d | 2025-04-01 | 2026-03-31 | Federal District Courthouse & Public Safety Complex
MEP Rough-In | #16a34a | 2024-08-01 | 2026-05-31 | Federal District Courthouse & Public Safety Complex
Interior Finishes | #0d9488 | 2025-10-01 | 2026-08-31 | Federal District Courthouse & Public Safety Complex
Commissioning & Closeout | #0284c7 | 2026-06-01 | 2026-09-30 | Federal District Courthouse & Public Safety Complex

## 08_tasks
name | phase_name | priority | start_date | end_date | completion_pct | is_milestone | is_critical_path | project_name | status
Building permit application and review | Preconstruction & Permitting | critical | 2024-01-01 | 2024-01-15 | 100 | false | true | Federal District Courthouse & Public Safety Complex | completed
Demolition permit and abatement survey | Preconstruction & Permitting | high | 2024-01-05 | 2024-01-20 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Environmental impact assessment - NEPA | Preconstruction & Permitting | high | 2024-01-01 | 2024-01-25 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
GSA pre-construction kickoff meeting | Preconstruction & Permitting | critical | 2024-01-15 | 2024-01-15 | 100 | true | true | Federal District Courthouse & Public Safety Complex | completed
Notice to proceed issued | Preconstruction & Permitting | critical | 2024-01-31 | 2024-01-31 | 100 | true | true | Federal District Courthouse & Public Safety Complex | completed
Construction fencing and site security | Site Preparation & Mobilization | high | 2024-02-01 | 2024-02-07 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Field office trailers and temp utilities | Site Preparation & Mobilization | high | 2024-02-05 | 2024-02-14 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Utility locates and protection | Site Preparation & Mobilization | high | 2024-02-07 | 2024-02-21 | 100 | false | true | Federal District Courthouse & Public Safety Complex | completed
Existing structure demolition | Site Preparation & Mobilization | critical | 2024-02-15 | 2024-03-15 | 100 | false | true | Federal District Courthouse & Public Safety Complex | completed
Tree removal and site clearing | Site Preparation & Mobilization | medium | 2024-02-15 | 2024-02-28 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Mobilization complete milestone | Site Preparation & Mobilization | critical | 2024-03-31 | 2024-03-31 | 100 | true | true | Federal District Courthouse & Public Safety Complex | completed
Mass excavation to subgrade | Earthwork & Underground Utilities | critical | 2024-03-01 | 2024-05-15 | 100 | false | true | Federal District Courthouse & Public Safety Complex | completed
Rock excavation and dewatering | Earthwork & Underground Utilities | high | 2024-03-15 | 2024-06-30 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Storm drainage installation | Earthwork & Underground Utilities | high | 2024-05-01 | 2024-07-31 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Sanitary sewer and water main | Earthwork & Underground Utilities | high | 2024-05-15 | 2024-08-15 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Electrical ductbank installation | Earthwork & Underground Utilities | high | 2024-06-01 | 2024-09-15 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Foundation preparation complete | Earthwork & Underground Utilities | critical | 2024-09-30 | 2024-09-30 | 100 | true | true | Federal District Courthouse & Public Safety Complex | completed
Drilled caissons 48in and 60in dia | Foundation & Substructure | critical | 2024-06-01 | 2024-08-31 | 100 | false | true | Federal District Courthouse & Public Safety Complex | completed
Pile caps and grade beams | Foundation & Substructure | critical | 2024-07-15 | 2024-10-15 | 100 | false | true | Federal District Courthouse & Public Safety Complex | completed
Foundation walls and waterproofing | Foundation & Substructure | high | 2024-08-15 | 2024-11-15 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Slab on grade Level B1 parking | Foundation & Substructure | high | 2024-09-01 | 2024-11-30 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Elevator pit and sump construction | Foundation & Substructure | medium | 2024-10-01 | 2024-12-15 | 100 | false | false | Federal District Courthouse & Public Safety Complex | completed
Foundation acceptance milestone | Foundation & Substructure | critical | 2024-12-31 | 2024-12-31 | 100 | true | true | Federal District Courthouse & Public Safety Complex | completed
Structural concrete Levels 1 through 6 | Structural Concrete & Steel | critical | 2024-10-01 | 2025-04-30 | 100 | false | true | Federal District Courthouse & Public Safety Complex | completed
Structural concrete Levels 7 through 12 | Structural Concrete & Steel | critical | 2025-02-01 | 2025-09-30 | 65 | false | true | Federal District Courthouse & Public Safety Complex | in_progress
Structural steel erection | Structural Concrete & Steel | critical | 2024-12-01 | 2025-08-31 | 80 | false | true | Federal District Courthouse & Public Safety Complex | in_progress
Metal deck and shear studs | Structural Concrete & Steel | high | 2025-01-15 | 2025-09-15 | 60 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
Topping out ceremony milestone | Structural Concrete & Steel | high | 2025-09-30 | 2025-09-30 | 0 | true | true | Federal District Courthouse & Public Safety Complex | not_started
Curtain wall system Levels 1 through 6 | Enclosure & Facade | critical | 2025-04-01 | 2025-12-31 | 70 | false | true | Federal District Courthouse & Public Safety Complex | in_progress
Curtain wall system Levels 7 through 12 | Enclosure & Facade | critical | 2025-08-01 | 2026-03-31 | 25 | false | true | Federal District Courthouse & Public Safety Complex | in_progress
Exterior masonry veneer | Enclosure & Facade | high | 2025-06-01 | 2026-01-31 | 55 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
Roofing and waterproofing | Enclosure & Facade | high | 2025-10-01 | 2026-02-28 | 40 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
Building enclosure weather-tight | Enclosure & Facade | critical | 2026-03-31 | 2026-03-31 | 0 | true | true | Federal District Courthouse & Public Safety Complex | not_started
Electrical rough-in Levels 1 through 6 | MEP Rough-In | critical | 2025-02-01 | 2025-10-31 | 60 | false | true | Federal District Courthouse & Public Safety Complex | in_progress
Plumbing rough-in | MEP Rough-In | high | 2025-03-01 | 2025-12-31 | 45 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
HVAC ductwork and equipment | MEP Rough-In | critical | 2025-04-01 | 2026-02-28 | 40 | false | true | Federal District Courthouse & Public Safety Complex | in_progress
Fire protection sprinkler rough-in | MEP Rough-In | high | 2025-06-01 | 2026-03-31 | 30 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
Elevator installation | MEP Rough-In | high | 2025-08-01 | 2026-05-31 | 15 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
Security system conduit and backbone | MEP Rough-In | high | 2025-10-01 | 2026-04-30 | 10 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
Drywall framing and hanging Levels 1-3 | Interior Finishes | high | 2025-10-01 | 2026-03-31 | 25 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
Courtroom millwork and paneling | Interior Finishes | high | 2026-01-01 | 2026-06-30 | 5 | false | false | Federal District Courthouse & Public Safety Complex | in_progress
Lobby stone and tile finishes | Interior Finishes | medium | 2026-02-01 | 2026-07-31 | 0 | false | false | Federal District Courthouse & Public Safety Complex | not_started
Paint and wall coverings | Interior Finishes | medium | 2026-03-01 | 2026-08-15 | 0 | false | false | Federal District Courthouse & Public Safety Complex | not_started
Flooring carpet tile and terrazzo | Interior Finishes | medium | 2026-04-01 | 2026-08-31 | 0 | false | false | Federal District Courthouse & Public Safety Complex | not_started
Commissioning plan and TAB | Commissioning & Closeout | critical | 2026-06-01 | 2026-08-31 | 0 | false | true | Federal District Courthouse & Public Safety Complex | not_started
Final inspections and punch list | Commissioning & Closeout | critical | 2026-07-01 | 2026-09-15 | 0 | false | true | Federal District Courthouse & Public Safety Complex | not_started
Security system commissioning and testing | Commissioning & Closeout | high | 2026-07-15 | 2026-09-15 | 0 | false | false | Federal District Courthouse & Public Safety Complex | not_started
Certificate of occupancy milestone | Commissioning & Closeout | critical | 2026-09-30 | 2026-09-30 | 0 | true | true | Federal District Courthouse & Public Safety Complex | not_started

## 09_project_budget_lines
csi_code | description | budgeted_amount | committed_amount | actual_amount | project_name
01 00 00 | General Requirements & Project Management | 4800000 | 4500000 | 2600000 | Federal District Courthouse & Public Safety Complex
02 00 00 | Existing Conditions & Demolition | 850000 | 820000 | 820000 | Federal District Courthouse & Public Safety Complex
03 00 00 | Concrete | 7200000 | 7200000 | 5200000 | Federal District Courthouse & Public Safety Complex
04 00 00 | Masonry | 2900000 | 2900000 | 1566000 | Federal District Courthouse & Public Safety Complex
05 00 00 | Metals - Structural Steel | 8500000 | 8500000 | 7650000 | Federal District Courthouse & Public Safety Complex
06 00 00 | Wood Plastics & Composites | 1200000 | 1100000 | 400000 | Federal District Courthouse & Public Safety Complex
07 00 00 | Thermal & Moisture Protection | 2650000 | 2450000 | 1200000 | Federal District Courthouse & Public Safety Complex
08 00 00 | Openings - Doors Windows Curtain Wall | 4200000 | 3800000 | 2100000 | Federal District Courthouse & Public Safety Complex
09 00 00 | Finishes | 3600000 | 3200000 | 864000 | Federal District Courthouse & Public Safety Complex
10 00 00 | Specialties | 800000 | 700000 | 0 | Federal District Courthouse & Public Safety Complex
11 00 00 | Equipment - Courtroom Systems | 2400000 | 2100000 | 0 | Federal District Courthouse & Public Safety Complex
12 00 00 | Furnishings | 1800000 | 1600000 | 0 | Federal District Courthouse & Public Safety Complex
14 00 00 | Conveying Equipment - Elevators | 2200000 | 2000000 | 600000 | Federal District Courthouse & Public Safety Complex
21 00 00 | Fire Suppression | 1600000 | 1600000 | 288000 | Federal District Courthouse & Public Safety Complex
22 00 00 | Plumbing | 3200000 | 3000000 | 1400000 | Federal District Courthouse & Public Safety Complex
23 00 00 | HVAC | 4200000 | 4000000 | 1850000 | Federal District Courthouse & Public Safety Complex
26 00 00 | Electrical | 6800000 | 6800000 | 3400000 | Federal District Courthouse & Public Safety Complex
28 00 00 | Electronic Safety & Security | 2400000 | 2400000 | 432000 | Federal District Courthouse & Public Safety Complex
31 00 00 | Earthwork | 3800000 | 3800000 | 3800000 | Federal District Courthouse & Public Safety Complex
32 00 00 | Exterior Improvements | 1500000 | 1200000 | 0 | Federal District Courthouse & Public Safety Complex
33 00 00 | Utilities | 1600000 | 1500000 | 1200000 | Federal District Courthouse & Public Safety Complex
01 40 00 | Davis-Bacon & Section 3 Compliance | 500000 | 350000 | 231000 | Federal District Courthouse & Public Safety Complex

## 10_certifications
cert_name | cert_type | issuing_authority | cert_number | issued_date | expiry_date | contact_name
OSHA 30-Hour Construction Safety | certification | OSHA | OSHA30-2024-FCD-001 | 2023-06-15 | 2028-06-15 | James Whitfield
OSHA 30-Hour Construction Safety | certification | OSHA | OSHA30-2024-FCD-002 | 2023-08-10 | 2028-08-10 | Marcus Delaney
OSHA 30-Hour Construction Safety | certification | OSHA | OSHA30-2024-FCD-003 | 2023-07-20 | 2028-07-20 | Daniel Hargrove
OSHA 30-Hour Construction Safety | certification | OSHA | OSHA30-2024-FCD-004 | 2023-09-01 | 2028-09-01 | Kevin Osei
OSHA 30-Hour Construction Safety | certification | OSHA | OSHA30-2024-FCD-005 | 2024-01-15 | 2029-01-15 | Raymond Torres
EM-385-1-1 USACE Safety | certification | US Army Corps of Engineers | EM385-FCD-001 | 2023-04-20 | 2026-04-20 | Raymond Torres
GSA Federal Construction Safety | certification | General Services Administration | GSA-SAFE-44210 | 2023-04-15 | 2026-04-15 | Raymond Torres
Davis-Bacon Compliance Specialist | certification | Dept of Labor | DBA-SPEC-2024-107 | 2024-02-01 | 2027-02-01 | Brenda Walsh
Section 3 Compliance Officer | certification | HUD | SEC3-OFF-2024-042 | 2024-03-10 | 2027-03-10 | Brenda Walsh
LEED AP BD+C | certification | USGBC | LEED-AP-10295847 | 2022-05-15 | 2026-05-15 | Patricia Nguyen
PMP - Project Management Professional | certification | PMI | PMI-PMP-3347891 | 2021-07-01 | 2027-07-01 | Daniel Hargrove
PMP - Project Management Professional | certification | PMI | PMI-PMP-4421567 | 2022-09-01 | 2028-09-01 | Linda Castillo
Tower Crane Operator NCCCO | certification | NCCCO | NCCCO-TC-88401 | 2023-03-20 | 2028-03-20 | Kevin Osei
FAR/DFARS Compliance | certification | DAU | FAR-DFAR-2024-210 | 2024-01-01 | 2027-01-01 | Angela Petrov
SECRET Security Clearance | license | US Dept of Defense | SCL-DOD-FCD-001 | 2023-01-15 | 2033-01-15 | James Whitfield
SECRET Security Clearance | license | US Dept of Defense | SCL-DOD-FCD-002 | 2023-06-01 | 2033-06-01 | Marcus Delaney
AWS CWI - Certified Welding Inspector | certification | American Welding Society | AWS-CWI-78902 | 2024-06-01 | 2027-06-01 | Russell Yamamoto
ACI Concrete Field Testing Technician | certification | American Concrete Institute | ACI-CFT-44210 | 2024-03-15 | 2027-03-15 | Michael Brennan

## 11_opportunities
name | client_name | stage | estimated_value | probability_pct | expected_close_date | source | notes
VA Medical Center Expansion - Richmond | Dept of Veterans Affairs | proposal | 95000000 | 70 | 2026-05-15 | direct | New inpatient tower and ambulatory care expansion at Richmond VAMC. Phased construction maintaining full hospital operations. Design-build delivery. Section 3 and Service-Disabled Veteran-Owned SB subcontracting plan required.
FEMA Regional Operations Center | Federal Emergency Management Agency | negotiation | 42000000 | 88 | 2026-03-01 | direct | Category 5 hurricane-hardened emergency operations facility in Atlanta GA. Redundant power water and communications. 72-hour self-sustaining capability. GSA lease-construct. LEED Silver minimum.
Dept of Labor HQ Renovation - Phase 2 | U.S. Dept of Labor | qualified | 28500000 | 55 | 2026-08-01 | referral | Floors 8-14 modernization of Frances Perkins Building. Occupied renovation phasing. Asbestos abatement. Historic preservation requirements under Section 106. Davis-Bacon prevailing wage applies.
State Police Regional Headquarters | State Dept of Public Safety | proposal | 34000000 | 65 | 2026-06-01 | direct | New 85000 SF regional headquarters with secure vehicle storage forensic lab and regional dispatch center. SCIF requirements for intelligence section. Blast-resistant design per ISC.
HUD CDBG Civic Center & Library | U.S. Dept of Housing & Urban Development | won | 18500000 | 95 | 2026-04-01 | partner | Community civic center with branch library and job training center. 100% CDBG-funded. Section 3 hiring plan critical. Must demonstrate 25% low-income workforce participation. LEED Gold target.

## 12_bids
project_name | client_name | bid_amount | due_date | bid_type | notes
VA Medical Center Expansion - Richmond | Dept of Veterans Affairs | 97000000 | 2026-03-15 | hard_bid | New 6-story inpatient tower with 120 beds 42 operating suites and ambulatory care pavilion. Includes central utility plant upgrade. 36-month construction duration. Full infection control risk assessment required. TAA-compliant materials. All-domestic steel per Buy America Act.
FEMA Regional Operations Center | Federal Emergency Management Agency | 43500000 | 2026-02-28 | negotiated | 72000 SF emergency operations center with 400kW backup generator farm 30000-gallon fuel storage and communications bunker. Category 5 wind resistant envelope. 24-month construction. SBA subcontracting plan 23% SDB goal.
State Police Regional Headquarters | State Dept of Public Safety | 35200000 | 2026-05-01 | hard_bid | 85000 SF facility with SCIF vehicle maintenance bay forensic evidence processing lab and EOC. Ballistic glazing level 4 at all ground floor. Anti-ram barriers at perimeter. 28-month construction. MBE/WBE 15% goal.

## 13_contracts
title | contract_type | party_name | party_email | contract_amount | start_date | end_date | payment_terms | scope_of_work | project_name | status
GSA Prime Contract - Federal District Courthouse | owner | U.S. General Services Administration | t.jefferson@gsa.gov | 68500000 | 2024-02-01 | 2026-09-30 | net_30 | Design-bid-build prime contract for new 12-story federal courthouse. Includes all site work structure enclosure MEP finishes and commissioning. Davis-Bacon and Section 3 apply. Miller Act performance and payment bonds required. 10% retainage until substantial completion. | Federal District Courthouse & Public Safety Complex | active
Earthwork & Site Preparation | subcontractor | Eagle Excavation LLC | h.nkemelu@eagleexcavation.com | 3800000 | 2024-02-01 | 2024-09-30 | net_30 | Mass excavation rock removal dewatering underground utilities storm drainage and backfill. | Federal District Courthouse & Public Safety Complex | active
Cast-in-Place Concrete | subcontractor | Nationwide Concrete Inc | t.bassett@nationwideconcrete.com | 7200000 | 2024-06-01 | 2025-12-31 | net_30 | All structural concrete including foundations caissons pile caps elevated slabs columns and shear walls. Formwork rebar and placement. | Federal District Courthouse & Public Safety Complex | active
Structural Steel Erection | subcontractor | Federal Steel Erectors | j.kessler@federalsteel.com | 8500000 | 2024-12-01 | 2025-09-30 | net_30 | Fabrication delivery and erection of structural steel including columns beams bracing metal deck and shear studs. | Federal District Courthouse & Public Safety Complex | active
Electrical Systems | subcontractor | Patriot Electrical Contractors | s.drummond@patriotelectric.com | 6800000 | 2025-02-01 | 2026-08-31 | net_30 | Complete electrical power distribution emergency generators switchgear MCC panels branch wiring lighting and fire alarm. | Federal District Courthouse & Public Safety Complex | active
Mechanical & Plumbing | subcontractor | Capital MEP Group | c.merritt@capitalmep.com | 7400000 | 2025-03-01 | 2026-08-31 | net_30 | Complete HVAC systems including chillers boilers AHUs ductwork controls and plumbing including domestic water sanitary waste medical gas and natural gas. | Federal District Courthouse & Public Safety Complex | active
Masonry | subcontractor | Monument Masonry Corp | d.altman@monumentmasonry.com | 2900000 | 2025-06-01 | 2026-01-31 | net_30 | Exterior brick and limestone veneer CMU backup walls interior CMU partitions and stone site walls. | Federal District Courthouse & Public Safety Complex | active
Roofing & Waterproofing | subcontractor | Capitol Roofing Systems | l.vandenberg@capitolroofing.com | 1850000 | 2025-10-01 | 2026-02-28 | net_30 | TPO membrane roofing system metal edge copings green roof assemblies and below-grade waterproofing. | Federal District Courthouse & Public Safety Complex | active
Drywall & Framing | subcontractor | Union Drywall & Framing | v.asamoah@uniondrywall.com | 3200000 | 2025-10-01 | 2026-07-31 | net_30 | Metal stud framing drywall hanging taping acoustical ceilings and soffits. | Federal District Courthouse & Public Safety Complex | active
Security Systems Integration | subcontractor | SafeGuard Security Integration | p.monroe@safeguardsec.com | 2400000 | 2025-08-01 | 2026-08-31 | net_30 | Access control CCTV intrusion detection x-ray screening magnetometers sally ports and courtroom duress systems. | Federal District Courthouse & Public Safety Complex | active
Fire Protection | subcontractor | Apex Fire Protection LLC | g.flanagan@apexfire.com | 1600000 | 2025-06-01 | 2026-06-30 | net_30 | Wet and dry sprinkler systems pre-action systems for IT and records fire pump and standpipe. | Federal District Courthouse & Public Safety Complex | active
Elevators | subcontractor | Potomac Elevator Co | m.cruz@potomacelevator.com | 2200000 | 2025-08-01 | 2026-08-31 | net_30 | 6 passenger elevators 2 freight elevators and 1 secure prisoner transport elevator. All traction type. | Federal District Courthouse & Public Safety Complex | active
Structural Engineering Services | consultant | Huang Structural Engineering | w.huang@huangstructural.com | 485000 | 2024-02-01 | 2026-09-30 | net_30 | Structural engineering support during construction including shop drawing review RFI responses field inspections and special inspections. | Federal District Courthouse & Public Safety Complex | active
Davis-Bacon Compliance Auditing | consultant | Davis-Bacon Compliance Consulting | a.reeves@dbcomplianceco.com | 185000 | 2024-02-01 | 2026-09-30 | net_30 | Weekly certified payroll review Davis-Bacon wage interviews labor classification audits and DOL reporting. | Federal District Courthouse & Public Safety Complex | active
Testing & Inspection Services | consultant | National Testing Laboratory | h.brooks@nationaltestlab.com | 320000 | 2024-02-01 | 2026-09-30 | net_30 | Concrete testing steel inspection soils testing fireproofing inspection and special inspections. | Federal District Courthouse & Public Safety Complex | active
Architectural Services During Construction | consultant | Thornton Hartman Architects | r.thornton@thorntonarch.com | 750000 | 2024-02-01 | 2026-09-30 | net_30 | Architect of record construction administration including submittal review RFI responses site observations and punch list. | Federal District Courthouse & Public Safety Complex | active

## 14_daily_logs
log_date | weather_conditions | temperature | work_performed | safety_incidents | delays | project_name | status
2026-01-06 | clear | 34 | Steel erection Levels 10-11 continued with 6 columns and 12 beams set. Concrete pour Level 8 east wing 380 CY pumped. Curtain wall installation Levels 4-5 south facade 8 panels set. MEP rough-in Level 3 electrical conduit 75% complete. 218 workers on site. | None | None | Federal District Courthouse & Public Safety Complex | submitted
2026-01-07 | cloudy | 38 | Concrete finishing Level 8 east wing. Steel bolting Level 10 connections torqued. Masonry veneer Level 3 north facade 1200 SF installed. Curtain wall Level 5 continued 6 panels. Fire sprinkler rough-in Level 2 80% complete. 224 workers on site. | None | None | Federal District Courthouse & Public Safety Complex | submitted
2026-01-08 | clear | 31 | Metal deck placement Level 11 started. Concrete Level 7 west wing forming. Curtain wall glazing Level 3 complete. Electrical switchgear Level B1 energized and tested. Plumbing riser Level 4-6 copper brazing. 230 workers on site. | None | None | Federal District Courthouse & Public Safety Complex | submitted
2026-01-09 | rainy | 36 | Rain delay first 2 hours - crane operations suspended. Steel erection resumed at 1000. Concrete forming Level 7 continued under tarps. Interior drywall framing Level 1 courtrooms started. Davis-Bacon wage interviews conducted by compliance team - 12 workers interviewed. 198 workers on site. | None | Rain delay 2 hours morning - crane standby | Federal District Courthouse & Public Safety Complex | submitted
2026-01-10 | clear | 29 | Structural concrete pour Level 7 west wing 420 CY. 4 concrete test cylinders taken. Steel erection Level 11 north bay 8 columns set. Elevator shaft construction Level 5-6. Roofing membrane prep Level 12 mechanical penthouse area. Section 3 compliance report submitted to HUD. 215 workers on site. | None | None | Federal District Courthouse & Public Safety Complex | submitted
2026-01-13 | cloudy | 33 | Steel topping out ceremony preparation - Level 12 final columns scheduled this week. Metal deck Level 11 50% complete. Curtain wall Level 6 south facade started. HVAC ductwork Level 2 main trunk lines 60% installed. Masonry veneer Level 4 east facade 800 SF. GSA COR site observation visit. 222 workers on site. | None | None | Federal District Courthouse & Public Safety Complex | submitted
2026-01-14 | clear | 28 | Level 12 final structural steel column set - topping out achieved. Ironworkers celebration. Concrete Level 9 east wing rebar placement. Curtain wall Level 6 continued 10 panels. Electrical rough-in Level 3 branch circuits. Security conduit backbone Level B1 started. 226 workers on site. | Near miss - dropped bolt from Level 11. Area cleared. Safety stand-down conducted. | None | Federal District Courthouse & Public Safety Complex | submitted
2026-01-15 | clear | 30 | Post-topping steel connections Level 12. Concrete forming Level 9 west wing. Curtain wall sealant Level 3-4 all joints. Plumbing rough-in Level 4 restroom groups. Fire sprinkler Level 3 100% hung. Drywall Level 1 courtroom A framing 40% complete. 220 workers on site. | None | None | Federal District Courthouse & Public Safety Complex | submitted
2026-01-16 | snow | 25 | Snow event - reduced operations. Crane operations suspended until afternoon. Ground crews performed snow removal and salting. Interior work continued at full pace - drywall MEP electrical. Steel connections Level 12 continued. Davis-Bacon certified payroll #48 submitted. 185 workers on site. | None | Snow delay - crane suspended AM shift | Federal District Courthouse & Public Safety Complex | submitted
2026-01-17 | clear | 27 | Full operations resumed. Concrete pour Level 9 east wing 390 CY. Metal deck Level 12 started 20% first day. Curtain wall Level 7 north facade 4 panels. HVAC Level 3 branch ductwork. Electrical panel boards Level 2 mounted. Elevator guide rails Level 3-4 installed. 228 workers on site. | None | None | Federal District Courthouse & Public Safety Complex | submitted

## 15_rfis
subject | question | priority | status | due_date | cost_impact | schedule_impact_days | project_name | assigned_to | answer
Secure Holding Door Hardware Specification Conflict | Drawing A-401 specifies Grade 1 mortise lock set rated to 600 lb while the security narrative requires 1000 lb minimum for all holding area doors. Which specification governs? | high | submitted | 2026-02-01 | 12000 | 3 | Federal District Courthouse & Public Safety Complex
Courtroom Acoustic Panel Substrate Mismatch | Specification 09 84 00 calls for 1 inch acoustic panels on 5/8 inch gypsum board but structural drawings show 6 inch CMU at courtroom walls. Furring strips not detailed. Clarify attachment method and confirm acoustic performance. | high | submitted | 2026-02-10 | 8500 | 2 | Federal District Courthouse & Public Safety Complex
Emergency Generator Fuel Storage NFPA 30 Setback | Generator fuel day tank 500 gallon diesel located 12 feet from building per site plan. NFPA 30 requires 25 foot minimum setback for above-ground storage adjacent to buildings. Confirm relocation or request variance from AHJ. | critical | submitted | 2026-01-28 | 385000 | 12 | Federal District Courthouse & Public Safety Complex
LEED Credit Documentation Version Conflict | Specification references LEED v3 2009 thresholds but GSA Facilities Standards require LEED v4. Recycled content credit thresholds differ. Which version controls for credit achievement calculations? | medium | submitted | 2026-02-20 | 0 | 0 | Federal District Courthouse & Public Safety Complex
Section 3 Workforce Tracking Integration | How should Section 3 workforce hours be tracked alongside Davis-Bacon certified payroll? Current system tracks separately but HUD requires integrated reporting for CDBG-funded portions. Clarify acceptable reporting format. | medium | answered | 2026-02-15 | 0 | 0 | Federal District Courthouse & Public Safety Complex |  | Coordinate with Brenda Walsh to use integrated WH-347 form supplemented with Section 3 certification data. Monthly report to HUD per CDBG grant agreement Section 8.
Elevator Cab Interior Finish Discrepancy | Architectural drawings show stainless steel elevator cab interiors but specification 14 20 00 calls for laminate panels. Secure prisoner transport elevator requires anti-ligature design not addressed in either document. Clarify all three cab types. | high | submitted | 2026-02-05 | 45000 | 5 | Federal District Courthouse & Public Safety Complex

## 16_change_orders
title | description | reason | amount | schedule_impact_days | project_name | status | co_number
CO-001 Secure Holding Expansion 48 to 72 Capacity | GSA directed expansion of secure holding facility from 48 to 72 person capacity per updated federal marshals operational requirements. Additional 3200 SF of hardened construction with blast-resistant partitions sally port expansion and enhanced CCTV coverage. | owner_request | 1850000 | 21 | Federal District Courthouse & Public Safety Complex | draft | CO-001
CO-002 Blast-Resistant Glazing Upgrade | Upgrade all ground floor and Level 2 glazing from standard insulated glass to blast-resistant laminated glass per updated ISC security criteria. Includes reinforced curtain wall anchors and blast-rated mullion profiles. | owner_request | 2400000 | 15 | Federal District Courthouse & Public Safety Complex | draft | CO-002
CO-003 Emergency Generator Relocation | Relocate emergency generator farm from east side to north side of building to comply with NFPA 30 setback requirements identified during RFI-003 review. Includes new concrete pad fuel piping and electrical feeder relocation. | error_omission | 385000 | 12 | Federal District Courthouse & Public Safety Complex | draft | CO-003
CO-004 HVAC Filtration Upgrade MERV-13 to MERV-16 | Upgrade all AHU filtration from MERV-13 to MERV-16 per updated GSA Indoor Air Quality standards. Includes fan motor upgrades to handle increased static pressure and modified ductwork transitions. | owner_request | 620000 | 8 | Federal District Courthouse & Public Safety Complex | draft | CO-004
CO-005 Fiber Optic Network Infrastructure | Add dedicated fiber optic backbone network throughout building for federal agency connectivity. 144-strand single mode fiber risers to each floor with redundant pathways. Separate from base building data cabling. | owner_request | 480000 | 5 | Federal District Courthouse & Public Safety Complex | draft | CO-005
CO-006 Granite Facade Upgrade from Limestone | Upgrade exterior facade cladding from Indiana limestone to Barre Gray granite per Architect recommendation and GSA approval. Improved durability and lower lifecycle maintenance cost. Includes revised stone anchorage details. | scope_change | 1100000 | 10 | Federal District Courthouse & Public Safety Complex | draft | CO-006
CO-007 Section 3 Training Laboratory | Add 3200 SF workforce training laboratory on Level 1 per HUD CDBG grant requirements. Includes classroom space computer lab tool storage and instructor office. Supports Section 3 hiring goal achievement. | owner_request | 750000 | 7 | Federal District Courthouse & Public Safety Complex | draft | CO-007

## 17_submittals
title | submittal_number | project_name | spec_section | status | due_date | review_comments
Concrete Mix Design - 6000 PSI Structural | SUB-001 | Federal District Courthouse & Public Safety Complex | 03 30 00 | approved_as_submitted | 2024-05-15 | Mix design acceptable per ACI 318-19. Provide test data at 7 and 28 days.
Structural Steel Shop Drawings - Levels 1-6 | SUB-002 | Federal District Courthouse & Public Safety Complex | 05 12 00 | approved_as_noted | 2024-10-01 | Revise connection details at moment frames per RFI-001 response. Resubmit details 5A and 5B.
Curtain Wall System - Mock-Up Approval | SUB-003 | Federal District Courthouse & Public Safety Complex | 08 44 00 | approved_as_submitted | 2025-02-15 | Mock-up panel passed water and air infiltration testing per ASTM E1105.
HVAC Equipment - Chillers and Boilers | SUB-004 | Federal District Courthouse & Public Safety Complex | 23 60 00 | approved_as_noted | 2025-01-20 | Sound data requires additional vibration isolation at Level 12 mechanical room. Revise structural supports.
Elevator Equipment and Cab Finishes | SUB-005 | Federal District Courthouse & Public Safety Complex | 14 20 00 | pending | 2026-02-01
Fire Sprinkler Shop Drawings - Levels 1-4 | SUB-006 | Federal District Courthouse & Public Safety Complex | 21 13 00 | approved_as_submitted | 2025-05-01 | Hydraulic calculations acceptable. Proceed with fabrication.
Security System - Access Control Hardware | SUB-007 | Federal District Courthouse & Public Safety Complex | 28 10 00 | pending | 2026-02-15
Blast-Resistant Glazing - Product Data | SUB-008 | Federal District Courthouse & Public Safety Complex | 08 88 00 | approved_as_submitted | 2025-09-01 | Glazing meets GSA blast resistance criteria Level C per ISC.
Granite Facade Cladding - Samples and Shop Drawings | SUB-009 | Federal District Courthouse & Public Safety Complex | 04 42 00 | approved_as_noted | 2025-11-15 | Color range acceptable. Provide anchoring detail revisions per structural engineer comments.
Courtroom Millwork - Shop Drawings | SUB-010 | Federal District Courthouse & Public Safety Complex | 06 40 00 | pending | 2026-03-01

## 18_safety_incidents
title | description | incident_type | severity | incident_date | location | osha_recordable | project_name | status
Near Miss - Dropped Bolt from Level 8 | Ironworker dropped 3/4 inch bolt from Level 8 during connection work. Bolt struck unoccupied scaffolding platform. Area below was properly barricaded per steel erection plan. No injury or property damage. | near_miss | minor | 2025-09-15 | Level 8 south elevation | false | Federal District Courthouse & Public Safety Complex | resolved
First Aid - Laceration from Sheet Metal Edge | Drywall framer sustained 2-inch laceration on forearm from sharp metal stud edge. First aid administered on site. Worker returned to duty same day with butterfly bandage. Glove use reinforced in safety briefing. | injury | minor | 2025-11-22 | Level 2 courtroom wing | true | Federal District Courthouse & Public Safety Complex | resolved
Near Miss - Mortar Debris from Scaffold | Small amount of mortar debris fell from masonry scaffold on Level 4 exterior. Debris landed in barricaded exclusion zone. No injuries. Scaffold toe boards inspected and found adequate. Additional netting installed as precaution. | near_miss | minor | 2025-12-08 | Level 4 north facade | false | Federal District Courthouse & Public Safety Complex | resolved
Near Miss - Dropped Bolt from Level 11 | During final steel connections at Level 11 a high-strength bolt was dropped. Area below was barricaded and occupied by no personnel. Safety stand-down conducted immediately for all ironwork crews. Tool tethering protocol reinforced. | near_miss | minor | 2026-01-14 | Level 11 north bay | false | Federal District Courthouse & Public Safety Complex | resolved

## 19_safety_inspections
inspection_type | inspection_date | score | findings | corrective_actions | status | project_name
site_safety | 2026-01-06 | 91 | General site safety inspection. PPE compliance 97%. Housekeeping good. Fall protection at Level 10 perimeter verified. One citation: missing fire extinguisher tag at Level 3 tool crib. | Replace expired fire extinguisher tag. Verified next day. | completed | Federal District Courthouse & Public Safety Complex
equipment | 2026-01-08 | 94 | Equipment inspection all tower crane excavator and aerial lifts. Annual certifications current. Daily inspection logs complete. Wire rope condition good. No deficiencies noted. | None required. All equipment in compliance. | completed | Federal District Courthouse & Public Safety Complex
fall_protection | 2026-01-13 | 88 | Federal compliance audit - Davis-Bacon prevailing wage interview results reviewed 12 of 12 workers in compliance. Section 3 workforce participation at 8.2% against 25% goal needs improvement. LEED tracking documentation current. | Increase Section 3 outreach per CO-007 training lab initiative. Schedule additional HUD coordination meeting. | completed | Federal District Courthouse & Public Safety Complex
site_safety | 2025-10-22 | 82 | Unannounced OSHA compliance inspection. Citation issued for inadequate guardrail at Level 7 floor opening subsequently corrected same day. Cable railing system replaced with standard 42-inch top rail mid rail and toe board assembly. | Guardrail deficiency corrected within 2 hours. Photographic documentation provided to OSHA. No penalty assessed. | completed | Federal District Courthouse & Public Safety Complex

## 20_toolbox_talks
title | description | topic | scheduled_date | attendees_count | notes | project_name | status
Fall Protection and Leading Edge Work | Review of fall protection requirements for structural steel and concrete forming operations at height. Emphasis on 100% tie-off requirement personal fall arrest system inspection and rescue planning per OSHA 1926 Subpart M. | fall_protection | 2026-01-06 | 48 | Focused on ironworkers masonry and concrete crews working at Levels 8-12. Demonstrated proper harness inspection procedure. | Federal District Courthouse & Public Safety Complex | conducted
Davis-Bacon Prevailing Wage Rights | Worker rights under Davis-Bacon Act including prevailing wage rates fringe benefits overtime provisions and complaint procedures. Led by Davis-Bacon Compliance Consulting. | hazard_communication | 2026-01-08 | 85 | All trades required to attend quarterly. Compliance consultant Angela Reeves led session. Worker classification Q&A conducted. | Federal District Courthouse & Public Safety Complex | conducted
Section 3 Employment and Training Overview | Overview of HUD Section 3 requirements for CDBG-funded projects. Hiring preferences training opportunities and documentation requirements. HUD Program Manager Frank Sloane attended. | hazard_communication | 2026-01-09 | 62 | Introduced upcoming Section 3 Training Lab CO-007. Enrollment forms distributed for pre-apprenticeship program. | Federal District Courthouse & Public Safety Complex | conducted
Electrical Safety and LOTO Procedures | Lockout tagout procedures for energized electrical systems. Arc flash hazard awareness and PPE requirements per NFPA 70E. Specific focus on switchgear energization at Level B1. | electrical | 2026-01-13 | 32 | Electricians and MEP crews. Reviewed arc flash boundary distances and incident energy calculations for new switchgear. | Federal District Courthouse & Public Safety Complex | conducted
Confined Space Entry - Elevator Shafts | Confined space entry procedures for elevator shaft work including atmospheric monitoring entry permits rescue procedures and communication protocols. Per OSHA 1910.146 and 1926 Subpart AA. | ppe | 2026-01-15 | 28 | Elevator installation crew and safety personnel. Hands-on atmospheric monitor calibration demonstrated. | Federal District Courthouse & Public Safety Complex | conducted

## 21_time_entries
entry_date | hours | overtime_hours | description | cost_code | project_name | status
2026-01-06 | 10 | 2 | Project management - steel erection coordination Levels 10-11 and concrete pour Level 8 oversight | 01400 | Federal District Courthouse & Public Safety Complex | approved
2026-01-06 | 8 | 0 | Quality control inspections - concrete cylinders Level 8 and weld inspections Level 10 | 01450 | Federal District Courthouse & Public Safety Complex | approved
2026-01-06 | 10 | 2 | Superintendent field operations - 218 workers coordinated across all active areas | 01100 | Federal District Courthouse & Public Safety Complex | approved
2026-01-07 | 10 | 2 | PM coordination - curtain wall Level 5 masonry Level 3 fire sprinkler Level 2 | 01400 | Federal District Courthouse & Public Safety Complex | approved
2026-01-07 | 8 | 0 | Safety inspections and PPE compliance monitoring - all active floors | 01500 | Federal District Courthouse & Public Safety Complex | approved
2026-01-08 | 10 | 2 | Superintendent field ops - switchgear energization Level B1 and metal deck Level 11 | 01100 | Federal District Courthouse & Public Safety Complex | approved
2026-01-08 | 8 | 0 | BIM coordination - clash detection review MEP vs structure Levels 4-6 | 01310 | Federal District Courthouse & Public Safety Complex | approved
2026-01-09 | 8 | 0 | Davis-Bacon compliance - wage interviews 12 workers and certified payroll review | 01410 | Federal District Courthouse & Public Safety Complex | approved
2026-01-09 | 6 | 0 | Rain delay - crane operations suspended AM. Interior work coordination afternoon. | 01100 | Federal District Courthouse & Public Safety Complex | approved
2026-01-10 | 10 | 2 | PM - concrete pour Level 7 west wing 420 CY and steel erection Level 11 | 01400 | Federal District Courthouse & Public Safety Complex | approved
2026-01-10 | 8 | 0 | Section 3 outreach - community hiring event planning and compliance report to HUD | 01410 | Federal District Courthouse & Public Safety Complex | approved
2026-01-13 | 10 | 2 | Superintendent - topping out prep and Level 12 final columns coordination | 01100 | Federal District Courthouse & Public Safety Complex | approved
2026-01-13 | 8 | 1 | Project engineer - structural steel inspection Level 12 and shop drawing review | 05100 | Federal District Courthouse & Public Safety Complex | approved
2026-01-14 | 10 | 2 | PM - topping out milestone and curtain wall Level 6 installation oversight | 01400 | Federal District Courthouse & Public Safety Complex | approved
2026-01-14 | 8 | 0 | Safety stand-down after near miss - dropped bolt Level 11. All crews briefed. | 01500 | Federal District Courthouse & Public Safety Complex | approved
2026-01-15 | 10 | 2 | Superintendent - concrete Level 9 forming and fire sprinkler Level 3 completion | 01100 | Federal District Courthouse & Public Safety Complex | approved
2026-01-15 | 8 | 0 | Document control - submittal log update and RFI tracking for CO-003 response | 01300 | Federal District Courthouse & Public Safety Complex | approved
2026-01-16 | 6 | 0 | Snow delay operations - reduced crew. Interior work coordination and safety walkthrough. | 01100 | Federal District Courthouse & Public Safety Complex | approved
2026-01-16 | 8 | 0 | Cost control - January progress billing preparation and change order pricing review | 01200 | Federal District Courthouse & Public Safety Complex | approved
2026-01-17 | 10 | 2 | PM - full operations resumed. Concrete Level 9 pour and metal deck Level 12 | 01400 | Federal District Courthouse & Public Safety Complex | approved

## 22_equipment_assignments
equipment_name | project_name | assigned_date | return_date | notes | status
CAT 336 Next Gen Excavator | Federal District Courthouse & Public Safety Complex | 2024-02-15 |  | Foundation and utility excavation. Relocated to interior demolition and loading. | active
Manitowoc 3900W Tower Crane | Federal District Courthouse & Public Safety Complex | 2024-06-01 |  | Primary tower crane for structural steel and concrete placement all levels. | active
CAT D6 XE Dozer | Federal District Courthouse & Public Safety Complex | 2024-02-15 | 2024-10-30 | Site grading and earthwork. Demobilized after foundation backfill complete. | returned
Mack Granite Dump Truck 1 | Federal District Courthouse & Public Safety Complex | 2024-02-15 |  | Hauling excavation spoils and site logistics. | active
Mack Granite Dump Truck 2 | Federal District Courthouse & Public Safety Complex | 2024-02-15 |  | Material delivery and debris removal. | active
JLG 600S Boom Lift | Federal District Courthouse & Public Safety Complex | 2024-10-01 |  | Facade work access and high-elevation inspections. | active
Multiquip Generator 400kW | Federal District Courthouse & Public Safety Complex | 2024-02-15 |  | Temporary site power until permanent service. | active
Putzmeister 58Z Concrete Pump | Federal District Courthouse & Public Safety Complex | 2024-06-01 |  | Concrete placement all elevated levels. | active

## 23_equipment_maintenance
equipment_name | title | maintenance_type | description | maintenance_date | cost | performed_by | vendor_name | next_due_date | status
Manitowoc 3900W Tower Crane | Annual Load Test and Inspection | preventive | Annual OSHA and manufacturer required load test at 110% capacity. All wire ropes inspected and measured. Boom and jib pins checked. Electrical systems verified. Passed all tests. | 2026-01-04 | 18500 | CraneTech Services | CraneTech Inspection Services | 2027-01-04 | completed
CAT 336 Next Gen Excavator | 1000-Hour Preventive Service | preventive | Engine oil and filters hydraulic filters air filter fuel filters coolant check undercarriage inspection track tension adjustment. All within spec. | 2025-12-18 | 3800 | In-House Mechanic | Caterpillar Dealer Service | 2026-03-18 | completed
Putzmeister 58Z Concrete Pump | Quarterly Line Clean and Inspection | preventive | Complete pipeline flush boom cylinder inspection hydraulic hose check hopper wear plate measurement. Replaced 2 boom section hoses. | 2026-01-07 | 2200 | Putzmeister Field Tech | Putzmeister America | 2026-04-07 | completed
JLG 600S Boom Lift | Annual ANSI A92 Inspection | preventive | Annual inspection per ANSI A92.5. Structural welds inspected. Hydraulic cylinders checked. Electrical system and emergency lowering tested. Platform guardrails and gates verified. | 2025-11-30 | 1850 | JLG Certified Tech | JLG Industries | 2026-11-30 | completed
Mack Granite Dump Truck 1 | DOT Annual Inspection | preventive | Federal DOT annual inspection including brakes tires lights suspension and emissions. Passed with no deficiencies. New DOT sticker affixed. | 2025-12-10 | 1200 | Fleet Maintenance Shop | DC Fleet Services | 2026-12-10 | completed
Multiquip Generator 400kW | Semi-Annual Service | preventive | Oil change fuel filter replacement coolant check load bank test at 100% rated capacity for 4 hours. Transfer switch exercise. Battery load test. | 2025-09-15 | 2400 | Power Systems Tech | Mid-Atlantic Power Systems | 2026-03-15 | completed

## 24_invoices
invoice_type | invoice_number | invoice_date | amount | tax_amount | due_date | description | status | vendor_name | client_name | project_name | gl_account | retainage_pct | retainage_held
receivable | AIA-FDC-001 | 2025-03-01 | 2800000 | 0 | 2025-04-01 | Progress Payment 01 - Mobilization earthwork and site preparation | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 280000
receivable | AIA-FDC-002 | 2025-04-01 | 2600000 | 0 | 2025-05-01 | Progress Payment 02 - Earthwork completion and underground utilities | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 260000
receivable | AIA-FDC-003 | 2025-05-01 | 3100000 | 0 | 2025-06-01 | Progress Payment 03 - Foundation caissons pile caps and grade beams | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 310000
receivable | AIA-FDC-004 | 2025-06-01 | 3400000 | 0 | 2025-07-01 | Progress Payment 04 - Level B1 slab on grade and foundation walls | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 340000
receivable | AIA-FDC-005 | 2025-07-01 | 3200000 | 0 | 2025-08-01 | Progress Payment 05 - Structural concrete Levels 1-2 and steel erection start | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 320000
receivable | AIA-FDC-006 | 2025-08-01 | 3500000 | 0 | 2025-09-01 | Progress Payment 06 - Structural concrete Levels 3-5 and steel erection | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 350000
receivable | AIA-FDC-007 | 2025-09-01 | 3800000 | 0 | 2025-10-01 | Progress Payment 07 - Levels 6-7 structure masonry and MEP start | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 380000
receivable | AIA-FDC-008 | 2025-10-01 | 3600000 | 0 | 2025-11-01 | Progress Payment 08 - Levels 8-9 structure and curtain wall start | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 360000
receivable | AIA-FDC-009 | 2025-11-01 | 3900000 | 0 | 2025-12-01 | Progress Payment 09 - Levels 10-11 structure and MEP rough-in | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 390000
receivable | AIA-FDC-010 | 2025-12-01 | 4100000 | 0 | 2026-01-01 | Progress Payment 10 - Level 12 structure curtain wall and roofing start | paid |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 410000
receivable | AIA-FDC-011 | 2026-01-01 | 2900000 | 0 | 2026-01-31 | Progress Payment 11 - Curtain wall Levels 7-10 and interior finishes start | pending |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 290000
receivable | AIA-FDC-012 | 2026-01-15 | 3500000 | 0 | 2026-02-14 | Progress Payment 12 - MEP rough-in Levels 1-6 and change order work | pending |  | U.S. General Services Administration | Federal District Courthouse & Public Safety Complex | 4000 | 10 | 350000
payable | INV-EAGLE-001 | 2025-04-15 | 3800000 | 0 | 2025-05-15 | Eagle Excavation - Earthwork complete final billing | paid | Eagle Excavation LLC |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-NWC-001 | 2025-06-30 | 1440000 | 0 | 2025-07-30 | Nationwide Concrete - Pay App 1 foundations | paid | Nationwide Concrete Inc |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-NWC-002 | 2025-09-30 | 1440000 | 0 | 2025-10-30 | Nationwide Concrete - Pay App 2 structural L1-4 | paid | Nationwide Concrete Inc |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-NWC-003 | 2025-12-15 | 1440000 | 0 | 2026-01-15 | Nationwide Concrete - Pay App 3 structural L5-8 | paid | Nationwide Concrete Inc |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-NWC-004 | 2026-01-15 | 880000 | 0 | 2026-02-15 | Nationwide Concrete - Pay App 4 structural L9-10 in progress | pending | Nationwide Concrete Inc |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-FSE-001 | 2025-06-30 | 2550000 | 0 | 2025-07-30 | Federal Steel - Pay App 1 steel erection L1-6 | paid | Federal Steel Erectors |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-FSE-002 | 2025-12-15 | 2550000 | 0 | 2026-01-15 | Federal Steel - Pay App 2 steel erection L7-12 | paid | Federal Steel Erectors |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-FSE-003 | 2026-01-31 | 1700000 | 0 | 2026-03-02 | Federal Steel - Pay App 3 connections and metal deck | pending | Federal Steel Erectors |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-PAT-001 | 2025-12-01 | 1700000 | 0 | 2025-12-31 | Patriot Electrical - Pay App 1 rough-in L1-3 | paid | Patriot Electrical Contractors |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-PAT-002 | 2026-01-31 | 1020000 | 0 | 2026-03-02 | Patriot Electrical - Pay App 2 rough-in L4-6 | pending | Patriot Electrical Contractors |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-CMEP-001 | 2025-12-01 | 1850000 | 0 | 2025-12-31 | Capital MEP - Pay App 1 HVAC and plumbing L1-3 | paid | Capital MEP Group |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-CMEP-002 | 2026-01-31 | 1110000 | 0 | 2026-03-02 | Capital MEP - Pay App 2 HVAC L4-5 and plumbing risers | pending | Capital MEP Group |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-MMAS-001 | 2025-12-15 | 1566000 | 0 | 2026-01-15 | Monument Masonry - Pay App 1 exterior veneer L1-4 | paid | Monument Masonry Corp |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-CROOF-001 | 2026-01-15 | 832500 | 0 | 2026-02-15 | Capitol Roofing - Pay App 1 Level 12 membrane and penthouse | pending | Capitol Roofing Systems |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-UDF-001 | 2026-01-31 | 864000 | 0 | 2026-03-02 | Union Drywall - Pay App 1 framing and drywall L1 | pending | Union Drywall & Framing |  | Federal District Courthouse & Public Safety Complex | 5010 | 0 | 0
payable | INV-HSE-001 | 2025-09-30 | 242500 | 0 | 2025-10-30 | Huang Structural - Quarterly billing Q3 2025 | paid | Huang Structural Engineering |  | Federal District Courthouse & Public Safety Complex | 6050 | 0 | 0
payable | INV-HSE-002 | 2025-12-31 | 121250 | 0 | 2026-01-31 | Huang Structural - Quarterly billing Q4 2025 | paid | Huang Structural Engineering |  | Federal District Courthouse & Public Safety Complex | 6050 | 0 | 0
payable | INV-DBC-001 | 2025-12-31 | 92500 | 0 | 2026-01-31 | Davis-Bacon Compliance - Annual billing 2025 | paid | Davis-Bacon Compliance Consulting |  | Federal District Courthouse & Public Safety Complex | 5050 | 0 | 0
payable | INV-NTL-001 | 2025-12-31 | 160000 | 0 | 2026-01-31 | National Testing Lab - Testing and inspections through Dec 2025 | paid | National Testing Laboratory |  | Federal District Courthouse & Public Safety Complex | 5040 | 0 | 0
payable | INV-THA-001 | 2025-12-31 | 375000 | 0 | 2026-01-31 | Thornton Hartman - Architectural services through Dec 2025 | paid | Thornton Hartman Architects |  | Federal District Courthouse & Public Safety Complex | 6050 | 0 | 0

## 25_journal_entries
entry_number | entry_date | description | reference | account_number | debit | credit | line_description
JE-001 | 2024-02-15 | GSA Federal Appropriation - Initial Grant Draw | GRANT-GSA-001 | 1005 | 8000000 | 0 | Federal grant funds received
JE-001 | 2024-02-15 | GSA Federal Appropriation - Initial Grant Draw | GRANT-GSA-001 | 4010 | 0 | 8000000 | Federal grant revenue recognized
JE-002 | 2024-03-01 | State Public Safety Bond Appropriation | GRANT-STATE-001 | 1006 | 4100000 | 0 | State appropriation funds received
JE-002 | 2024-03-01 | State Public Safety Bond Appropriation | GRANT-STATE-001 | 4020 | 0 | 4100000 | State appropriation revenue recognized
JE-003 | 2024-04-01 | CDBG Grant - Initial Drawdown | GRANT-CDBG-001 | 1005 | 2000000 | 0 | CDBG federal grant funds received
JE-003 | 2024-04-01 | CDBG Grant - Initial Drawdown | GRANT-CDBG-001 | 4010 | 0 | 2000000 | CDBG grant revenue recognized
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 1000 | 5000000 | 0 | Starting cash contributed
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 1100 | 3200000 | 0 | Equipment at cost
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 1110 | 0 | 850000 | Accumulated depreciation
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 1040 | 685000 | 0 | Prepaid insurance and bonds
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 1200 | 250000 | 0 | Bid bonds and security deposits
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 2080 | 0 | 1800000 | Equipment notes payable
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 2060 | 0 | 685000 | Performance bond liability
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 3000 | 0 | 500000 | Common stock
JE-004 | 2024-02-01 | Opening balances - equity and working capital | OPENING | 3010 | 0 | 5300000 | Retained earnings
JE-005 | 2025-03-31 | Monthly G&A allocation - 2025-03 | GA-2503 | 6000 | 148000 | 0 | Project management salaries
JE-005 | 2025-03-31 | Monthly G&A allocation - 2025-03 | GA-2503 | 6010 | 85000 | 0 | General and administrative
JE-005 | 2025-03-31 | Monthly G&A allocation - 2025-03 | GA-2503 | 6020 | 58000 | 0 | Insurance allocation
JE-005 | 2025-03-31 | Monthly G&A allocation - 2025-03 | GA-2503 | 1000 | 0 | 291000 | Cash paid for G&A
JE-006 | 2025-04-30 | Monthly G&A allocation - 2025-04 | GA-2504 | 6000 | 148000 | 0 | Project management salaries
JE-006 | 2025-04-30 | Monthly G&A allocation - 2025-04 | GA-2504 | 6010 | 85000 | 0 | General and administrative
JE-006 | 2025-04-30 | Monthly G&A allocation - 2025-04 | GA-2504 | 6020 | 58000 | 0 | Insurance allocation
JE-006 | 2025-04-30 | Monthly G&A allocation - 2025-04 | GA-2504 | 1000 | 0 | 291000 | Cash paid for G&A
JE-007 | 2025-05-31 | Monthly G&A allocation - 2025-05 | GA-2505 | 6000 | 148000 | 0 | Project management salaries
JE-007 | 2025-05-31 | Monthly G&A allocation - 2025-05 | GA-2505 | 6010 | 85000 | 0 | General and administrative
JE-007 | 2025-05-31 | Monthly G&A allocation - 2025-05 | GA-2505 | 6020 | 58000 | 0 | Insurance allocation
JE-007 | 2025-05-31 | Monthly G&A allocation - 2025-05 | GA-2505 | 1000 | 0 | 291000 | Cash paid for G&A
JE-008 | 2025-06-30 | Monthly G&A allocation - 2025-06 | GA-2506 | 6000 | 148000 | 0 | Project management salaries
JE-008 | 2025-06-30 | Monthly G&A allocation - 2025-06 | GA-2506 | 6010 | 85000 | 0 | General and administrative
JE-008 | 2025-06-30 | Monthly G&A allocation - 2025-06 | GA-2506 | 6020 | 58000 | 0 | Insurance allocation
JE-008 | 2025-06-30 | Monthly G&A allocation - 2025-06 | GA-2506 | 1000 | 0 | 291000 | Cash paid for G&A
JE-009 | 2025-07-31 | Monthly G&A allocation - 2025-07 | GA-2507 | 6000 | 148000 | 0 | Project management salaries
JE-009 | 2025-07-31 | Monthly G&A allocation - 2025-07 | GA-2507 | 6010 | 85000 | 0 | General and administrative
JE-009 | 2025-07-31 | Monthly G&A allocation - 2025-07 | GA-2507 | 6020 | 58000 | 0 | Insurance allocation
JE-009 | 2025-07-31 | Monthly G&A allocation - 2025-07 | GA-2507 | 1000 | 0 | 291000 | Cash paid for G&A
JE-010 | 2025-08-31 | Monthly G&A allocation - 2025-08 | GA-2508 | 6000 | 148000 | 0 | Project management salaries
JE-010 | 2025-08-31 | Monthly G&A allocation - 2025-08 | GA-2508 | 6010 | 85000 | 0 | General and administrative
JE-010 | 2025-08-31 | Monthly G&A allocation - 2025-08 | GA-2508 | 6020 | 58000 | 0 | Insurance allocation
JE-010 | 2025-08-31 | Monthly G&A allocation - 2025-08 | GA-2508 | 1000 | 0 | 291000 | Cash paid for G&A
JE-011 | 2025-09-30 | Monthly G&A allocation - 2025-09 | GA-2509 | 6000 | 148000 | 0 | Project management salaries
JE-011 | 2025-09-30 | Monthly G&A allocation - 2025-09 | GA-2509 | 6010 | 85000 | 0 | General and administrative
JE-011 | 2025-09-30 | Monthly G&A allocation - 2025-09 | GA-2509 | 6020 | 58000 | 0 | Insurance allocation
JE-011 | 2025-09-30 | Monthly G&A allocation - 2025-09 | GA-2509 | 1000 | 0 | 291000 | Cash paid for G&A
JE-012 | 2025-10-31 | Monthly G&A allocation - 2025-10 | GA-2510 | 6000 | 148000 | 0 | Project management salaries
JE-012 | 2025-10-31 | Monthly G&A allocation - 2025-10 | GA-2510 | 6010 | 85000 | 0 | General and administrative
JE-012 | 2025-10-31 | Monthly G&A allocation - 2025-10 | GA-2510 | 6020 | 58000 | 0 | Insurance allocation
JE-012 | 2025-10-31 | Monthly G&A allocation - 2025-10 | GA-2510 | 1000 | 0 | 291000 | Cash paid for G&A
JE-013 | 2025-11-30 | Monthly G&A allocation - 2025-11 | GA-2511 | 6000 | 148000 | 0 | Project management salaries
JE-013 | 2025-11-30 | Monthly G&A allocation - 2025-11 | GA-2511 | 6010 | 85000 | 0 | General and administrative
JE-013 | 2025-11-30 | Monthly G&A allocation - 2025-11 | GA-2511 | 6020 | 58000 | 0 | Insurance allocation
JE-013 | 2025-11-30 | Monthly G&A allocation - 2025-11 | GA-2511 | 1000 | 0 | 291000 | Cash paid for G&A
JE-014 | 2025-12-31 | Monthly G&A allocation - 2025-12 | GA-2512 | 6000 | 148000 | 0 | Project management salaries
JE-014 | 2025-12-31 | Monthly G&A allocation - 2025-12 | GA-2512 | 6010 | 85000 | 0 | General and administrative
JE-014 | 2025-12-31 | Monthly G&A allocation - 2025-12 | GA-2512 | 6020 | 58000 | 0 | Insurance allocation
JE-014 | 2025-12-31 | Monthly G&A allocation - 2025-12 | GA-2512 | 1000 | 0 | 291000 | Cash paid for G&A
JE-015 | 2025-03-31 | Insurance expense - 2025-03 | INS-2503 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-015 | 2025-03-31 | Insurance expense - 2025-03 | INS-2503 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-016 | 2025-04-30 | Insurance expense - 2025-04 | INS-2504 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-016 | 2025-04-30 | Insurance expense - 2025-04 | INS-2504 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-017 | 2025-05-31 | Insurance expense - 2025-05 | INS-2505 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-017 | 2025-05-31 | Insurance expense - 2025-05 | INS-2505 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-018 | 2025-06-30 | Insurance expense - 2025-06 | INS-2506 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-018 | 2025-06-30 | Insurance expense - 2025-06 | INS-2506 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-019 | 2025-07-31 | Insurance expense - 2025-07 | INS-2507 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-019 | 2025-07-31 | Insurance expense - 2025-07 | INS-2507 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-020 | 2025-08-31 | Insurance expense - 2025-08 | INS-2508 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-020 | 2025-08-31 | Insurance expense - 2025-08 | INS-2508 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-021 | 2025-09-30 | Insurance expense - 2025-09 | INS-2509 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-021 | 2025-09-30 | Insurance expense - 2025-09 | INS-2509 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-022 | 2025-10-31 | Insurance expense - 2025-10 | INS-2510 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-022 | 2025-10-31 | Insurance expense - 2025-10 | INS-2510 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-023 | 2025-11-30 | Insurance expense - 2025-11 | INS-2511 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-023 | 2025-11-30 | Insurance expense - 2025-11 | INS-2511 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-024 | 2025-12-31 | Insurance expense - 2025-12 | INS-2512 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-024 | 2025-12-31 | Insurance expense - 2025-12 | INS-2512 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-025 | 2025-03-31 | Equipment depreciation - 2025-03 | DEP-2503 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-025 | 2025-03-31 | Equipment depreciation - 2025-03 | DEP-2503 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-026 | 2025-04-30 | Equipment depreciation - 2025-04 | DEP-2504 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-026 | 2025-04-30 | Equipment depreciation - 2025-04 | DEP-2504 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-027 | 2025-05-31 | Equipment depreciation - 2025-05 | DEP-2505 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-027 | 2025-05-31 | Equipment depreciation - 2025-05 | DEP-2505 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-028 | 2025-06-30 | Equipment depreciation - 2025-06 | DEP-2506 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-028 | 2025-06-30 | Equipment depreciation - 2025-06 | DEP-2506 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-029 | 2025-07-31 | Equipment depreciation - 2025-07 | DEP-2507 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-029 | 2025-07-31 | Equipment depreciation - 2025-07 | DEP-2507 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-030 | 2025-08-31 | Equipment depreciation - 2025-08 | DEP-2508 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-030 | 2025-08-31 | Equipment depreciation - 2025-08 | DEP-2508 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-031 | 2025-09-30 | Equipment depreciation - 2025-09 | DEP-2509 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-031 | 2025-09-30 | Equipment depreciation - 2025-09 | DEP-2509 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-032 | 2025-10-31 | Equipment depreciation - 2025-10 | DEP-2510 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-032 | 2025-10-31 | Equipment depreciation - 2025-10 | DEP-2510 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-033 | 2025-11-30 | Equipment depreciation - 2025-11 | DEP-2511 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-033 | 2025-11-30 | Equipment depreciation - 2025-11 | DEP-2511 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-034 | 2025-12-31 | Equipment depreciation - 2025-12 | DEP-2512 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-034 | 2025-12-31 | Equipment depreciation - 2025-12 | DEP-2512 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-035 | 2025-03-31 | Interest on equipment notes - 2025-03 | INT-2503 | 7000 | 9500 | 0 | Equipment note interest
JE-035 | 2025-03-31 | Interest on equipment notes - 2025-03 | INT-2503 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-036 | 2025-04-30 | Interest on equipment notes - 2025-04 | INT-2504 | 7000 | 9500 | 0 | Equipment note interest
JE-036 | 2025-04-30 | Interest on equipment notes - 2025-04 | INT-2504 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-037 | 2025-05-31 | Interest on equipment notes - 2025-05 | INT-2505 | 7000 | 9500 | 0 | Equipment note interest
JE-037 | 2025-05-31 | Interest on equipment notes - 2025-05 | INT-2505 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-038 | 2025-06-30 | Interest on equipment notes - 2025-06 | INT-2506 | 7000 | 9500 | 0 | Equipment note interest
JE-038 | 2025-06-30 | Interest on equipment notes - 2025-06 | INT-2506 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-039 | 2025-07-31 | Interest on equipment notes - 2025-07 | INT-2507 | 7000 | 9500 | 0 | Equipment note interest
JE-039 | 2025-07-31 | Interest on equipment notes - 2025-07 | INT-2507 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-040 | 2025-08-31 | Interest on equipment notes - 2025-08 | INT-2508 | 7000 | 9500 | 0 | Equipment note interest
JE-040 | 2025-08-31 | Interest on equipment notes - 2025-08 | INT-2508 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-041 | 2025-09-30 | Interest on equipment notes - 2025-09 | INT-2509 | 7000 | 9500 | 0 | Equipment note interest
JE-041 | 2025-09-30 | Interest on equipment notes - 2025-09 | INT-2509 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-042 | 2025-10-31 | Interest on equipment notes - 2025-10 | INT-2510 | 7000 | 9500 | 0 | Equipment note interest
JE-042 | 2025-10-31 | Interest on equipment notes - 2025-10 | INT-2510 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-043 | 2025-11-30 | Interest on equipment notes - 2025-11 | INT-2511 | 7000 | 9500 | 0 | Equipment note interest
JE-043 | 2025-11-30 | Interest on equipment notes - 2025-11 | INT-2511 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-044 | 2025-12-31 | Interest on equipment notes - 2025-12 | INT-2512 | 7000 | 9500 | 0 | Equipment note interest
JE-044 | 2025-12-31 | Interest on equipment notes - 2025-12 | INT-2512 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-045 | 2025-12-31 | Direct labor accrual through December 2025 | LABOR-YE25 | 5000 | 3200000 | 0 | Direct field labor wages and burden YTD
JE-045 | 2025-12-31 | Direct labor accrual through December 2025 | LABOR-YE25 | 2040 | 0 | 3200000 | Accrued wages and benefits payable
JE-046 | 2025-12-31 | Materials and supplies accrual Dec 2025 | MAT-YE25 | 5020 | 1450000 | 0 | Materials incorporated into project YTD
JE-046 | 2025-12-31 | Materials and supplies accrual Dec 2025 | MAT-YE25 | 1000 | 0 | 1450000 | Cash paid for materials
JE-047 | 2025-12-31 | Equipment costs accrual through Dec 2025 | EQUIP-YE25 | 5030 | 420000 | 0 | Equipment operating costs on FDC-2024
JE-047 | 2025-12-31 | Equipment costs accrual through Dec 2025 | EQUIP-YE25 | 1000 | 0 | 420000 | Cash paid for equipment operation
JE-048 | 2025-12-31 | Other direct costs through Dec 2025 | ODC-YE25 | 5040 | 139000 | 0 | Permits testing and miscellaneous direct costs
JE-048 | 2025-12-31 | Other direct costs through Dec 2025 | ODC-YE25 | 1000 | 0 | 139000 | Cash paid for other direct costs
JE-049 | 2025-12-31 | Davis-Bacon internal compliance costs 2025 | DBA-YE25 | 5050 | 85000 | 0 | Internal DB compliance staff time and training
JE-049 | 2025-12-31 | Davis-Bacon internal compliance costs 2025 | DBA-YE25 | 1000 | 0 | 85000 | Cash paid for DB compliance
JE-050 | 2025-12-31 | Section 3 compliance costs 2025 | S3-YE25 | 5060 | 53000 | 0 | Section 3 outreach hiring and documentation
JE-050 | 2025-12-31 | Section 3 compliance costs 2025 | S3-YE25 | 1000 | 0 | 53000 | Cash paid for Section 3 programs
JE-051 | 2025-12-31 | Performance bond premium amortization 2025 | BOND-YE25 | 6030 | 342500 | 0 | Bond premium amortized 10 months
JE-051 | 2025-12-31 | Performance bond premium amortization 2025 | BOND-YE25 | 1040 | 0 | 342500 | Prepaid bond premium reduction
JE-052 | 2026-01-31 | Monthly G&A allocation - 2026-01 | GA-2601 | 6000 | 148000 | 0 | Project management salaries
JE-052 | 2026-01-31 | Monthly G&A allocation - 2026-01 | GA-2601 | 6010 | 85000 | 0 | General and administrative
JE-052 | 2026-01-31 | Monthly G&A allocation - 2026-01 | GA-2601 | 6020 | 58000 | 0 | Insurance allocation
JE-052 | 2026-01-31 | Monthly G&A allocation - 2026-01 | GA-2601 | 1000 | 0 | 291000 | Cash paid for G&A
JE-053 | 2026-01-31 | Insurance expense - 2026-01 | INS-2601 | 6020 | 12000 | 0 | GL umbrella premium allocation
JE-053 | 2026-01-31 | Insurance expense - 2026-01 | INS-2601 | 2070 | 0 | 12000 | Workers comp reserve increase
JE-054 | 2026-01-31 | Equipment depreciation - 2026-01 | DEP-2601 | 6040 | 35417 | 0 | Monthly depreciation on equipment
JE-054 | 2026-01-31 | Equipment depreciation - 2026-01 | DEP-2601 | 1110 | 0 | 35417 | Accumulated depreciation increase
JE-055 | 2026-01-31 | Interest on equipment notes - 2026-01 | INT-2601 | 7000 | 9500 | 0 | Equipment note interest
JE-055 | 2026-01-31 | Interest on equipment notes - 2026-01 | INT-2601 | 2080 | 0 | 9500 | Notes payable interest accrued
JE-056 | 2026-01-31 | Direct labor - January 2026 | LABOR-2601 | 5000 | 340000 | 0 | Field labor January 2026
JE-056 | 2026-01-31 | Direct labor - January 2026 | LABOR-2601 | 2040 | 0 | 340000 | Accrued wages January
JE-057 | 2026-01-05 | GSA Additional Grant Draw Q1 2026 | GRANT-GSA-002 | 1005 | 200000 | 0 | Federal grant additional draw
JE-057 | 2026-01-05 | GSA Additional Grant Draw Q1 2026 | GRANT-GSA-002 | 4010 | 0 | 200000 | Federal grant revenue recognized