## Portfolio Summary
PINNACLE BUILDS LLC — Portfolio Financial Summary
Five Active Projects — As of January 31, 2026
Project | Contract Value | % Complete | Revenue Earned | Costs PTD | Gross Profit | Gross Margin
MRN — The Meridian at River North Chicago, IL ¦ Mixed-Use High-Rise ¦ Active | 84220000 | 65% | 54743000 | 50570000 | 4173000 | 7.623%
SDM — St. Dominic Medical Center Expansion Austin, TX ¦ Healthcare / Hospital ¦ Active | 59690000 | 28% | 16713200 | 15176000 | 1537200 | 9.198%
PRC — Paladin Resort & Casino Las Vegas, NV ¦ Casino Resort ¦ Preconstruction | 145000000 | 4% | 5800000 | 5500000 | 300000 | 5.172%
MSL — Mid-South Logistics Park - Bldg 2 Memphis, TN ¦ Industrial / Distribution ¦ Closeout | 39390000 | 97% | 38208300 | 35308000 | 2900300 | 7.591%
DSR — Denver SW Recreation & Aquatics Center Denver, CO ¦ Municipal / Recreation ¦ Active | 24753000 | 35% | 8663550 | 7980000 | 683550 | 7.89%
PORTFOLIO TOTAL | 353053000 | 35.16% | 124128050 | 114534000 | 9594050 | 7.729%
PORTFOLIO KEY METRICS — WIP STATUS
Project | Total Billed | Retainage Held | BIE (Over) / CIE (Under) | Cash Collected | Open AR | Project Status
MRN — The Meridian at River North | 70000000 | 7000000 | 15257000 | 57600000 | 5400000 | Active
SDM — St. Dominic Medical Center Expansion | 29100000 | 2910000 | 12386800 | 22990000 | 3200000 | Active
PRC — Paladin Resort & Casino | 5800000 | 580000 | 0 | 5220000 | 0 | Preconstruction
MSL — Mid-South Logistics Park - Bldg 2 | 37600000 | 3760000 | -608300 | 32840000 | 1000000 | Closeout
DSR — Denver SW Recreation & Aquatics Center | 7000000 | 350000 | -1663550 | 4200000 | 2450000 | Active
PORTFOLIO TOTALS | 149500000 | 14600000 | 25371950 | 122850000 | 12050000
PORTFOLIO NOTES
• BIE = Billings in Excess of Costs (Overbilling) — Current Liability on Balance Sheet.
• CIE = Costs in Excess of Billings (Underbilling) — Current Asset on Balance Sheet.
• MRN Chicago: Large BIE ($15.3M) reflects aggressive front-loaded billing schedule typical for high-rise residential.
• SDM Austin: BIE ($12.4M) reflects GMP with early mobilization and preconstruction billing on healthcare project.
• PRC Las Vegas: BIE = $0 — preconstruction services billed equals earned. GMP not yet established.
• MSL Memphis: CIE ($608K) — final retainage punchlist work earned ahead of final billing. Closeout phase.
• DSR Denver: CIE ($1.66M) — design-build with design fees earned ahead of billing. 5% retainage (public project).
• Revenue Recognition: Percentage-of-Completion method (ASC 606) applied to all projects.
• YTD figures shown in the P&L tab reflect January 2026 activity only across all 5 projects.
• Colorado prevailing wage (Little Davis-Bacon Act) applies to DSR Denver per City and County of Denver contract.

## P&L by Project
PINNACLE BUILDS LLC — Consolidated P&L by Project
Project-to-Date (PTD) figures as of January 31, 2026 ¦ Revenue recognized via % of completion (ASC 606)
Revenue & Cost Category | MRN Chicago IL Mixed-Use | SDM Austin TX Healthcare | PRC Las Vegas NV Casino | MSL Memphis TN Industrial | DSR Denver CO Municipal | PORTFOLIO TOTAL
| PTD thru Jan 2026 | PTD thru Jan 2026 | PTD thru Jan 2026 | PTD thru Jan 2026 | PTD thru Jan 2026 | PTD TOTAL
REVENUE (% of Completion)
Contract Revenue — Earned PTD | 54743000 | 16713200 | 5800000 | 38208300 | 8663550 | 124128050
% Complete | 65% | 28% | 4% | 97% | 35%
Change Orders (Approved) — Included Above | — | — | — | — | — | —
TOTAL REVENUE EARNED | 54743000.65 | 16713200.28 | 5800000.04 | 38208300.97 | 8663550.35 | 124128050
DIRECT COSTS (COST OF REVENUE)
Direct Labor (Field Self-Perform) | 4753580 | 1426544 | 517000 | 3318952 | 750120 | 10766196
Subcontractor Costs | 36916100 | 11078480 | 4015000 | 25774840 | 5825400 | 83609820
Materials & Supplies | 2123940 | 637392 | 231000 | 1482936 | 335160 | 4810428
Equipment Costs | 657410 | 197288 | 71500 | 459004 | 103740 | 1488942
Specialty Systems (Project-Specific) | 4652440 | 1396192 | 506000 | 3248336 | 734160 | 10537128
Other Direct Costs (Permits, Testing, Commissioning) | 1466530 | 440104 | 159500 | 1023932 | 231420 | 3321486
TOTAL DIRECT COSTS | 50570000 | 15176000 | 5500000 | 35308000 | 7980000 | 114534000
GROSS PROFIT | 4173000.65 | 1537200.28 | 300000.04 | 2900300.97 | 683550.35 | 9594050
Gross Margin % | 7.623% | 9.198% | 5.172% | 7.591% | 7.89% | 7.729%
GENERAL & ADMINISTRATIVE EXPENSES (Company-Wide Allocation)
Project Management Salaries (PM, Super, PE) | 930336 | 659366 | 1601743 | 435122 | 273434 | 3900001
G&A Overhead & Corporate | 429386 | 304323 | 739266 | 200825 | 126200 | 1800000
Insurance (GL, Umbrella, WC Premiums) | 310112 | 219789 | 533914 | 145041 | 91145 | 1300001
Bonds (Performance & Payment) | 233777 | 165687 | 402489 | 109338 | 68709 | 980000
Depreciation — Equipment | 147900 | 104822 | 254636 | 69173 | 43469 | 620000
Professional Fees | 90648 | 64246 | 156067 | 42396 | 26642 | 379999
Marketing & Business Development | 42939 | 30432 | 73927 | 20083 | 12620 | 180001
Office & Facilities | 71564 | 50720 | 123211 | 33471 | 21033 | 299999
IT & Software | 26240 | 18597 | 45177 | 12273 | 7712 | 109999
Vehicle & Travel | 31011 | 21979 | 53391 | 14504 | 9114 | 129999
Miscellaneous G&A | 23855 | 16907 | 41070 | 11157 | 7011 | 100000
TOTAL G&A EXPENSES | 2337768 | 1656868 | 4024891 | 1093383 | 687089 | 9799999
OPERATING INCOME (EBIT) | 1835232.65 | -119667.72 | -3724890.96 | 1806917.97 | -3538.65 | -205949
OTHER INCOME / (EXPENSE)
Interest Expense | -22000 | -18000 | -5000 | -12000 | -8000 | -65000
Other Income (Equipment Rental, Misc.) | 0 | 0 | 12000 | 8000 | 0 | 20000
NET INCOME | 1813232.65 | -137667.72 | -3717890.96 | 1802917.97 | -11538.65 | -250949
Net Margin % | 3.312% | -0.8237% | -64.1% | 4.719% | -0.1332% | -0.2022%

## WIP Schedule
PINNACLE BUILDS LLC — Work-In-Progress (WIP) Schedule — All Projects
As of January 31, 2026 ¦ Percentage-of-Completion Method (ASC 606) ¦ BIE = Overbilling (Liability) ¦ CIE = Underbilling (Asset)
Project / Location | Type | Status | Revised Contract | % Complete | Revenue Earned | Billed to Date | BIE / (CIE) | Retainage Recv | Contract Backlog
MRN — The Meridian at River North 📍 Chicago, IL | Mixed-Use High-Rise | Active | 84220000 | 65% | 54743000 | 70000000 | 15257000 | 7000000 | 29477000
SDM — St. Dominic Medical Center Expansion 📍 Austin, TX | Healthcare / Hospital | Active | 59690000 | 28% | 16713200 | 29100000 | 12386800 | 2910000 | 42976800
PRC — Paladin Resort & Casino 📍 Las Vegas, NV | Casino Resort | Preconstruction | 145000000 | 4% | 5800000 | 5800000 | 0 | 580000 | 139200000
MSL — Mid-South Logistics Park - Bldg 2 📍 Memphis, TN | Industrial / Distribution | Closeout | 39390000 | 97% | 38208300 | 37600000 | -608300 | 3760000 | 1181700
DSR — Denver SW Recreation & Aquatics Center 📍 Denver, CO | Municipal / Recreation | Active | 24753000 | 35% | 8663550 | 7000000 | -1663550 | 350000 | 16089450
PORTFOLIO TOTAL |  |  | 353053000 | 35.16% | 124128050 | 149500000 | 25371950 | 14600000 | 228924950
WIP RECONCILIATION — BIE / CIE EXPLANATION
BIE (Billings in Excess of Costs) = OVERBILLING — Current Liability on Balance Sheet. CIE (Costs in Excess of Billings) = UNDERBILLING — Current Asset on Balance Sheet.
MRN — The Meridian at River North |  | BIE $15,257,000 | High-rise lump sum — aggressive billing schedule, early draw structure with developer
SDM — St. Dominic Medical Center |  | BIE $12,386,800 | GMP with front-loaded owner billing; health system draw schedule includes preconstruction fees
PRC — Paladin Resort & Casino |  | Balanced $0 | Preconstruction services — billed equals earned; GMP not yet established
MSL — Mid-South Logistics Park |  | CIE $(608,300) | Closeout phase — earned revenue slightly ahead of final billing on warranty/punchlist items
DSR — Denver SW Recreation |  | CIE $(1,663,550) | Design-build — design fees earned faster than construction billing; 5% retainage (public project)

## Balance Sheet
PINNACLE BUILDS LLC — Consolidated Balance Sheet
As of January 31, 2026
Reflects all five active projects: MRN • SDM • PRC • MSL • DSR
ASSETS | Amount ($) | Amount ($)
CURRENT ASSETS |  | CURRENT LIABILITIES
AP — Subcontractors (All Projects) | 8240000 | 24180000
AP — Materials & Vendors | 2180000 | 4820000
Billings in Excess of Costs (BIE) — MRN + SDM | 3420000 | 27643800
Retainage Payable to Subcontractors | 7680000 | 11240000
Accrued Wages & Benefits | 5900000 | 8420000
Accrued Taxes — Federal, State, Payroll | 3800000 | 1840000
Accrued G&A Expenses | 2800000 | 816667
Workers Comp Reserve | 1000000 | 385000
TOTAL CURRENT LIABILITIES | 14600000 | 79345467
Costs in Excess of Billings (CIE) — DSR + MSL | 2271850
Prepaid Insurance, Bonds & Deposits | 1840000 | LONG-TERM LIABILITIES
Notes Payable — Equipment Financing | 920000 | 3840000
Lines of Credit — Equipment & Operations | 54651850 | 1200000
Performance Bond Reserves |  | 1840000
TOTAL LONG-TERM LIABILITIES |  | 6880000
TOTAL LIABILITIES | 3845000 | 86225467
Less: Accumulated Depreciation | -1240000
Vehicles — At Cost | 880000 | STOCKHOLDERS' EQUITY
Common Stock & Paid-In Capital | -295000 | 1500000
Retained Earnings — Prior Years | 3190000 | 2840983
Current Year Net Income (PTD thru Jan 2026) |  | 4117034
TOTAL STOCKHOLDERS' EQUITY |  | 8458017
TOTAL LIABILITIES & EQUITY | 380000 | 94683484
Goodwill & Intangibles | 0
BALANCE CHECK (Assets - L+E = $0): =B31-D28
TOTAL ASSETS | 57841850

## YTD P&L (Jan 2026)
PINNACLE BUILDS LLC — Year-to-Date P&L (January 2026 Only)
Single month — January 1–31, 2026 ¦ All amounts in USD
Revenue / Cost Category | MRN Chicago | SDM Austin | PRC Las Vegas | MSL Memphis | DSR Denver | JAN 2026 TOTAL
REVENUE
Contract Revenue — Earned (Jan) | 5900000 | 3800000 | 960000 | 1000000 | 2800000 | 14460000
TOTAL YTD REVENUE | 5900000 | 3800000 | 960000 | 1000000 | 2800000 | 14460000
DIRECT COSTS
Total Direct Costs (Labor + Subs + Materials + Equipment) | 4100000 | 3420000 | 910000 | 890000 | 2420000 | 11740000
TOTAL YTD DIRECT COSTS | 4100000 | 3420000 | 910000 | 890000 | 2420000 | 11740000
YTD GROSS PROFIT | 1800000 | 380000 | 50000 | 110000 | 380000 | 2720000
GENERAL & ADMINISTRATIVE (Monthly Allocation)
G&A Expenses — January 2026 (Allocated by Contract Value) | 194814 | 138072 | 335408 | 91115 | 57258 | 816667
Interest Expense — January 2026 | -22000 | -18000 | -5000 | -12000 | -8000 | -65000
YTD NET INCOME (LOSS) — JANUARY 2026 | 1583186 | 223928 | -290408 | 6885 | 314742 | 1838333
YTD Net Margin % | 26.83% | 5.893% | -30.25% | 0.6885% | 11.24% | 12.71%