## Project Overview & WIP
PINNACLE BUILDS LLC — CTA Red Line Extension Utility Relocation Tunnel
CTA-RLX-2024 ¦ S. Michigan Ave 103rd–130th St, Chicago IL ¦ Active — 34% Complete ¦ As of January 31, 2026
PROJECT SNAPSHOT
Project Type | Heavy Civil / Underground Tunnel |  | Contract Type | CM at Risk (GMP)
Client | Chicago Transit Authority |  | Funding | FTA Full Funding Grant Agreement + Illinois BUILD Grant
Location | 103rd–130th St under S. Michigan Ave, Chicago IL |  | DBE Goal | 25% — FTA Required
TBM Type | Earth Pressure Balance (EPB) Herrenknecht S-1124 |  | TBM Name | Mary - after Mary Breckinridge
Tunnel Geometry | 21-ft ID finished bore, dual barrel |  | Tunnel Length | 2.1 miles (22,176 LF per bore)
Depth Range | 45–65 feet BGS (below grade surface) |  | Ground Conditions | Chicago Blue Clay / Dolomite interface
TBM Progress | 4,284 LF bored = 1,020 rings installed |  | Rings Target | 3,100 total rings (32.9% rings complete)
Station Caverns | 3 underground stations: 111th, 119th, 130th St |  | Cross Passages | 8 required per NFPA 130 (2 of 8 complete)
Union Labor | Laborers Local 2, OE Local 150, IW Local 1, IBEW Local 134 |  | IEPA Requirement | Groundwater monitoring — 28 instruments
CONTRACT SUMMARY
Original GMP Contract Value | 127500000
Approved Change Orders (CO-001 thru CO-004) | 5680000
Revised Contract Value | 133180000
Estimated Cost at Completion | 119800000
Estimated Gross Profit (Project) | 13380000
Estimated Gross Margin | 10.05%
WORK-IN-PROGRESS (WIP) SCHEDULE
Cost Category / Trade Package | Budget / Subcontract | % Complete | Revenue Earned | Billed to Date | BIE / (CIE)
TBM Drive — South Bore (EPB Self-Perform) | 58000000 | 33% | 19140000 | 24000000 | 4860000
Segmental Lining — Supply & Install | 24800000 | 34% | 8432000 | 8432000 | 0
Annular & Contact Grouting | 6400000 | 34% | 2176000 | 2176000 | 0
Dewatering — Deep Wells (monthly cost) | 8200000 | 34% | 2788000 | 2788000 | 0
Station Cavern — 111th St (NATM Shotcrete) | 14600000 | 28% | 4088000 | 4088000 | 0
Station Cavern — 119th St (NATM Shotcrete) | 14600000 | 12% | 1752000 | 1752000 | 0
Station Cavern — 130th St (Not started) | 14600000 | 0% | 0 | 0 | 0
Cross Passages — 8 Total (2 complete) | 7800000 | 18% | 1404000 | 1404000 | 0
Tunnel Electrical — Temp Power + Permanent | 11400000 | 34% | 3876000 | 3876000 | 0
Structural Steel — Station Caverns | 8900000 | 20% | 1780000 | 1780000 | 0
Utility Relocation — ComEd, NICOR, CDOT Water | 14800000 | 94% | 13912000 | 13912000 | 0
TBM OEM Service & Parts (Herrenknecht) | 4200000 | 34% | 1428000 | 1428000 | 0
General Conditions + COs 001-004 | 18880000 | 75% | 14160000 | 16264000 | 2104000
TOTAL — ALL PACKAGES | 207180000 | 36.17% | 74936000 | 81900000 | 6964000

## P&L Statement
CTA-RLX-2024 — P&L Statement ¦ Percentage-of-Completion (ASC 606)
Account | YTD Jan 2026 | Project-to-Date | Full Project Est.
REVENUE
Contract Revenue — Earned (% of Completion) | 10600000 | 45281200 | 133180000
% Complete (this period / project / full) | 7.96% | 34% | 100%
TOTAL REVENUE | 10600000 | 45281200 | 133180000
DIRECT COSTS — COST OF REVENUE
Direct Labor (Union Field Workers — Laborers L2, OE L150, IW L1) | 2150400 | 9775680 | 28752000
Subcontractors (Lining, Grouting, Electrical, Steel, Dewatering) | 4300800 | 19551360 | 57504000
Equipment (TBM, Gantry, Crane, Conveyor, Ventilation, Grout Plant) | 1612800 | 7331760 | 21564000
Materials (Lining Segments, Grout, Shotcrete, Utilities) | 627200 | 2851240 | 8386000
Other Direct (Permits, IEPA, Safety, FTA Compliance, Monitoring) | 268800 | 1221960 | 3594000
TOTAL DIRECT COSTS | 8960000 | 40732000 | 119800000
GROSS PROFIT | 1640000 | 4549200 | 13380000
Gross Margin % | 15.47% | 10.05% | 10.05%
GENERAL & ADMINISTRATIVE (Annual Allocation)
Heavy Civil Project Management (PM, Super, TBM Ops) | 140000 | 1680000 | 1680000
G&A Overhead Allocation | 63000 | 756000 | 756000
Insurance (GL, Umbrella, Workers Comp) | 52500 | 630000 | 630000
Performance & Payment Bonds | 42000 | 504000 | 504000
Equipment Depreciation (TBM note impact) | 28000 | 336000 | 336000
Professional Fees (Legal, Geotech, HNTB liaison) | 14000 | 168000 | 168000
Misc G&A | 10500 | 126000 | 126000
TOTAL G&A | 350000 | 4200000 | 4200000
OPERATING INCOME (EBIT) | 1290000 | 349200 | 9180000
OTHER INCOME / (EXPENSE)
Interest Expense — TBM Note + Equipment LOC | -185000 | -528000 | -528000
Other Income (Equipment rental to CTA during shafts) | 0 | 85000 | 85000
NET INCOME | 1105000 | -93800 | 8737000
Net Margin % | 10.42% | -0.2071% | 6.56%

## Billing & Cash Flow
CTA-RLX-2024 — AIA Billing Schedule & Cash Flow
Category | Jan 2026 YTD | Project-to-Date | Notes
AIA APPLICATION PROGRESS DRAW HISTORY
Application | Billed Amount | Status | Period / Scope Summary
AIA App #01 — June 2024 | 9500000 | Paid | TBM mobilization, launching shaft, preconstruction services
AIA App #02 — September 2024 | 11800000 | Paid | TBM launch Ring 1-180 + dewatering + utility relocation start
AIA App #03 — December 2024 | 13200000 | Paid | Rings 181-480 + CO-001 timber caisson + NICOR reroute start
AIA App #04 — March 2025 | 12600000 | Paid | Rings 481-700 + CO-002 NICOR complete + CO-003 groundwater
AIA App #05 — June 2025 | 11400000 | Paid | Rings 701-900 + 111th St station cavern excavation start
AIA App #06 — September 2025 | 12800000 | Paid | Rings 901-1000 + CO-004 shotcrete upgrade 119th St
AIA App #07 — January 2026 | 10600000 | PENDING | Rings 1001-1100 + cross passage ground improvement start
TOTAL BILLED TO DATE | 81900000
Less: Retainage Held by CTA (10%) | -8190000
Net Cash Collected (Apps 1-6 paid) | 71300000
OPERATING CASH FLOW (SIMPLIFIED)
Net Income | 1105000 | -93800
Add: Depreciation | 28000 | 672000 | Equipment incl. TBM
(Increase) AR — App #7 Pending | -10600000 | -14500000 | Pending CTA payment
(Increase) Retainage Receivable | -1060000 | -8190000 | 10% held all apps
Increase BIE — Overbilling | 0 | 36618800 | Billing ahead of earned — see WIP
Increase AP — Subcontractors | 8960000 | 22800000 | Sub invoices net of retainage withheld
Increase Retainage Payable to Subs | 0 | 6840000 | 10% withheld from subs
Increase Accrued Wages (Union payroll) | 2140000 | 6420000 | 3-week payroll lag union
Increase Accrued Other | 480000 | 2280000 | IEPA, monitoring, compliance
NET CASH FROM OPERATIONS | 1053000 | 52847000
KEY BIE / CIE NOTE
BIE (Billings in Excess of Earnings) = $36,618,800 — This project has a significant overbilling balance. Heavy civil tunnel projects typically bill aggressively on mobilization and TBM costs early in the project, resulting in front-loaded billing. Revenue earned via % complete (34%) lags total billings ($81,900,000) because the contract is 34% complete but 61.5% billed. BIE appears as a CURRENT LIABILITY on the balance sheet.