HARD ROCK LEGACY COMPLEX

Financial Statements  |  Year Ended December 31, 2025  |  University of Miami Athletic Complex  |  $1.85B Program

PROGRAM OVERVIEW — CONTRACT STATUS

| Project | GMP Contract | Approved COs | Total Value | % Complete |
| --- | --- | --- | --- | --- |
| Hard Rock Legacy Stadium (HRL-2024) | 1,100,000,000 | 19,494,000 | 1,119,494,000 | 28% |
| Football Performance Center (HPC-2024) | 285,000,000 | 5,300,000 | 290,300,000 | 22% |
| Athlete Village (CAV-2024) | 195,000,000 | 8,300,000 | 203,300,000 | 12% |
| Admin Tower (HAA-2024) | 185,000,000 | 2,650,000 | 187,650,000 | 5% |
| Site & Infrastructure (SDI-2024) | 85,000,000 | 6,800,000 | 91,800,000 | 68% |
| TOTAL PROGRAM | 1,850,000,000 | 42,544,000 | 1,892,544,000 | 21% |

PROFIT & LOSS STATEMENT

For the Year Ended December 31, 2025  |  JV: Titan Builds / PCL Construction  |  GMP Delivery Method

|  | 2025 Billed | 2024 Billed | % Complete | Margin |
| --- | --- | --- | --- | --- |
| CONTRACT REVENUE BY PROJECT |  |  |  |  |
| Hard Rock Legacy Stadium (HRL-2024) | 208,200,000 | 130,000,000 | 28% | 8.4% |
| Football Performance Center (HPC-2024) | 29,350,000 | 33,650,000 | 22% | 8.7% |
| Coral Gables Athlete Village (CAV-2024) | 14,800,000 | 8,600,000 | 12% | 9.0% |
| Athletic Administration Tower (HAA-2024) | 9,750,000 | 4,750,000 | 5% | 9.2% |
| Site & Infrastructure (SDI-2024) | 28,800,000 | 22,000,000 | 68% | 8.0% |
| Change Order Revenue - All Projects | 19,494,000 | 7,356,000 | N/A | 6.5% |
| TOTAL REVENUE | 290,900,000 | 194,500,000 |  |  |
| DIRECT CONSTRUCTION COSTS |  |  |  |  |
| Subcontractor Costs - Structural / Concrete / Site | 191,644,920 | 129,188,000 |  |  |
| Subcontractor Costs - MEP (Bechtel, Turner, Johnson Controls) | 21,293,880 | 14,332,000 |  |  |
| Materials - Structural Concrete | 18,632,145 | 12,541,000 |  |  |
| Materials - Structural Steel & Rebar | 13,308,675 | 8,958,000 |  |  |
| Direct Labor - Field Staff | 10,646,940 | 7,180,000 |  |  |
| Equipment - Owned Operation & Rented | 5,323,470 | 3,590,000 |  |  |
| General Conditions - Site Facilities & Temp Work | 5,323,470 | 3,590,000 |  |  |
| TOTAL DIRECT COSTS | 266,173,500 | 177,968,000 |  |  |
| GROSS PROFIT | 24,726,500 | 16,532,000 | 8.5% |  |
| INDIRECT & OVERHEAD COSTS |  |  |  |  |
| Project Management Staff (PM, PE, Superintendent) | 5,236,200 |  |  |  |
| On-site General Conditions Staff | 2,327,200 |  |  |  |
| Safety Director & Safety Program | 1,745,400 |  |  |  |
| Builders Risk & General Liability Insurance | 2,036,300 |  |  |  |
| Performance & Payment Bonds | 1,163,600 |  |  |  |
| Legal & Professional Fees | 1,163,600 |  |  |  |
| IT, Software & Communications | 872,700 |  |  |  |
| Executive Management Allocation | 872,700 |  |  |  |
| TOTAL OVERHEAD | 15,417,700 | 8,968,000 | 5.3% |  |
| NET INCOME | 9,308,800 | 7,564,000 | 3.2% |  |

HARD ROCK LEGACY COMPLEX

Balance Sheet  |  As of December 31, 2025

|  | Dec 31, 2025 |  |
| --- | --- | --- |
| CURRENT ASSETS |  |  |
| Cash & Equivalents - Project Operating Accounts | 48,500,000 |  |
| Accounts Receivable - UM Progress Billings (Nov-Dec outstanding) | 38,500,000 |  |
| Retainage Receivable (5% withheld by UM, cumulative) | 23,057,500 |  |
| Costs in Excess of Billings (Underbilled WIP Q4 2025) | 15,200,000 |  |
| Change Order AR - Approved COs Pending Billing | 4,850,000 |  |
| Prepaid Expenses | 4,850,000 |  |
| TOTAL CURRENT ASSETS | 134,957,500 |  |
| PROPERTY, PLANT & EQUIPMENT |  |  |
| Construction Equipment - Owned (at cost) | 20,850,000 |  |
| Accumulated Depreciation - Equipment | (3,200,000) |  |
| Project Deposits (Utilities & Permits) | 2,100,000 |  |
| NET NON-CURRENT ASSETS | 19,750,000 |  |
| TOTAL ASSETS | 154,707,500 |  |
| CURRENT LIABILITIES |  |  |
| Accounts Payable - Subcontractors (Dec 2025 Outstanding) | 41,000,000 |  |
| Retainage Payable to Subcontractors (5% cumulative withheld) | 21,150,000 |  |
| Accrued Payroll | 4,200,000 |  |
| Accrued Project Costs | 6,800,000 |  |
| Equipment Financing - Current & Long Term | 5,500,000 |  |
| TOTAL LIABILITIES | 78,650,000 |  |
| OWNERS' EQUITY (JV - Titan Builds / PCL Construction) |  |  |
| Owner Capital Contributions (JV Funded) | 59,163,200 |  |
| Retained Earnings - Prior Years (2024 Net Income) | 7,585,500 |  |
| Current Year Net Income (2025) | 9,308,800 |  |
| TOTAL OWNERS' EQUITY | 76,057,500 |  |
| TOTAL LIABILITIES & EQUITY | 154,707,500 |  |

HARD ROCK LEGACY COMPLEX

Statement of Cash Flows  |  Year Ended December 31, 2025

|  | Year 2025 |  |
| --- | --- | --- |
| OPERATING ACTIVITIES |  |  |
| Net Income | 9,308,800 |  |
| Adjustments: |  |  |
| Increase in Accounts Receivable (progress billings) | (45,000,000) |  |
| Increase in Retainage Receivable (5% withheld by UM) | (15,000,000) |  |
| Increase in Accounts Payable - Subcontractors | 82,000,000 |  |
| Increase in Accrued Costs & Payroll | 6,500,000 |  |
| NET CASH FROM OPERATING ACTIVITIES | 37,808,800 |  |
| INVESTING ACTIVITIES |  |  |
| Equipment Purchases (Boom Lifts, Trucks) | (2,800,000) |  |
| Project Deposits (New Permit & Utility Deposits) | (800,000) |  |
| NET CASH FROM INVESTING ACTIVITIES | (3,600,000) |  |
| FINANCING ACTIVITIES |  |  |
| Equipment Financing - New Borrowings | 1,200,000 |  |
| Owner Distributions to JV Partners | (8,000,000) |  |
| NET CASH FROM FINANCING ACTIVITIES | (6,800,000) |  |
| NET CHANGE IN CASH | 27,408,800 |  |
| Cash at Beginning of Year (January 1, 2025) | 21,091,200 |  |
| CASH AT END OF YEAR (December 31, 2025) | 48,500,000 |  |

NOTES TO FINANCIAL STATEMENTS

Basis of Presentation: These financial statements are presented for the joint venture between Titan Builds and PCL Construction formed for the Hard Rock Legacy Complex program. Revenue is recognized on the percentage-of-completion method based on costs incurred relative to estimated total costs.

Contract Values: All five project contracts utilize GMP delivery except the Site & Infrastructure package which is Lump Sum. Approved change orders through December 31, 2025 total $42.5M across the program. Total program value at completion is estimated at $1.893 billion.

Retainage: Owner (University of Miami) withholds 5% retainage from all progress payments. The JV withholds 5% retainage from all subcontractor payments. Retainage is released upon substantial completion of each project and final acceptance.

Accounts Payable - Subcontractors: The $117M subcontractor AP balance represents progress payments approved and due to Barton Malow (structural steel), Bechtel Infrastructure (MEP), Hensel Phelps (concrete), and other major subcontractors for December 2025 billings.

Schedule: As of December 31, 2025 the stadium project is 28% complete on a 42-month schedule targeting first game August 30, 2027. The football performance center targets completion December 31, 2026. The athlete village and admin tower follow in Q1 and Q2 2027 respectively.

Change Orders: Thirteen approved change orders totaling $42.5M are included in contract revenue. Major items include natural grass conversion ($4.85M), enhanced premium club finishes ($8.2M), scoreboard upgrade ($5.5M), unforeseen rock excavation ($2.3M), and expanded tailgate plaza ($6.8M).

Tax: The joint venture is treated as a pass-through entity for income tax purposes. No income tax provision is recorded at the JV level. Partner-level tax obligations are the responsibility of each JV member.