## Chart of Accounts
account_number | name | account_type | sub_type | description
1000 | Cash - Operating | asset | current_asset
1005 | Cash - Payroll | asset | current_asset
1010 | Accounts Receivable | asset | current_asset
1020 | Retainage Receivable | asset | current_asset
1030 | Costs in Excess of Billings | asset | current_asset
1040 | Prepaid Insurance | asset | current_asset
1050 | Prepaid Expenses | asset | current_asset
1100 | Construction Equipment | asset | fixed_asset
1110 | Vehicles | asset | fixed_asset
1120 | Office Equipment & Furniture | asset | fixed_asset
1130 | Accumulated Depreciation | asset | fixed_asset
2000 | Accounts Payable | liability | current_liability
2010 | Retainage Payable | liability | current_liability
2020 | Billings in Excess of Costs | liability | current_liability
2030 | Accrued Payroll | liability | current_liability
2040 | Accrued Expenses | liability | current_liability
2050 | Sales Tax Payable | liability | current_liability
2100 | Construction Line of Credit | liability | current_liability
2110 | Equipment Notes Payable | liability | long_term_liability
3000 | Members Capital | equity | equity
3010 | Retained Earnings | equity | retained_earnings
4000 | Contract Revenue | revenue | operating_revenue
4010 | Change Order Revenue | revenue | operating_revenue
5000 | Direct Materials | expense | cost_of_goods
5100 | Field Labor | expense | cost_of_goods
5110 | Supervision Labor | expense | cost_of_goods
5120 | Field Payroll Taxes & Benefits | expense | cost_of_goods
5200 | Equipment Rental | expense | cost_of_goods
5210 | Equipment Fuel & Maintenance | expense | cost_of_goods
5300 | Subcontract - Electrical | expense | cost_of_goods
5310 | Subcontract - Mechanical | expense | cost_of_goods
5320 | Subcontract - Structural Steel | expense | cost_of_goods
5330 | Subcontract - Concrete | expense | cost_of_goods
5340 | Subcontract - Drywall | expense | cost_of_goods
5350 | Subcontract - Fire Protection | expense | cost_of_goods
5360 | Subcontract - Roofing | expense | cost_of_goods
5370 | Subcontract - Glazing | expense | cost_of_goods
5380 | Subcontract - Masonry | expense | cost_of_goods
5390 | Subcontract - Elevator | expense | cost_of_goods
5400 | Subcontract - Painting | expense | cost_of_goods
5410 | Subcontract - Flooring | expense | cost_of_goods
6000 | Officer Salaries | expense | operating_expense
6010 | Office Staff Salaries | expense | operating_expense
6020 | G&A Payroll Taxes | expense | operating_expense
6030 | Office Rent | expense | operating_expense
6040 | Insurance & Bonding | expense | operating_expense
6050 | Professional Services | expense | operating_expense
6060 | IT & Software | expense | operating_expense
6070 | Marketing & Business Development | expense | operating_expense
6080 | Travel & Entertainment | expense | operating_expense
6090 | Utilities & Telephone | expense | operating_expense
6100 | Depreciation | expense | operating_expense
7000 | Interest Expense | expense | other_expense

## Bank Accounts
name | bank_name | account_type | account_number_last4 | routing_number_last4 | current_balance
Operating Account | Truist Bank | checking | 8812 | 6201 | 3250000.00
Payroll Account | Truist Bank | checking | 8813 | 6201 | 480000.00
Construction Line of Credit | SunTrust / Truist | checking | 2240 | 6201 | 2000000.00
Escrow & Retainage | Bank of America | savings | 5590 | 0530 | 1200000.00

## Projects
name | code | project_type | budget | start_date | end_date | completion_pct | client_name | status | city | state
Peachtree Office Tower | MBG-POT-2024 | Commercial Office | 28000000 | 2024-02-15 | 2026-01-31 | 65 | Peachtree Partners LLC | active | Atlanta | GA
Emory Medical Wing Expansion | MBG-EMW-2024 | Healthcare | 32000000 | 2024-05-01 | 2026-06-30 | 50 | Emory Healthcare | active | Atlanta | GA
Decatur High School Renovation | MBG-DHS-2025 | Education | 15000000 | 2025-01-15 | 2025-12-31 | 25 | DeKalb County Schools | active | Atlanta | GA
Hapeville Distribution Center | MBG-HDC-2025 | Industrial | 10000000 | 2025-03-01 | 2025-11-30 | 15 | Southeast Logistics Group | active | Atlanta | GA

## Contacts
first_name | last_name | email | phone | job_title | contact_type | company_name
Donna | Hamilton | donna.hamilton@meridianbuilders.com | 665-989-3863 | Project Manager | employee | Meridian Builders Group LLC
Louis | Powell | louis.powell@meridianbuilders.com | 949-558-8102 | Project Manager | employee | Meridian Builders Group LLC
Andrea | Lewis | andrea.lewis@meridianbuilders.com | 745-324-2313 | Project Manager | employee | Meridian Builders Group LLC
Elijah | Morton | elijah.morton@meridianbuilders.com | 469-249-4350 | Project Manager | employee | Meridian Builders Group LLC
Christine | Collins | christine.collins@meridianbuilders.com | 516-986-4340 | Superintendent | employee | Meridian Builders Group LLC
Dorothy | Torres | dorothy.torres@meridianbuilders.com | 393-555-7063 | Superintendent | employee | Meridian Builders Group LLC
Bruce | Sullivan | bruce.sullivan@meridianbuilders.com | 415-612-8554 | Superintendent | employee | Meridian Builders Group LLC
Austin | Peterson | austin.peterson@meridianbuilders.com | 584-364-3033 | Superintendent | employee | Meridian Builders Group LLC
George | Johnson | george.johnson@meridianbuilders.com | 817-605-3418 | Assistant Superintendent | employee | Meridian Builders Group LLC
Dylan | Adams | dylan.adams@meridianbuilders.com | 397-371-1428 | Assistant Superintendent | employee | Meridian Builders Group LLC
Eugene | Stewart | eugene.stewart@meridianbuilders.com | 658-853-7351 | Assistant Superintendent | employee | Meridian Builders Group LLC
Steven | Wilson | steven.wilson@meridianbuilders.com | 823-453-9308 | Assistant Superintendent | employee | Meridian Builders Group LLC
Randy | Howard | randy.howard@meridianbuilders.com | 906-804-6549 | Project Engineer | employee | Meridian Builders Group LLC
Jacqueline | Mendoza | jacqueline.mendoza@meridianbuilders.com | 755-571-8922 | Project Engineer | employee | Meridian Builders Group LLC
Aaron | Thomas | aaron.thomas@meridianbuilders.com | 303-507-8118 | Project Engineer | employee | Meridian Builders Group LLC
Nicholas | Morris | nicholas.morris@meridianbuilders.com | 923-931-8166 | Project Engineer | employee | Meridian Builders Group LLC
Cheryl | Ellis | cheryl.ellis@meridianbuilders.com | 796-460-3411 | Foreman | employee | Meridian Builders Group LLC
Joseph | Wood | joseph.wood@meridianbuilders.com | 368-255-5508 | Foreman | employee | Meridian Builders Group LLC
Louis | Walker | louis.walker@meridianbuilders.com | 935-251-4590 | Foreman | employee | Meridian Builders Group LLC
Helen | Burke | helen.burke@meridianbuilders.com | 836-421-6852 | Foreman | employee | Meridian Builders Group LLC
Christine | Morton | christine.morton@meridianbuilders.com | 212-906-2868 | Foreman | employee | Meridian Builders Group LLC
Joan | Roberts | joan.roberts@meridianbuilders.com | 737-321-4426 | Foreman | employee | Meridian Builders Group LLC
Barbara | Jimenez | barbara.jimenez@meridianbuilders.com | 942-306-7563 | Laborer | employee | Meridian Builders Group LLC
Marilyn | Hill | marilyn.hill@meridianbuilders.com | 833-875-8810 | Laborer | employee | Meridian Builders Group LLC
Gloria | Martinez | gloria.martinez@meridianbuilders.com | 917-655-3639 | Laborer | employee | Meridian Builders Group LLC
Richard | Cole | richard.cole@meridianbuilders.com | 973-248-4246 | Laborer | employee | Meridian Builders Group LLC
Amy | Green | amy.green@meridianbuilders.com | 296-239-3293 | Laborer | employee | Meridian Builders Group LLC
Jason | White | jason.white@meridianbuilders.com | 325-457-2094 | Laborer | employee | Meridian Builders Group LLC
Wayne | Perry | wayne.perry@meridianbuilders.com | 237-753-7984 | Laborer | employee | Meridian Builders Group LLC
Joan | Aguilar | joan.aguilar@meridianbuilders.com | 551-912-8441 | Laborer | employee | Meridian Builders Group LLC
Harry | Roberts | harry.roberts@meridianbuilders.com | 821-793-5115 | Safety Director | employee | Meridian Builders Group LLC
Nathan | Nguyen | nathan.nguyen@meridianbuilders.com | 413-622-2268 | Quality Control Manager | employee | Meridian Builders Group LLC
Janice | Morgan | janice.morgan@meridianbuilders.com | 610-466-2555 | President / CEO | employee | Meridian Builders Group LLC
Timothy | Collins | timothy.collins@meridianbuilders.com | 248-599-5446 | VP of Operations | employee | Meridian Builders Group LLC
James | Cooper | james.cooper@meridianbuilders.com | 511-238-1427 | VP of Preconstruction | employee | Meridian Builders Group LLC
Austin | Ramos | austin.ramos@meridianbuilders.com | 437-612-1159 | CFO / Controller | employee | Meridian Builders Group LLC
Denise | Lee | denise.lee@meridianbuilders.com | 424-505-1377 | Office Manager | employee | Meridian Builders Group LLC
Daniel | Price | daniel.price@meridianbuilders.com | 531-889-8279 | Accounting Manager | employee | Meridian Builders Group LLC
David | Mitchell | david.mitchell@meridianbuilders.com | 285-223-6774 | HR Director | employee | Meridian Builders Group LLC
Teresa | Torres | teresa.torres@meridianbuilders.com | 362-913-1052 | Estimator | employee | Meridian Builders Group LLC

## Vendors
company_name | first_name | last_name | job_title | email | phone
Peach State Electrical | Philip | Brown | Account Manager | philip.brown@peachstateelectr.com | 920-527-9312
Southeastern Mechanical | Diane | Hall | Account Manager | diane.hall@southeasternmech.com | 589-591-8317
Atlanta Steel Erectors | Ronald | Diaz | Account Manager | ronald.diaz@atlantasteelerec.com | 364-815-5436
Magnolia Concrete Works | Christopher | Hamilton | Account Manager | christopher.hamilton@magnoliaconcrete.com | 848-964-3229
Capitol Drywall & Ceilings | Virginia | McDonald | Account Manager | virginia.mcdonald@capitoldrywallce.com | 313-867-5928
Dogwood Fire Protection | Steven | Lewis | Account Manager | steven.lewis@dogwoodfireprote.com | 792-830-4655
Piedmont Roofing Systems | Richard | Powell | Account Manager | richard.powell@piedmontroofings.com | 669-640-6758
Buckhead Glass & Glazing | Daniel | Moore | Account Manager | daniel.moore@buckheadglassgla.com | 247-652-7819
Heritage Masonry Inc | Jennifer | Flores | Account Manager | jennifer.flores@heritagemasonryi.com | 692-308-2450
Southern Elevator Co | Emma | Harris | Account Manager | emma.harris@southernelevator.com | 768-780-3408
Chattahoochee Painting | Emily | Nguyen | Account Manager | emily.nguyen@chattahoocheepai.com | 374-566-7216
Northside Flooring | Vincent | Clark | Account Manager | vincent.clark@northsidefloorin.com | 861-696-6293
HD Supply | Sandra | Woods | Account Manager | sandra.woods@hdsupply.com | 488-432-6706
Ferguson Enterprises | Ryan | Rodriguez | Account Manager | ryan.rodriguez@fergusonenterpri.com | 214-430-9300
Graybar Electric | Mark | Thompson | Account Manager | mark.thompson@graybarelectric.com | 328-680-1853
US LBM Holdings | Elijah | West | Account Manager | elijah.west@uslbmholdings.com | 558-722-8822
ABC Supply Co | Edward | Ellis | Account Manager | edward.ellis@abcsupplyco.com | 248-887-9294
Builders FirstSource | Albert | Rogers | Account Manager | albert.rogers@buildersfirstsou.com | 230-819-9607
Fastenal Company | Harry | Ramirez | Account Manager | harry.ramirez@fastenalcompany.com | 905-388-1648
Georgia Concrete & Products | Lawrence | Reyes | Account Manager | lawrence.reyes@georgiaconcretep.com | 674-911-1179

## Equipment
name | equipment_type | serial_number | make | model | year | purchase_cost | status
Tower Crane TC-1 | crane | ENLWDK5PWLFV | Liebherr | 200 EC-H 10 | 2020 | 0 | active
Tower Crane TC-2 | crane | XFGPDVLFD76H | Potain | MCT 205 | 2021 | 0 | active
Crawler Excavator | excavator | SRVX4PMCC9FP | Caterpillar | 330 GC | 2022 | 0 | active
Backhoe Loader | backhoe | HJ8O6OM0ISBO | John Deere | 310SL | 2021 | 0 | active
Skid Steer Loader | loader | ZE2RHXI8QMJV | Bobcat | S770 | 2022 | 0 | active
Telehandler 10K | telehandler | BCBX1QW4TNFE | JCB | 510-56 | 2023 | 0 | active
Telehandler 12K | telehandler | GROO10TGIA2K | JCB | 512-56 | 2021 | 0 | active
Boom Lift 80ft | aerial_lift | R77OBJMMZCKW | JLG | 800S | 2022 | 0 | active
Boom Lift 60ft | aerial_lift | FLIPAJCZ953J | JLG | 600S | 2023 | 0 | active
Scissor Lift 40ft | aerial_lift | P7T0WY5RWLD1 | Genie | GS-4047 | 2022 | 0 | active
Concrete Pump Truck | pump | W6HDWFOBLO3P | Putzmeister | 42Z-Meter | 2020 | 0 | active
Pickup Truck #1 | vehicle | IYVCN5KA3V32 | Ford | F-250 Super Duty | 2023 | 0 | active
Pickup Truck #2 | vehicle | RZ4EF3KA9519 | Ford | F-250 Super Duty | 2023 | 0 | active
Pickup Truck #3 | vehicle | 2UI86134OK4N | Chevrolet | Silverado 2500HD | 2022 | 0 | active
Pickup Truck #4 | vehicle | U2RU9FSCSNHE | Ram | 2500 Tradesman | 2022 | 0 | active
Flatbed Truck | vehicle | INL06RWTXMOC | Ford | F-550 | 2021 | 0 | active
Generator 100kW | generator | I3A9BN4XRJEZ | Caterpillar | XQ100 | 2022 | 0 | active
Generator 60kW | generator | WVKCE25XJBD3 | Generac | MDG75DF4 | 2023 | 0 | active

## Phases
name | code | start_date | end_date | status | project_name
Preconstruction | 01 00 00 | 2024-02-15 | 2024-06-13 | active | Peachtree Office Tower
Site Work & Foundations | 31 00 00 | 2024-06-13 | 2024-10-10 | active | Peachtree Office Tower
Structural | 03 00 00 | 2024-10-10 | 2025-02-06 | active | Peachtree Office Tower
Building Envelope | 07 00 00 | 2025-02-06 | 2025-06-05 | active | Peachtree Office Tower
MEP Rough-In | 23 00 00 | 2025-06-05 | 2025-10-02 | pending | Peachtree Office Tower
Finishes & Closeout | 09 00 00 | 2025-10-02 | 2026-01-31 | pending | Peachtree Office Tower
Preconstruction | 01 00 00 | 2024-05-01 | 2024-09-09 | active | Emory Medical Wing Expansion
Site Work & Foundations | 31 00 00 | 2024-09-09 | 2025-01-18 | active | Emory Medical Wing Expansion
Structural | 03 00 00 | 2025-01-18 | 2025-05-29 | active | Emory Medical Wing Expansion
Building Envelope | 07 00 00 | 2025-05-29 | 2025-10-07 | active | Emory Medical Wing Expansion
MEP Rough-In | 23 00 00 | 2025-10-07 | 2026-02-15 | pending | Emory Medical Wing Expansion
Finishes & Closeout | 09 00 00 | 2026-02-15 | 2026-06-30 | pending | Emory Medical Wing Expansion
Preconstruction | 01 00 00 | 2025-01-15 | 2025-03-14 | active | Decatur High School Renovation
Site Work & Foundations | 31 00 00 | 2025-03-14 | 2025-05-11 | active | Decatur High School Renovation
Structural | 03 00 00 | 2025-05-11 | 2025-07-08 | active | Decatur High School Renovation
Building Envelope | 07 00 00 | 2025-07-08 | 2025-09-04 | active | Decatur High School Renovation
MEP Rough-In | 23 00 00 | 2025-09-04 | 2025-11-01 | pending | Decatur High School Renovation
Finishes & Closeout | 09 00 00 | 2025-11-01 | 2025-12-31 | pending | Decatur High School Renovation
Preconstruction | 01 00 00 | 2025-03-01 | 2025-04-15 | active | Hapeville Distribution Center
Site Work & Foundations | 31 00 00 | 2025-04-15 | 2025-05-30 | active | Hapeville Distribution Center
Structural | 03 00 00 | 2025-05-30 | 2025-07-14 | active | Hapeville Distribution Center
Building Envelope | 07 00 00 | 2025-07-14 | 2025-08-28 | active | Hapeville Distribution Center
MEP Rough-In | 23 00 00 | 2025-08-28 | 2025-10-12 | pending | Hapeville Distribution Center
Finishes & Closeout | 09 00 00 | 2025-10-12 | 2025-11-30 | pending | Hapeville Distribution Center

## Contracts
contract_number | title | contract_type | contract_amount | start_date | end_date | status | project_name | party_name | payment_terms | scope_of_work
MBG-PRIME-001 | Peachtree Office Tower — Prime Contract | prime | 28000000 | 2024-02-15 | 2026-01-31 | active | Peachtree Office Tower | Peachtree Partners LLC | AIA G702/G703, Net 30, 10% retainage | General construction services for Peachtree Office Tower
MBG-PRIME-002 | Emory Medical Wing Expansion — Prime Contract | prime | 32000000 | 2024-05-01 | 2026-06-30 | active | Emory Medical Wing Expansion | Emory Healthcare | AIA G702/G703, Net 30, 10% retainage | General construction services for Emory Medical Wing Expansion
MBG-PRIME-003 | Decatur High School Renovation — Prime Contract | prime | 15000000 | 2025-01-15 | 2025-12-31 | active | Decatur High School Renovation | DeKalb County Schools | AIA G702/G703, Net 30, 10% retainage | General construction services for Decatur High School Renovation
MBG-PRIME-004 | Hapeville Distribution Center — Prime Contract | prime | 10000000 | 2025-03-01 | 2025-11-30 | active | Hapeville Distribution Center | Southeast Logistics Group | AIA G702/G703, Net 30, 10% retainage | General construction services for Hapeville Distribution Center
MBG-SUB-005 | Peachtree Office Tower — Electrical Subcontract | subcontract | 1929695.95 | 2024-02-15 | 2026-01-31 | active | Peachtree Office Tower | Peach State Electrical | Net 30, 10% retainage | Electrical scope for Peachtree Office Tower
MBG-SUB-006 | Peachtree Office Tower — HVAC & Plumbing Subcontract | subcontract | 1595903.12 | 2024-02-15 | 2026-01-31 | active | Peachtree Office Tower | Southeastern Mechanical | Net 30, 10% retainage | HVAC & Plumbing scope for Peachtree Office Tower
MBG-SUB-007 | Peachtree Office Tower — Structural Steel Subcontract | subcontract | 1805288.52 | 2024-02-15 | 2026-01-31 | active | Peachtree Office Tower | Atlanta Steel Erectors | Net 30, 10% retainage | Structural Steel scope for Peachtree Office Tower
MBG-SUB-008 | Peachtree Office Tower — Concrete & Foundations Subcontract | subcontract | 2354058.11 | 2024-02-15 | 2026-01-31 | active | Peachtree Office Tower | Magnolia Concrete Works | Net 30, 10% retainage | Concrete & Foundations scope for Peachtree Office Tower
MBG-SUB-009 | Peachtree Office Tower — Drywall & Framing Subcontract | subcontract | 2312567.91 | 2024-02-15 | 2026-01-31 | active | Peachtree Office Tower | Capitol Drywall & Ceilings | Net 30, 10% retainage | Drywall & Framing scope for Peachtree Office Tower
MBG-SUB-010 | Peachtree Office Tower — Fire Sprinkler Subcontract | subcontract | 2791511.54 | 2024-02-15 | 2026-01-31 | active | Peachtree Office Tower | Dogwood Fire Protection | Net 30, 10% retainage | Fire Sprinkler scope for Peachtree Office Tower
MBG-SUB-011 | Emory Medical Wing Expansion — Electrical Subcontract | subcontract | 2677537.92 | 2024-05-01 | 2026-06-30 | active | Emory Medical Wing Expansion | Peach State Electrical | Net 30, 10% retainage | Electrical scope for Emory Medical Wing Expansion
MBG-SUB-012 | Emory Medical Wing Expansion — HVAC & Plumbing Subcontract | subcontract | 3184454.82 | 2024-05-01 | 2026-06-30 | active | Emory Medical Wing Expansion | Southeastern Mechanical | Net 30, 10% retainage | HVAC & Plumbing scope for Emory Medical Wing Expansion
MBG-SUB-013 | Emory Medical Wing Expansion — Roofing & Waterproofing Subcontract | subcontract | 1910141.13 | 2024-05-01 | 2026-06-30 | active | Emory Medical Wing Expansion | Piedmont Roofing Systems | Net 30, 10% retainage | Roofing & Waterproofing scope for Emory Medical Wing Expansion
MBG-SUB-014 | Emory Medical Wing Expansion — Curtain Wall & Glazing Subcontract | subcontract | 1811455.32 | 2024-05-01 | 2026-06-30 | active | Emory Medical Wing Expansion | Buckhead Glass & Glazing | Net 30, 10% retainage | Curtain Wall & Glazing scope for Emory Medical Wing Expansion
MBG-SUB-015 | Emory Medical Wing Expansion — Masonry Subcontract | subcontract | 3194523.01 | 2024-05-01 | 2026-06-30 | active | Emory Medical Wing Expansion | Heritage Masonry Inc | Net 30, 10% retainage | Masonry scope for Emory Medical Wing Expansion

## Opportunities
name | description | estimated_value | status | probability | expected_close_date | client_name
Buckhead Mixed-Use Development | 30-story mixed-use with 200 residential units and ground-floor retail. $65M estimated. | 65000000 | proposal | 40 | 2025-06-30 | Buckhead Investment Group
CDC Laboratory Building Renovation | BSL-3 laboratory renovation at CDC headquarters. Federal contract, IDIQ vehicle. | 22000000 | qualified | 25 | 2025-09-15 | US Centers for Disease Control
Hartsfield-Jackson Concourse T Extension | Extension of domestic terminal concourse. 8 new gates, hold rooms, and retail. | 45000000 | tracking | 15 | 2026-01-15 | City of Atlanta - DOA
Georgia Tech Student Center | New 80,000 SF student center with dining, event space, and student org offices. | 28000000 | proposal | 50 | 2025-05-01 | Georgia Institute of Technology

## Bids
bid_number | title | bid_amount | status | submission_date | description
MBG-BID-2025-001 | Georgia Tech Student Center — GMP Proposal | 28500000 | submitted | 2025-03-15 | GMP proposal for new student center. Includes self-perform concrete and sitework.
MBG-BID-2025-002 | Buckhead Mixed-Use — Conceptual Budget | 67000000 | draft |  | Conceptual budget for mixed-use tower. Pre-qualification phase.
MBG-BID-2025-003 | CDC Lab Renovation — Technical Proposal | 23500000 | submitted | 2025-04-01 | Technical proposal for BSL-3 lab renovation. Past performance and key personnel.

## Budget Lines
description | cost_code | estimated_amount | project_name
General Conditions | 01 00 00 | 1400000.00 | Peachtree Office Tower
Sitework & Foundations | 31 00 00 | 3360000.00 | Peachtree Office Tower
Concrete | 03 00 00 | 2800000.00 | Peachtree Office Tower
Structural Steel | 05 00 00 | 4200000.00 | Peachtree Office Tower
Electrical | 26 00 00 | 3360000.00 | Peachtree Office Tower
Mechanical / HVAC | 23 00 00 | 3920000.00 | Peachtree Office Tower
Plumbing | 22 00 00 | 2240000.00 | Peachtree Office Tower
Building Envelope | 07 00 00 | 2800000.00 | Peachtree Office Tower
Interior Finishes | 09 00 00 | 2520000.00 | Peachtree Office Tower
Contingency | 01 04 00 | 1400000.00 | Peachtree Office Tower
General Conditions | 01 00 00 | 1600000.00 | Emory Medical Wing Expansion
Sitework & Foundations | 31 00 00 | 3840000.00 | Emory Medical Wing Expansion
Concrete | 03 00 00 | 3200000.00 | Emory Medical Wing Expansion
Structural Steel | 05 00 00 | 4800000.00 | Emory Medical Wing Expansion
Electrical | 26 00 00 | 3840000.00 | Emory Medical Wing Expansion
Mechanical / HVAC | 23 00 00 | 4480000.00 | Emory Medical Wing Expansion
Plumbing | 22 00 00 | 2560000.00 | Emory Medical Wing Expansion
Building Envelope | 07 00 00 | 3200000.00 | Emory Medical Wing Expansion
Interior Finishes | 09 00 00 | 2880000.00 | Emory Medical Wing Expansion
Contingency | 01 04 00 | 1600000.00 | Emory Medical Wing Expansion
General Conditions | 01 00 00 | 750000.00 | Decatur High School Renovation
Sitework & Foundations | 31 00 00 | 1800000.00 | Decatur High School Renovation
Concrete | 03 00 00 | 1500000.00 | Decatur High School Renovation
Structural Steel | 05 00 00 | 2250000.00 | Decatur High School Renovation
Electrical | 26 00 00 | 1800000.00 | Decatur High School Renovation
Mechanical / HVAC | 23 00 00 | 2100000.00 | Decatur High School Renovation
Plumbing | 22 00 00 | 1200000.00 | Decatur High School Renovation
Building Envelope | 07 00 00 | 1500000.00 | Decatur High School Renovation
Interior Finishes | 09 00 00 | 1350000.00 | Decatur High School Renovation
Contingency | 01 04 00 | 750000.00 | Decatur High School Renovation
General Conditions | 01 00 00 | 500000.00 | Hapeville Distribution Center
Sitework & Foundations | 31 00 00 | 1200000.00 | Hapeville Distribution Center
Concrete | 03 00 00 | 1000000.00 | Hapeville Distribution Center
Structural Steel | 05 00 00 | 1500000.00 | Hapeville Distribution Center
Electrical | 26 00 00 | 1200000.00 | Hapeville Distribution Center
Mechanical / HVAC | 23 00 00 | 1400000.00 | Hapeville Distribution Center
Plumbing | 22 00 00 | 800000.00 | Hapeville Distribution Center
Building Envelope | 07 00 00 | 1000000.00 | Hapeville Distribution Center
Interior Finishes | 09 00 00 | 900000.00 | Hapeville Distribution Center
Contingency | 01 04 00 | 500000.00 | Hapeville Distribution Center

## Invoices
invoice_number | invoice_type | invoice_date | due_date | amount | tax_amount | gl_account | retainage_pct | retainage_held | status | description | project_name | client_name | vendor_name
MBG-OB-R01 | receivable | 2024-12-31 | 2024-12-31 | 2800000.00 |  | 3010 | 0 | 0 | paid | Opening balance — prior progress billing Peachtree Office Tower | Peachtree Office Tower | Peachtree Partners LLC
MBG-OB-R02 | receivable | 2024-12-31 | 2024-12-31 | 3200000.00 |  | 3010 | 0 | 0 | paid | Opening balance — prior progress billing Emory Medical Wing Expansion | Emory Medical Wing Expansion | Emory Healthcare
MBG-OB-P01 | payable | 2024-12-31 | 2024-12-31 | 1200000.00 |  | 3010 | 0 | 0 | paid | Opening balance — prior vendor payment #1 | Peachtree Office Tower |  | Peach State Electrical
MBG-OB-P02 | payable | 2024-12-31 | 2024-12-31 | 900000.00 |  | 3010 | 0 | 0 | paid | Opening balance — prior vendor payment #2 | Emory Medical Wing Expansion |  | Southeastern Mechanical
MBG-OB-P03 | payable | 2024-12-31 | 2024-12-31 | 600000.00 |  | 3010 | 0 | 0 | paid | Opening balance — prior vendor payment #3 | Peachtree Office Tower |  | HD Supply
MBG-202501-R01 | receivable | 2025-01-31 | 2025-02-28 | 2036832.35 |  | 4000 | 10 | 203683.24 | paid | Progress billing — Peachtree Office Tower — January | Peachtree Office Tower | Peachtree Partners LLC
MBG-202501-R02 | receivable | 2025-01-31 | 2025-02-28 | 2285138.53 |  | 4000 | 10 | 228513.85 | paid | Progress billing — Emory Medical Wing Expansion — January | Emory Medical Wing Expansion | Emory Healthcare
MBG-202501-R03 | receivable | 2025-01-31 | 2025-02-28 | 1063857.04 |  | 4000 | 10 | 106385.70 | paid | Progress billing — Decatur High School Renovation — January | Decatur High School Renovation | DeKalb County Schools
MBG-202501-R04 | receivable | 2025-01-31 | 2025-02-28 | 703975.46 |  | 4000 | 10 | 70397.55 | paid | Progress billing — Hapeville Distribution Center — January | Hapeville Distribution Center | Southeast Logistics Group
MBG-202502-R01 | receivable | 2025-02-28 | 2025-03-31 | 2037008.19 |  | 4000 | 10 | 203700.82 | paid | Progress billing — Peachtree Office Tower — February | Peachtree Office Tower | Peachtree Partners LLC
MBG-202502-R02 | receivable | 2025-02-28 | 2025-03-31 | 2290989.03 |  | 4000 | 10 | 229098.90 | paid | Progress billing — Emory Medical Wing Expansion — February | Emory Medical Wing Expansion | Emory Healthcare
MBG-202502-R03 | receivable | 2025-02-28 | 2025-03-31 | 1093937.23 |  | 4000 | 10 | 109393.72 | paid | Progress billing — Decatur High School Renovation — February | Decatur High School Renovation | DeKalb County Schools
MBG-202502-R04 | receivable | 2025-02-28 | 2025-03-31 | 714364.44 |  | 4000 | 10 | 71436.44 | paid | Progress billing — Hapeville Distribution Center — February | Hapeville Distribution Center | Southeast Logistics Group
MBG-202503-R01 | receivable | 2025-03-31 | 2025-04-30 | 2302797.08 |  | 4000 | 10 | 230279.71 | paid | Progress billing — Peachtree Office Tower — March | Peachtree Office Tower | Peachtree Partners LLC
MBG-202503-R02 | receivable | 2025-03-31 | 2025-04-30 | 2580043.77 |  | 4000 | 10 | 258004.38 | paid | Progress billing — Emory Medical Wing Expansion — March | Emory Medical Wing Expansion | Emory Healthcare
MBG-202503-R03 | receivable | 2025-03-31 | 2025-04-30 | 1199823.69 |  | 4000 | 10 | 119982.37 | paid | Progress billing — Decatur High School Renovation — March | Decatur High School Renovation | DeKalb County Schools
MBG-202503-R04 | receivable | 2025-03-31 | 2025-04-30 | 814204.50 |  | 4000 | 10 | 81420.45 | paid | Progress billing — Hapeville Distribution Center — March | Hapeville Distribution Center | Southeast Logistics Group
MBG-202504-R01 | receivable | 2025-04-30 | 2025-05-31 | 2392947.13 |  | 4000 | 10 | 239294.71 | paid | Progress billing — Peachtree Office Tower — April | Peachtree Office Tower | Peachtree Partners LLC
MBG-202504-R02 | receivable | 2025-04-30 | 2025-05-31 | 2781833.13 |  | 4000 | 10 | 278183.31 | paid | Progress billing — Emory Medical Wing Expansion — April | Emory Medical Wing Expansion | Emory Healthcare
MBG-202504-R03 | receivable | 2025-04-30 | 2025-05-31 | 1306547.32 |  | 4000 | 10 | 130654.73 | paid | Progress billing — Decatur High School Renovation — April | Decatur High School Renovation | DeKalb County Schools
MBG-202504-R04 | receivable | 2025-04-30 | 2025-05-31 | 868668.83 |  | 4000 | 10 | 86866.88 | paid | Progress billing — Hapeville Distribution Center — April | Hapeville Distribution Center | Southeast Logistics Group
MBG-202505-R01 | receivable | 2025-05-31 | 2025-06-30 | 2638275.26 |  | 4000 | 10 | 263827.53 | paid | Progress billing — Peachtree Office Tower — May | Peachtree Office Tower | Peachtree Partners LLC
MBG-202505-R02 | receivable | 2025-05-31 | 2025-06-30 | 2988659.83 |  | 4000 | 10 | 298865.98 | paid | Progress billing — Emory Medical Wing Expansion — May | Emory Medical Wing Expansion | Emory Healthcare
MBG-202505-R03 | receivable | 2025-05-31 | 2025-06-30 | 1428028.26 |  | 4000 | 10 | 142802.83 | paid | Progress billing — Decatur High School Renovation — May | Decatur High School Renovation | DeKalb County Schools
MBG-202505-R04 | receivable | 2025-05-31 | 2025-06-30 | 936012.11 |  | 4000 | 10 | 93601.21 | paid | Progress billing — Hapeville Distribution Center — May | Hapeville Distribution Center | Southeast Logistics Group
MBG-202506-R01 | receivable | 2025-06-30 | 2025-07-31 | 2792349.11 |  | 4000 | 10 | 279234.91 | paid | Progress billing — Peachtree Office Tower — June | Peachtree Office Tower | Peachtree Partners LLC
MBG-202506-R02 | receivable | 2025-06-30 | 2025-07-31 | 3032874.01 |  | 4000 | 10 | 303287.40 | paid | Progress billing — Emory Medical Wing Expansion — June | Emory Medical Wing Expansion | Emory Healthcare
MBG-202506-R03 | receivable | 2025-06-30 | 2025-07-31 | 1502782.19 |  | 4000 | 10 | 150278.22 | paid | Progress billing — Decatur High School Renovation — June | Decatur High School Renovation | DeKalb County Schools
MBG-202506-R04 | receivable | 2025-06-30 | 2025-07-31 | 961032.78 |  | 4000 | 10 | 96103.28 | paid | Progress billing — Hapeville Distribution Center — June | Hapeville Distribution Center | Southeast Logistics Group
MBG-202507-R01 | receivable | 2025-07-31 | 2025-08-31 | 2789169.83 |  | 4000 | 10 | 278916.98 | paid | Progress billing — Peachtree Office Tower — July | Peachtree Office Tower | Peachtree Partners LLC
MBG-202507-R02 | receivable | 2025-07-31 | 2025-08-31 | 3088164.12 |  | 4000 | 10 | 308816.41 | paid | Progress billing — Emory Medical Wing Expansion — July | Emory Medical Wing Expansion | Emory Healthcare
MBG-202507-R03 | receivable | 2025-07-31 | 2025-08-31 | 1465315.02 |  | 4000 | 10 | 146531.50 | paid | Progress billing — Decatur High School Renovation — July | Decatur High School Renovation | DeKalb County Schools
MBG-202507-R04 | receivable | 2025-07-31 | 2025-08-31 | 986794.16 |  | 4000 | 10 | 98679.42 | paid | Progress billing — Hapeville Distribution Center — July | Hapeville Distribution Center | Southeast Logistics Group
MBG-202508-R01 | receivable | 2025-08-31 | 2025-09-30 | 2586981.02 |  | 4000 | 10 | 258698.10 | paid | Progress billing — Peachtree Office Tower — August | Peachtree Office Tower | Peachtree Partners LLC
MBG-202508-R02 | receivable | 2025-08-31 | 2025-09-30 | 3009486.91 |  | 4000 | 10 | 300948.69 | paid | Progress billing — Emory Medical Wing Expansion — August | Emory Medical Wing Expansion | Emory Healthcare
MBG-202508-R03 | receivable | 2025-08-31 | 2025-09-30 | 1368207.18 |  | 4000 | 10 | 136820.72 | paid | Progress billing — Decatur High School Renovation — August | Decatur High School Renovation | DeKalb County Schools
MBG-202508-R04 | receivable | 2025-08-31 | 2025-09-30 | 917109.47 |  | 4000 | 10 | 91710.95 | paid | Progress billing — Hapeville Distribution Center — August | Hapeville Distribution Center | Southeast Logistics Group
MBG-202509-R01 | receivable | 2025-09-30 | 2025-10-31 | 2419653.95 |  | 4000 | 10 | 241965.40 | paid | Progress billing — Peachtree Office Tower — September | Peachtree Office Tower | Peachtree Partners LLC
MBG-202509-R02 | receivable | 2025-09-30 | 2025-10-31 | 2786773.07 |  | 4000 | 10 | 278677.31 | paid | Progress billing — Emory Medical Wing Expansion — September | Emory Medical Wing Expansion | Emory Healthcare
MBG-202509-R03 | receivable | 2025-09-30 | 2025-10-31 | 1279200.33 |  | 4000 | 10 | 127920.03 | paid | Progress billing — Decatur High School Renovation — September | Decatur High School Renovation | DeKalb County Schools
MBG-202509-R04 | receivable | 2025-09-30 | 2025-10-31 | 822926.46 |  | 4000 | 10 | 82292.65 | paid | Progress billing — Hapeville Distribution Center — September | Hapeville Distribution Center | Southeast Logistics Group
MBG-202510-R01 | receivable | 2025-10-31 | 2025-11-30 | 2245125.04 |  | 4000 | 10 | 224512.50 | paid | Progress billing — Peachtree Office Tower — October | Peachtree Office Tower | Peachtree Partners LLC
MBG-202510-R02 | receivable | 2025-10-31 | 2025-11-30 | 2538732.19 |  | 4000 | 10 | 253873.22 | paid | Progress billing — Emory Medical Wing Expansion — October | Emory Medical Wing Expansion | Emory Healthcare
MBG-202510-R03 | receivable | 2025-10-31 | 2025-11-30 | 1203860.99 |  | 4000 | 10 | 120386.10 | paid | Progress billing — Decatur High School Renovation — October | Decatur High School Renovation | DeKalb County Schools
MBG-202510-R04 | receivable | 2025-10-31 | 2025-11-30 | 787945.07 |  | 4000 | 10 | 78794.51 | paid | Progress billing — Hapeville Distribution Center — October | Hapeville Distribution Center | Southeast Logistics Group
MBG-202511-R01 | receivable | 2025-11-30 | 2025-12-31 | 2058157.01 |  | 4000 | 10 | 205815.70 | pending | Progress billing — Peachtree Office Tower — November | Peachtree Office Tower | Peachtree Partners LLC
MBG-202511-R02 | receivable | 2025-11-30 | 2025-12-31 | 2371150.80 |  | 4000 | 10 | 237115.08 | pending | Progress billing — Emory Medical Wing Expansion — November | Emory Medical Wing Expansion | Emory Healthcare
MBG-202511-R03 | receivable | 2025-11-30 | 2025-12-31 | 1054770.78 |  | 4000 | 10 | 105477.08 | pending | Progress billing — Decatur High School Renovation — November | Decatur High School Renovation | DeKalb County Schools
MBG-202511-R04 | receivable | 2025-11-30 | 2025-12-31 | 741869.33 |  | 4000 | 10 | 74186.93 | pending | Progress billing — Hapeville Distribution Center — November | Hapeville Distribution Center | Southeast Logistics Group
MBG-202512-R01 | receivable | 2025-12-31 | 2025-12-31 | 2059728.96 |  | 4000 | 10 | 205972.90 | pending | Progress billing — Peachtree Office Tower — December | Peachtree Office Tower | Peachtree Partners LLC
MBG-202512-R02 | receivable | 2025-12-31 | 2025-12-31 | 2330753.76 |  | 4000 | 10 | 233075.38 | pending | Progress billing — Emory Medical Wing Expansion — December | Emory Medical Wing Expansion | Emory Healthcare
MBG-202512-R03 | receivable | 2025-12-31 | 2025-12-31 | 1099925.24 |  | 4000 | 10 | 109992.52 | pending | Progress billing — Decatur High School Renovation — December | Decatur High School Renovation | DeKalb County Schools
MBG-202512-R04 | receivable | 2025-12-31 | 2025-12-31 | 235218.04 |  | 4000 | 10 | 23521.80 | pending | Progress billing — Hapeville Distribution Center — December | Hapeville Distribution Center | Southeast Logistics Group
MBG-01-S01 | payable | 2025-01-25 | 2025-01-31 | 330606.40 |  | 5300 | 10 | 33060.64 | paid | Electrical — January | Peachtree Office Tower |  | Peach State Electrical
MBG-01-S02 | payable | 2025-01-25 | 2025-01-31 | 404130.40 |  | 5310 | 10 | 40413.04 | paid | HVAC & Plumbing — January | Peachtree Office Tower |  | Southeastern Mechanical
MBG-01-S03 | payable | 2025-01-25 | 2025-01-31 | 453010.87 |  | 5320 | 10 | 45301.09 | paid | Structural Steel — January | Peachtree Office Tower |  | Atlanta Steel Erectors
MBG-01-S04 | payable | 2025-01-25 | 2025-01-31 | 313857.02 |  | 5330 | 10 | 31385.70 | paid | Concrete & Foundations — January | Peachtree Office Tower |  | Magnolia Concrete Works
MBG-01-S05 | payable | 2025-01-25 | 2025-01-31 | 452502.54 |  | 5340 | 10 | 45250.25 | paid | Drywall & Framing — January | Peachtree Office Tower |  | Capitol Drywall & Ceilings
MBG-01-S06 | payable | 2025-01-25 | 2025-01-31 | 370008.58 |  | 5350 | 10 | 37000.86 | paid | Fire Sprinkler — January | Peachtree Office Tower |  | Dogwood Fire Protection
MBG-01-S07 | payable | 2025-01-25 | 2025-01-31 | 376757.21 |  | 5360 | 10 | 37675.72 | paid | Roofing & Waterproofing — January | Peachtree Office Tower |  | Piedmont Roofing Systems
MBG-01-S08 | payable | 2025-01-25 | 2025-01-31 | 324550.71 |  | 5370 | 10 | 32455.07 | paid | Curtain Wall & Glazing — January | Peachtree Office Tower |  | Buckhead Glass & Glazing
MBG-02-S01 | payable | 2025-02-25 | 2025-02-28 | 316851.57 |  | 5300 | 10 | 31685.16 | paid | Electrical — February | Emory Medical Wing Expansion |  | Peach State Electrical
MBG-02-S02 | payable | 2025-02-25 | 2025-02-28 | 366111.01 |  | 5310 | 10 | 36611.10 | paid | HVAC & Plumbing — February | Emory Medical Wing Expansion |  | Southeastern Mechanical
MBG-02-S03 | payable | 2025-02-25 | 2025-02-28 | 331989.42 |  | 5320 | 10 | 33198.94 | paid | Structural Steel — February | Emory Medical Wing Expansion |  | Atlanta Steel Erectors
MBG-02-S04 | payable | 2025-02-25 | 2025-02-28 | 374267.12 |  | 5330 | 10 | 37426.71 | paid | Concrete & Foundations — February | Emory Medical Wing Expansion |  | Magnolia Concrete Works
MBG-02-S05 | payable | 2025-02-25 | 2025-02-28 | 455158.74 |  | 5340 | 10 | 45515.87 | paid | Drywall & Framing — February | Emory Medical Wing Expansion |  | Capitol Drywall & Ceilings
MBG-02-S06 | payable | 2025-02-25 | 2025-02-28 | 426868.46 |  | 5350 | 10 | 42686.85 | paid | Fire Sprinkler — February | Emory Medical Wing Expansion |  | Dogwood Fire Protection
MBG-02-S07 | payable | 2025-02-25 | 2025-02-28 | 408015.25 |  | 5360 | 10 | 40801.53 | paid | Roofing & Waterproofing — February | Emory Medical Wing Expansion |  | Piedmont Roofing Systems
MBG-02-S08 | payable | 2025-02-25 | 2025-02-28 | 346162.16 |  | 5370 | 10 | 34616.22 | paid | Curtain Wall & Glazing — February | Emory Medical Wing Expansion |  | Buckhead Glass & Glazing
MBG-03-S01 | payable | 2025-03-25 | 2025-03-31 | 519542.07 |  | 5300 | 10 | 51954.21 | paid | Electrical — March | Decatur High School Renovation |  | Peach State Electrical
MBG-03-S02 | payable | 2025-03-25 | 2025-03-31 | 455403.01 |  | 5310 | 10 | 45540.30 | paid | HVAC & Plumbing — March | Decatur High School Renovation |  | Southeastern Mechanical
MBG-03-S03 | payable | 2025-03-25 | 2025-03-31 | 368643.56 |  | 5320 | 10 | 36864.36 | paid | Structural Steel — March | Decatur High School Renovation |  | Atlanta Steel Erectors
MBG-03-S04 | payable | 2025-03-25 | 2025-03-31 | 385126.14 |  | 5330 | 10 | 38512.61 | paid | Concrete & Foundations — March | Decatur High School Renovation |  | Magnolia Concrete Works
MBG-03-S05 | payable | 2025-03-25 | 2025-03-31 | 471740.26 |  | 5340 | 10 | 47174.03 | paid | Drywall & Framing — March | Decatur High School Renovation |  | Capitol Drywall & Ceilings
MBG-03-S06 | payable | 2025-03-25 | 2025-03-31 | 387969.13 |  | 5350 | 10 | 38796.91 | paid | Fire Sprinkler — March | Decatur High School Renovation |  | Dogwood Fire Protection
MBG-03-S07 | payable | 2025-03-25 | 2025-03-31 | 398524.36 |  | 5360 | 10 | 39852.44 | paid | Roofing & Waterproofing — March | Decatur High School Renovation |  | Piedmont Roofing Systems
MBG-03-S08 | payable | 2025-03-25 | 2025-03-31 | 394407.41 |  | 5370 | 10 | 39440.74 | paid | Curtain Wall & Glazing — March | Decatur High School Renovation |  | Buckhead Glass & Glazing
MBG-04-S01 | payable | 2025-04-25 | 2025-04-30 | 391412.64 |  | 5300 | 10 | 39141.26 | paid | Electrical — April | Hapeville Distribution Center |  | Peach State Electrical
MBG-04-S02 | payable | 2025-04-25 | 2025-04-30 | 454688.93 |  | 5310 | 10 | 45468.89 | paid | HVAC & Plumbing — April | Hapeville Distribution Center |  | Southeastern Mechanical
MBG-04-S03 | payable | 2025-04-25 | 2025-04-30 | 440460.05 |  | 5320 | 10 | 44046.01 | paid | Structural Steel — April | Hapeville Distribution Center |  | Atlanta Steel Erectors
MBG-04-S04 | payable | 2025-04-25 | 2025-04-30 | 432741.74 |  | 5330 | 10 | 43274.17 | paid | Concrete & Foundations — April | Hapeville Distribution Center |  | Magnolia Concrete Works
MBG-04-S05 | payable | 2025-04-25 | 2025-04-30 | 420132.77 |  | 5340 | 10 | 42013.28 | paid | Drywall & Framing — April | Hapeville Distribution Center |  | Capitol Drywall & Ceilings
MBG-04-S06 | payable | 2025-04-25 | 2025-04-30 | 482814.23 |  | 5350 | 10 | 48281.42 | paid | Fire Sprinkler — April | Hapeville Distribution Center |  | Dogwood Fire Protection
MBG-04-S07 | payable | 2025-04-25 | 2025-04-30 | 403367.47 |  | 5360 | 10 | 40336.75 | paid | Roofing & Waterproofing — April | Hapeville Distribution Center |  | Piedmont Roofing Systems
MBG-04-S08 | payable | 2025-04-25 | 2025-04-30 | 533704.21 |  | 5370 | 10 | 53370.42 | paid | Curtain Wall & Glazing — April | Hapeville Distribution Center |  | Buckhead Glass & Glazing
MBG-05-S01 | payable | 2025-05-25 | 2025-05-31 | 448548.24 |  | 5300 | 10 | 44854.82 | paid | Electrical — May | Peachtree Office Tower |  | Peach State Electrical
MBG-05-S02 | payable | 2025-05-25 | 2025-05-31 | 559714.82 |  | 5310 | 10 | 55971.48 | paid | HVAC & Plumbing — May | Peachtree Office Tower |  | Southeastern Mechanical
MBG-05-S03 | payable | 2025-05-25 | 2025-05-31 | 452633.57 |  | 5320 | 10 | 45263.36 | paid | Structural Steel — May | Peachtree Office Tower |  | Atlanta Steel Erectors
MBG-05-S04 | payable | 2025-05-25 | 2025-05-31 | 432818.17 |  | 5330 | 10 | 43281.82 | paid | Concrete & Foundations — May | Peachtree Office Tower |  | Magnolia Concrete Works
MBG-05-S05 | payable | 2025-05-25 | 2025-05-31 | 558706.73 |  | 5340 | 10 | 55870.67 | paid | Drywall & Framing — May | Peachtree Office Tower |  | Capitol Drywall & Ceilings
MBG-05-S06 | payable | 2025-05-25 | 2025-05-31 | 526409.63 |  | 5350 | 10 | 52640.96 | paid | Fire Sprinkler — May | Peachtree Office Tower |  | Dogwood Fire Protection
MBG-05-S07 | payable | 2025-05-25 | 2025-05-31 | 413747.61 |  | 5360 | 10 | 41374.76 | paid | Roofing & Waterproofing — May | Peachtree Office Tower |  | Piedmont Roofing Systems
MBG-05-S08 | payable | 2025-05-25 | 2025-05-31 | 522675.48 |  | 5370 | 10 | 52267.55 | paid | Curtain Wall & Glazing — May | Peachtree Office Tower |  | Buckhead Glass & Glazing
MBG-06-S01 | payable | 2025-06-25 | 2025-06-30 | 545329.02 |  | 5300 | 10 | 54532.90 | paid | Electrical — June | Emory Medical Wing Expansion |  | Peach State Electrical
MBG-06-S02 | payable | 2025-06-25 | 2025-06-30 | 542343.46 |  | 5310 | 10 | 54234.35 | paid | HVAC & Plumbing — June | Emory Medical Wing Expansion |  | Southeastern Mechanical
MBG-06-S03 | payable | 2025-06-25 | 2025-06-30 | 478749.74 |  | 5320 | 10 | 47874.97 | paid | Structural Steel — June | Emory Medical Wing Expansion |  | Atlanta Steel Erectors
MBG-06-S04 | payable | 2025-06-25 | 2025-06-30 | 541643.26 |  | 5330 | 10 | 54164.33 | paid | Concrete & Foundations — June | Emory Medical Wing Expansion |  | Magnolia Concrete Works
MBG-06-S05 | payable | 2025-06-25 | 2025-06-30 | 504106.64 |  | 5340 | 10 | 50410.66 | paid | Drywall & Framing — June | Emory Medical Wing Expansion |  | Capitol Drywall & Ceilings
MBG-06-S06 | payable | 2025-06-25 | 2025-06-30 | 563404.91 |  | 5350 | 10 | 56340.49 | paid | Fire Sprinkler — June | Emory Medical Wing Expansion |  | Dogwood Fire Protection
MBG-06-S07 | payable | 2025-06-25 | 2025-06-30 | 480679.50 |  | 5360 | 10 | 48067.95 | paid | Roofing & Waterproofing — June | Emory Medical Wing Expansion |  | Piedmont Roofing Systems
MBG-06-S08 | payable | 2025-06-25 | 2025-06-30 | 436963.81 |  | 5370 | 10 | 43696.38 | paid | Curtain Wall & Glazing — June | Emory Medical Wing Expansion |  | Buckhead Glass & Glazing
MBG-07-S01 | payable | 2025-07-25 | 2025-07-31 | 536528.51 |  | 5300 | 10 | 53652.85 | paid | Electrical — July | Decatur High School Renovation |  | Peach State Electrical
MBG-07-S02 | payable | 2025-07-25 | 2025-07-31 | 484559.45 |  | 5310 | 10 | 48455.95 | paid | HVAC & Plumbing — July | Decatur High School Renovation |  | Southeastern Mechanical
MBG-07-S03 | payable | 2025-07-25 | 2025-07-31 | 531522.42 |  | 5320 | 10 | 53152.24 | paid | Structural Steel — July | Decatur High School Renovation |  | Atlanta Steel Erectors
MBG-07-S04 | payable | 2025-07-25 | 2025-07-31 | 489049.72 |  | 5330 | 10 | 48904.97 | paid | Concrete & Foundations — July | Decatur High School Renovation |  | Magnolia Concrete Works
MBG-07-S05 | payable | 2025-07-25 | 2025-07-31 | 530403.85 |  | 5340 | 10 | 53040.39 | paid | Drywall & Framing — July | Decatur High School Renovation |  | Capitol Drywall & Ceilings
MBG-07-S06 | payable | 2025-07-25 | 2025-07-31 | 600170.99 |  | 5350 | 10 | 60017.10 | paid | Fire Sprinkler — July | Decatur High School Renovation |  | Dogwood Fire Protection
MBG-07-S07 | payable | 2025-07-25 | 2025-07-31 | 425353.74 |  | 5360 | 10 | 42535.37 | paid | Roofing & Waterproofing — July | Decatur High School Renovation |  | Piedmont Roofing Systems
MBG-07-S08 | payable | 2025-07-25 | 2025-07-31 | 495631.66 |  | 5370 | 10 | 49563.17 | paid | Curtain Wall & Glazing — July | Decatur High School Renovation |  | Buckhead Glass & Glazing
MBG-08-S01 | payable | 2025-08-25 | 2025-08-31 | 603496.77 |  | 5300 | 10 | 60349.68 | paid | Electrical — August | Hapeville Distribution Center |  | Peach State Electrical
MBG-08-S02 | payable | 2025-08-25 | 2025-08-31 | 465739.32 |  | 5310 | 10 | 46573.93 | paid | HVAC & Plumbing — August | Hapeville Distribution Center |  | Southeastern Mechanical
MBG-08-S03 | payable | 2025-08-25 | 2025-08-31 | 422141.23 |  | 5320 | 10 | 42214.12 | paid | Structural Steel — August | Hapeville Distribution Center |  | Atlanta Steel Erectors
MBG-08-S04 | payable | 2025-08-25 | 2025-08-31 | 544676.37 |  | 5330 | 10 | 54467.64 | paid | Concrete & Foundations — August | Hapeville Distribution Center |  | Magnolia Concrete Works
MBG-08-S05 | payable | 2025-08-25 | 2025-08-31 | 438337.26 |  | 5340 | 10 | 43833.73 | paid | Drywall & Framing — August | Hapeville Distribution Center |  | Capitol Drywall & Ceilings
MBG-08-S06 | payable | 2025-08-25 | 2025-08-31 | 499278.74 |  | 5350 | 10 | 49927.87 | paid | Fire Sprinkler — August | Hapeville Distribution Center |  | Dogwood Fire Protection
MBG-08-S07 | payable | 2025-08-25 | 2025-08-31 | 465715.60 |  | 5360 | 10 | 46571.56 | paid | Roofing & Waterproofing — August | Hapeville Distribution Center |  | Piedmont Roofing Systems
MBG-08-S08 | payable | 2025-08-25 | 2025-08-31 | 475868.96 |  | 5370 | 10 | 47586.90 | paid | Curtain Wall & Glazing — August | Hapeville Distribution Center |  | Buckhead Glass & Glazing
MBG-09-S01 | payable | 2025-09-25 | 2025-09-30 | 376310.03 |  | 5300 | 10 | 37631.00 | paid | Electrical — September | Peachtree Office Tower |  | Peach State Electrical
MBG-09-S02 | payable | 2025-09-25 | 2025-09-30 | 507015.62 |  | 5310 | 10 | 50701.56 | paid | HVAC & Plumbing — September | Peachtree Office Tower |  | Southeastern Mechanical
MBG-09-S03 | payable | 2025-09-25 | 2025-09-30 | 491753.33 |  | 5320 | 10 | 49175.33 | paid | Structural Steel — September | Peachtree Office Tower |  | Atlanta Steel Erectors
MBG-09-S04 | payable | 2025-09-25 | 2025-09-30 | 394400.72 |  | 5330 | 10 | 39440.07 | paid | Concrete & Foundations — September | Peachtree Office Tower |  | Magnolia Concrete Works
MBG-09-S05 | payable | 2025-09-25 | 2025-09-30 | 430807.66 |  | 5340 | 10 | 43080.77 | paid | Drywall & Framing — September | Peachtree Office Tower |  | Capitol Drywall & Ceilings
MBG-09-S06 | payable | 2025-09-25 | 2025-09-30 | 400536.79 |  | 5350 | 10 | 40053.68 | paid | Fire Sprinkler — September | Peachtree Office Tower |  | Dogwood Fire Protection
MBG-09-S07 | payable | 2025-09-25 | 2025-09-30 | 441769.00 |  | 5360 | 10 | 44176.90 | paid | Roofing & Waterproofing — September | Peachtree Office Tower |  | Piedmont Roofing Systems
MBG-09-S08 | payable | 2025-09-25 | 2025-09-30 | 516728.90 |  | 5370 | 10 | 51672.89 | paid | Curtain Wall & Glazing — September | Peachtree Office Tower |  | Buckhead Glass & Glazing
MBG-10-S01 | payable | 2025-10-25 | 2025-10-31 | 475705.87 |  | 5300 | 10 | 47570.59 | paid | Electrical — October | Emory Medical Wing Expansion |  | Peach State Electrical
MBG-10-S02 | payable | 2025-10-25 | 2025-10-31 | 486042.78 |  | 5310 | 10 | 48604.28 | paid | HVAC & Plumbing — October | Emory Medical Wing Expansion |  | Southeastern Mechanical
MBG-10-S03 | payable | 2025-10-25 | 2025-10-31 | 417935.03 |  | 5320 | 10 | 41793.50 | paid | Structural Steel — October | Emory Medical Wing Expansion |  | Atlanta Steel Erectors
MBG-10-S04 | payable | 2025-10-25 | 2025-10-31 | 348318.15 |  | 5330 | 10 | 34831.82 | paid | Concrete & Foundations — October | Emory Medical Wing Expansion |  | Magnolia Concrete Works
MBG-10-S05 | payable | 2025-10-25 | 2025-10-31 | 355438.91 |  | 5340 | 10 | 35543.89 | paid | Drywall & Framing — October | Emory Medical Wing Expansion |  | Capitol Drywall & Ceilings
MBG-10-S06 | payable | 2025-10-25 | 2025-10-31 | 444188.53 |  | 5350 | 10 | 44418.85 | paid | Fire Sprinkler — October | Emory Medical Wing Expansion |  | Dogwood Fire Protection
MBG-10-S07 | payable | 2025-10-25 | 2025-10-31 | 432168.34 |  | 5360 | 10 | 43216.83 | paid | Roofing & Waterproofing — October | Emory Medical Wing Expansion |  | Piedmont Roofing Systems
MBG-10-S08 | payable | 2025-10-25 | 2025-10-31 | 421558.32 |  | 5370 | 10 | 42155.83 | paid | Curtain Wall & Glazing — October | Emory Medical Wing Expansion |  | Buckhead Glass & Glazing
MBG-11-S01 | payable | 2025-11-25 | 2025-11-30 | 430636.92 |  | 5300 | 10 | 43063.69 | pending | Electrical — November | Decatur High School Renovation |  | Peach State Electrical
MBG-11-S02 | payable | 2025-11-25 | 2025-11-30 | 314323.28 |  | 5310 | 10 | 31432.33 | pending | HVAC & Plumbing — November | Decatur High School Renovation |  | Southeastern Mechanical
MBG-11-S03 | payable | 2025-11-25 | 2025-11-30 | 308410.73 |  | 5320 | 10 | 30841.07 | pending | Structural Steel — November | Decatur High School Renovation |  | Atlanta Steel Erectors
MBG-11-S04 | payable | 2025-11-25 | 2025-11-30 | 442979.49 |  | 5330 | 10 | 44297.95 | pending | Concrete & Foundations — November | Decatur High School Renovation |  | Magnolia Concrete Works
MBG-11-S05 | payable | 2025-11-25 | 2025-11-30 | 348877.13 |  | 5340 | 10 | 34887.71 | pending | Drywall & Framing — November | Decatur High School Renovation |  | Capitol Drywall & Ceilings
MBG-11-S06 | payable | 2025-11-25 | 2025-11-30 | 394287.96 |  | 5350 | 10 | 39428.80 | pending | Fire Sprinkler — November | Decatur High School Renovation |  | Dogwood Fire Protection
MBG-11-S07 | payable | 2025-11-25 | 2025-11-30 | 376735.38 |  | 5360 | 10 | 37673.54 | pending | Roofing & Waterproofing — November | Decatur High School Renovation |  | Piedmont Roofing Systems
MBG-11-S08 | payable | 2025-11-25 | 2025-11-30 | 409172.83 |  | 5370 | 10 | 40917.28 | pending | Curtain Wall & Glazing — November | Decatur High School Renovation |  | Buckhead Glass & Glazing
MBG-12-S01 | payable | 2025-12-25 | 2025-12-31 | 422788.25 |  | 5300 | 10 | 42278.83 | pending | Electrical — December | Hapeville Distribution Center |  | Peach State Electrical
MBG-12-S02 | payable | 2025-12-25 | 2025-12-31 | 343905.51 |  | 5310 | 10 | 34390.55 | pending | HVAC & Plumbing — December | Hapeville Distribution Center |  | Southeastern Mechanical
MBG-12-S03 | payable | 2025-12-25 | 2025-12-31 | 332489.91 |  | 5320 | 10 | 33248.99 | pending | Structural Steel — December | Hapeville Distribution Center |  | Atlanta Steel Erectors
MBG-12-S04 | payable | 2025-12-25 | 2025-12-31 | 336541.48 |  | 5330 | 10 | 33654.15 | pending | Concrete & Foundations — December | Hapeville Distribution Center |  | Magnolia Concrete Works
MBG-12-S05 | payable | 2025-12-25 | 2025-12-31 | 390763.33 |  | 5340 | 10 | 39076.33 | pending | Drywall & Framing — December | Hapeville Distribution Center |  | Capitol Drywall & Ceilings
MBG-12-S06 | payable | 2025-12-25 | 2025-12-31 | 447877.33 |  | 5350 | 10 | 44787.73 | pending | Fire Sprinkler — December | Hapeville Distribution Center |  | Dogwood Fire Protection
MBG-12-S07 | payable | 2025-12-25 | 2025-12-31 | 422433.46 |  | 5360 | 10 | 42243.35 | pending | Roofing & Waterproofing — December | Hapeville Distribution Center |  | Piedmont Roofing Systems
MBG-12-S08 | payable | 2025-12-25 | 2025-12-31 | 328624.41 |  | 5370 | 10 | 32862.44 | pending | Curtain Wall & Glazing — December | Hapeville Distribution Center |  | Buckhead Glass & Glazing
MBG-01-M01 | payable | 2025-01-15 | 2025-01-31 | 282261.26 |  | 5000 | 0 | 0 | paid | Construction materials — January | Peachtree Office Tower |  | HD Supply
MBG-01-M02 | payable | 2025-01-15 | 2025-01-31 | 371420.69 |  | 5000 | 0 | 0 | paid | Construction materials — January | Peachtree Office Tower |  | Ferguson Enterprises
MBG-01-M03 | payable | 2025-01-15 | 2025-01-31 | 252079.91 |  | 5000 | 0 | 0 | paid | Construction materials — January | Peachtree Office Tower |  | Graybar Electric
MBG-01-M04 | payable | 2025-01-15 | 2025-01-31 | 260904.80 |  | 5000 | 0 | 0 | paid | Construction materials — January | Peachtree Office Tower |  | US LBM Holdings
MBG-02-M01 | payable | 2025-02-15 | 2025-02-28 | 317586.57 |  | 5000 | 0 | 0 | paid | Construction materials — February | Emory Medical Wing Expansion |  | HD Supply
MBG-02-M02 | payable | 2025-02-15 | 2025-02-28 | 269537.58 |  | 5000 | 0 | 0 | paid | Construction materials — February | Emory Medical Wing Expansion |  | Ferguson Enterprises
MBG-02-M03 | payable | 2025-02-15 | 2025-02-28 | 320988.62 |  | 5000 | 0 | 0 | paid | Construction materials — February | Emory Medical Wing Expansion |  | Graybar Electric
MBG-02-M04 | payable | 2025-02-15 | 2025-02-28 | 258553.89 |  | 5000 | 0 | 0 | paid | Construction materials — February | Emory Medical Wing Expansion |  | US LBM Holdings
MBG-03-M01 | payable | 2025-03-15 | 2025-03-31 | 287779.58 |  | 5000 | 0 | 0 | paid | Construction materials — March | Decatur High School Renovation |  | HD Supply
MBG-03-M02 | payable | 2025-03-15 | 2025-03-31 | 333454.60 |  | 5000 | 0 | 0 | paid | Construction materials — March | Decatur High School Renovation |  | Ferguson Enterprises
MBG-03-M03 | payable | 2025-03-15 | 2025-03-31 | 266794.20 |  | 5000 | 0 | 0 | paid | Construction materials — March | Decatur High School Renovation |  | Graybar Electric
MBG-03-M04 | payable | 2025-03-15 | 2025-03-31 | 278638.30 |  | 5000 | 0 | 0 | paid | Construction materials — March | Decatur High School Renovation |  | US LBM Holdings
MBG-04-M01 | payable | 2025-04-15 | 2025-04-30 | 258975.59 |  | 5000 | 0 | 0 | paid | Construction materials — April | Hapeville Distribution Center |  | HD Supply
MBG-04-M02 | payable | 2025-04-15 | 2025-04-30 | 279813.24 |  | 5000 | 0 | 0 | paid | Construction materials — April | Hapeville Distribution Center |  | Ferguson Enterprises
MBG-04-M03 | payable | 2025-04-15 | 2025-04-30 | 292912.55 |  | 5000 | 0 | 0 | paid | Construction materials — April | Hapeville Distribution Center |  | Graybar Electric
MBG-04-M04 | payable | 2025-04-15 | 2025-04-30 | 334965.29 |  | 5000 | 0 | 0 | paid | Construction materials — April | Hapeville Distribution Center |  | US LBM Holdings
MBG-05-M01 | payable | 2025-05-15 | 2025-05-31 | 263550.78 |  | 5000 | 0 | 0 | paid | Construction materials — May | Peachtree Office Tower |  | HD Supply
MBG-05-M02 | payable | 2025-05-15 | 2025-05-31 | 280793.42 |  | 5000 | 0 | 0 | paid | Construction materials — May | Peachtree Office Tower |  | Ferguson Enterprises
MBG-05-M03 | payable | 2025-05-15 | 2025-05-31 | 328964.68 |  | 5000 | 0 | 0 | paid | Construction materials — May | Peachtree Office Tower |  | Graybar Electric
MBG-05-M04 | payable | 2025-05-15 | 2025-05-31 | 293357.78 |  | 5000 | 0 | 0 | paid | Construction materials — May | Peachtree Office Tower |  | US LBM Holdings
MBG-06-M01 | payable | 2025-06-15 | 2025-06-30 | 305374.94 |  | 5000 | 0 | 0 | paid | Construction materials — June | Emory Medical Wing Expansion |  | HD Supply
MBG-06-M02 | payable | 2025-06-15 | 2025-06-30 | 240411.11 |  | 5000 | 0 | 0 | paid | Construction materials — June | Emory Medical Wing Expansion |  | Ferguson Enterprises
MBG-06-M03 | payable | 2025-06-15 | 2025-06-30 | 304397.98 |  | 5000 | 0 | 0 | paid | Construction materials — June | Emory Medical Wing Expansion |  | Graybar Electric
MBG-06-M04 | payable | 2025-06-15 | 2025-06-30 | 316482.64 |  | 5000 | 0 | 0 | paid | Construction materials — June | Emory Medical Wing Expansion |  | US LBM Holdings
MBG-07-M01 | payable | 2025-07-15 | 2025-07-31 | 267555.93 |  | 5000 | 0 | 0 | paid | Construction materials — July | Decatur High School Renovation |  | HD Supply
MBG-07-M02 | payable | 2025-07-15 | 2025-07-31 | 247345.34 |  | 5000 | 0 | 0 | paid | Construction materials — July | Decatur High School Renovation |  | Ferguson Enterprises
MBG-07-M03 | payable | 2025-07-15 | 2025-07-31 | 338318.08 |  | 5000 | 0 | 0 | paid | Construction materials — July | Decatur High School Renovation |  | Graybar Electric
MBG-07-M04 | payable | 2025-07-15 | 2025-07-31 | 313447.32 |  | 5000 | 0 | 0 | paid | Construction materials — July | Decatur High School Renovation |  | US LBM Holdings
MBG-08-M01 | payable | 2025-08-15 | 2025-08-31 | 264646.50 |  | 5000 | 0 | 0 | paid | Construction materials — August | Hapeville Distribution Center |  | HD Supply
MBG-08-M02 | payable | 2025-08-15 | 2025-08-31 | 285288.40 |  | 5000 | 0 | 0 | paid | Construction materials — August | Hapeville Distribution Center |  | Ferguson Enterprises
MBG-08-M03 | payable | 2025-08-15 | 2025-08-31 | 294583.52 |  | 5000 | 0 | 0 | paid | Construction materials — August | Hapeville Distribution Center |  | Graybar Electric
MBG-08-M04 | payable | 2025-08-15 | 2025-08-31 | 322148.25 |  | 5000 | 0 | 0 | paid | Construction materials — August | Hapeville Distribution Center |  | US LBM Holdings
MBG-09-M01 | payable | 2025-09-15 | 2025-09-30 | 284257.63 |  | 5000 | 0 | 0 | paid | Construction materials — September | Peachtree Office Tower |  | HD Supply
MBG-09-M02 | payable | 2025-09-15 | 2025-09-30 | 327521.56 |  | 5000 | 0 | 0 | paid | Construction materials — September | Peachtree Office Tower |  | Ferguson Enterprises
MBG-09-M03 | payable | 2025-09-15 | 2025-09-30 | 302568.41 |  | 5000 | 0 | 0 | paid | Construction materials — September | Peachtree Office Tower |  | Graybar Electric
MBG-09-M04 | payable | 2025-09-15 | 2025-09-30 | 252319.07 |  | 5000 | 0 | 0 | paid | Construction materials — September | Peachtree Office Tower |  | US LBM Holdings
MBG-10-M01 | payable | 2025-10-15 | 2025-10-31 | 235866.40 |  | 5000 | 0 | 0 | paid | Construction materials — October | Emory Medical Wing Expansion |  | HD Supply
MBG-10-M02 | payable | 2025-10-15 | 2025-10-31 | 295707.55 |  | 5000 | 0 | 0 | paid | Construction materials — October | Emory Medical Wing Expansion |  | Ferguson Enterprises
MBG-10-M03 | payable | 2025-10-15 | 2025-10-31 | 327783.97 |  | 5000 | 0 | 0 | paid | Construction materials — October | Emory Medical Wing Expansion |  | Graybar Electric
MBG-10-M04 | payable | 2025-10-15 | 2025-10-31 | 307308.75 |  | 5000 | 0 | 0 | paid | Construction materials — October | Emory Medical Wing Expansion |  | US LBM Holdings
MBG-11-M01 | payable | 2025-11-15 | 2025-11-30 | 287250.83 |  | 5000 | 0 | 0 | pending | Construction materials — November | Decatur High School Renovation |  | HD Supply
MBG-11-M02 | payable | 2025-11-15 | 2025-11-30 | 273850.47 |  | 5000 | 0 | 0 | pending | Construction materials — November | Decatur High School Renovation |  | Ferguson Enterprises
MBG-11-M03 | payable | 2025-11-15 | 2025-11-30 | 290255.33 |  | 5000 | 0 | 0 | pending | Construction materials — November | Decatur High School Renovation |  | Graybar Electric
MBG-11-M04 | payable | 2025-11-15 | 2025-11-30 | 315310.04 |  | 5000 | 0 | 0 | pending | Construction materials — November | Decatur High School Renovation |  | US LBM Holdings
MBG-12-M01 | payable | 2025-12-15 | 2025-12-31 | 251648.76 |  | 5000 | 0 | 0 | pending | Construction materials — December | Hapeville Distribution Center |  | HD Supply
MBG-12-M02 | payable | 2025-12-15 | 2025-12-31 | 336617.58 |  | 5000 | 0 | 0 | pending | Construction materials — December | Hapeville Distribution Center |  | Ferguson Enterprises
MBG-12-M03 | payable | 2025-12-15 | 2025-12-31 | 240213.48 |  | 5000 | 0 | 0 | pending | Construction materials — December | Hapeville Distribution Center |  | Graybar Electric
MBG-12-M04 | payable | 2025-12-15 | 2025-12-31 | 338186.83 |  | 5000 | 0 | 0 | pending | Construction materials — December | Hapeville Distribution Center |  | US LBM Holdings

## Journal Entries
entry_number | entry_date | description | account_number | debit | credit | line_description | status
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 1000 | 6930000.00 |  | Cash - Operating | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 1040 | 900000.00 |  | Prepaid insurance & bonding | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 1050 | 350000.00 |  | Prepaid expenses | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 1100 | 4200000.00 |  | Construction equipment at cost | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 1110 | 1600000.00 |  | Vehicles at cost | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 1120 | 280000.00 |  | Office equipment & furniture | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 1130 |  | 1800000.00 | Accumulated depreciation | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 2020 |  | 600000.00 | Billings in excess of costs | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 2030 |  | 1200000.00 | Accrued payroll | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 2040 |  | 450000.00 | Accrued expenses | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 2100 |  | 2000000.00 | Construction line of credit | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 2110 |  | 1400000.00 | Equipment notes payable | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 3000 |  | 2000000.00 | Members capital | posted
MBG-OB-001 | 2025-01-01 | Opening Balances — Meridian Builders Group | 3010 |  | 4810000.00 | Retained earnings — plug | posted
MBG-PAY-01 | 2025-01-31 | Payroll accrual — January 2025 | 5100 | 388983.05 |  | Field labor January | posted
MBG-PAY-01 | 2025-01-31 | Payroll accrual — January 2025 | 5110 | 172881.36 |  | Supervision labor January | posted
MBG-PAY-01 | 2025-01-31 | Payroll accrual — January 2025 | 5120 | 86440.68 |  | Field payroll taxes January | posted
MBG-PAY-01 | 2025-01-31 | Payroll accrual — January 2025 | 6000 | 100000.00 |  | Officer salaries January | posted
MBG-PAY-01 | 2025-01-31 | Payroll accrual — January 2025 | 6010 | 75000.00 |  | Office staff January | posted
MBG-PAY-01 | 2025-01-31 | Payroll accrual — January 2025 | 6020 | 35000.00 |  | G&A payroll taxes January | posted
MBG-PAY-01 | 2025-01-31 | Payroll accrual — January 2025 | 2030 |  | 858305.09 | Accrued payroll January | posted
MBG-PDIS-01 | 2025-01-31 | Payroll disbursement — January 2025 | 2030 | 858305.09 |  | Clear accrued payroll January | posted
MBG-PDIS-01 | 2025-01-31 | Payroll disbursement — January 2025 | 1000 |  | 858305.09 | Cash - payroll January | posted
MBG-EQ-01 | 2025-01-31 | Equipment costs — January 2025 | 5200 | 144067.80 |  | Equipment rental January | posted
MBG-EQ-01 | 2025-01-31 | Equipment costs — January 2025 | 5210 | 108050.85 |  | Equipment fuel & maintenance January | posted
MBG-EQ-01 | 2025-01-31 | Equipment costs — January 2025 | 1000 |  | 252118.65 | Cash - equipment costs January | posted
MBG-OH-01 | 2025-01-31 | Overhead expenses — January 2025 | 6030 | 30000.00 |  | Office rent January | posted
MBG-OH-01 | 2025-01-31 | Overhead expenses — January 2025 | 6040 | 150000.00 |  | Insurance & bonding January | posted
MBG-OH-01 | 2025-01-31 | Overhead expenses — January 2025 | 6050 | 40000.00 |  | Professional services January | posted
MBG-OH-01 | 2025-01-31 | Overhead expenses — January 2025 | 6060 | 20000.00 |  | IT & software January | posted
MBG-OH-01 | 2025-01-31 | Overhead expenses — January 2025 | 6070 | 15000.00 |  | Marketing January | posted
MBG-OH-01 | 2025-01-31 | Overhead expenses — January 2025 | 6080 | 15000.00 |  | Travel & entertainment January | posted
MBG-OH-01 | 2025-01-31 | Overhead expenses — January 2025 | 6090 | 20000.00 |  | Utilities & telephone January | posted
MBG-OH-01 | 2025-01-31 | Overhead expenses — January 2025 | 1000 |  | 290000.00 | Cash - overhead January | posted
MBG-INT-01 | 2025-01-31 | Interest expense — January 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes January | posted
MBG-INT-01 | 2025-01-31 | Interest expense — January 2025 | 1000 |  | 50000.00 | Cash - interest January | posted
MBG-PAY-02 | 2025-02-28 | Payroll accrual — February 2025 | 5100 | 388983.05 |  | Field labor February | posted
MBG-PAY-02 | 2025-02-28 | Payroll accrual — February 2025 | 5110 | 172881.36 |  | Supervision labor February | posted
MBG-PAY-02 | 2025-02-28 | Payroll accrual — February 2025 | 5120 | 86440.68 |  | Field payroll taxes February | posted
MBG-PAY-02 | 2025-02-28 | Payroll accrual — February 2025 | 6000 | 100000.00 |  | Officer salaries February | posted
MBG-PAY-02 | 2025-02-28 | Payroll accrual — February 2025 | 6010 | 75000.00 |  | Office staff February | posted
MBG-PAY-02 | 2025-02-28 | Payroll accrual — February 2025 | 6020 | 35000.00 |  | G&A payroll taxes February | posted
MBG-PAY-02 | 2025-02-28 | Payroll accrual — February 2025 | 2030 |  | 858305.09 | Accrued payroll February | posted
MBG-PDIS-02 | 2025-02-28 | Payroll disbursement — February 2025 | 2030 | 858305.09 |  | Clear accrued payroll February | posted
MBG-PDIS-02 | 2025-02-28 | Payroll disbursement — February 2025 | 1000 |  | 858305.09 | Cash - payroll February | posted
MBG-EQ-02 | 2025-02-28 | Equipment costs — February 2025 | 5200 | 144067.80 |  | Equipment rental February | posted
MBG-EQ-02 | 2025-02-28 | Equipment costs — February 2025 | 5210 | 108050.85 |  | Equipment fuel & maintenance February | posted
MBG-EQ-02 | 2025-02-28 | Equipment costs — February 2025 | 1000 |  | 252118.65 | Cash - equipment costs February | posted
MBG-OH-02 | 2025-02-28 | Overhead expenses — February 2025 | 6030 | 30000.00 |  | Office rent February | posted
MBG-OH-02 | 2025-02-28 | Overhead expenses — February 2025 | 6040 | 150000.00 |  | Insurance & bonding February | posted
MBG-OH-02 | 2025-02-28 | Overhead expenses — February 2025 | 6050 | 40000.00 |  | Professional services February | posted
MBG-OH-02 | 2025-02-28 | Overhead expenses — February 2025 | 6060 | 20000.00 |  | IT & software February | posted
MBG-OH-02 | 2025-02-28 | Overhead expenses — February 2025 | 6070 | 15000.00 |  | Marketing February | posted
MBG-OH-02 | 2025-02-28 | Overhead expenses — February 2025 | 6080 | 15000.00 |  | Travel & entertainment February | posted
MBG-OH-02 | 2025-02-28 | Overhead expenses — February 2025 | 6090 | 20000.00 |  | Utilities & telephone February | posted
MBG-OH-02 | 2025-02-28 | Overhead expenses — February 2025 | 1000 |  | 290000.00 | Cash - overhead February | posted
MBG-INT-02 | 2025-02-28 | Interest expense — February 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes February | posted
MBG-INT-02 | 2025-02-28 | Interest expense — February 2025 | 1000 |  | 50000.00 | Cash - interest February | posted
MBG-PAY-03 | 2025-03-31 | Payroll accrual — March 2025 | 5100 | 434745.76 |  | Field labor March | posted
MBG-PAY-03 | 2025-03-31 | Payroll accrual — March 2025 | 5110 | 193220.34 |  | Supervision labor March | posted
MBG-PAY-03 | 2025-03-31 | Payroll accrual — March 2025 | 5120 | 96610.17 |  | Field payroll taxes March | posted
MBG-PAY-03 | 2025-03-31 | Payroll accrual — March 2025 | 6000 | 100000.00 |  | Officer salaries March | posted
MBG-PAY-03 | 2025-03-31 | Payroll accrual — March 2025 | 6010 | 75000.00 |  | Office staff March | posted
MBG-PAY-03 | 2025-03-31 | Payroll accrual — March 2025 | 6020 | 35000.00 |  | G&A payroll taxes March | posted
MBG-PAY-03 | 2025-03-31 | Payroll accrual — March 2025 | 2030 |  | 934576.27 | Accrued payroll March | posted
MBG-PDIS-03 | 2025-03-31 | Payroll disbursement — March 2025 | 2030 | 934576.27 |  | Clear accrued payroll March | posted
MBG-PDIS-03 | 2025-03-31 | Payroll disbursement — March 2025 | 1000 |  | 934576.27 | Cash - payroll March | posted
MBG-EQ-03 | 2025-03-31 | Equipment costs — March 2025 | 5200 | 161016.95 |  | Equipment rental March | posted
MBG-EQ-03 | 2025-03-31 | Equipment costs — March 2025 | 5210 | 120762.71 |  | Equipment fuel & maintenance March | posted
MBG-EQ-03 | 2025-03-31 | Equipment costs — March 2025 | 1000 |  | 281779.66 | Cash - equipment costs March | posted
MBG-OH-03 | 2025-03-31 | Overhead expenses — March 2025 | 6030 | 30000.00 |  | Office rent March | posted
MBG-OH-03 | 2025-03-31 | Overhead expenses — March 2025 | 6040 | 150000.00 |  | Insurance & bonding March | posted
MBG-OH-03 | 2025-03-31 | Overhead expenses — March 2025 | 6050 | 40000.00 |  | Professional services March | posted
MBG-OH-03 | 2025-03-31 | Overhead expenses — March 2025 | 6060 | 20000.00 |  | IT & software March | posted
MBG-OH-03 | 2025-03-31 | Overhead expenses — March 2025 | 6070 | 15000.00 |  | Marketing March | posted
MBG-OH-03 | 2025-03-31 | Overhead expenses — March 2025 | 6080 | 15000.00 |  | Travel & entertainment March | posted
MBG-OH-03 | 2025-03-31 | Overhead expenses — March 2025 | 6090 | 20000.00 |  | Utilities & telephone March | posted
MBG-OH-03 | 2025-03-31 | Overhead expenses — March 2025 | 1000 |  | 290000.00 | Cash - overhead March | posted
MBG-INT-03 | 2025-03-31 | Interest expense — March 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes March | posted
MBG-INT-03 | 2025-03-31 | Interest expense — March 2025 | 1000 |  | 50000.00 | Cash - interest March | posted
MBG-DEP-Q1 | 2025-03-31 | Depreciation — Q1 2025 | 6100 | 225000.00 |  | Depreciation Q1 | posted
MBG-DEP-Q1 | 2025-03-31 | Depreciation — Q1 2025 | 1130 |  | 225000.00 | Accumulated depreciation Q1 | posted
MBG-PAY-04 | 2025-04-30 | Payroll accrual — April 2025 | 5100 | 457627.12 |  | Field labor April | posted
MBG-PAY-04 | 2025-04-30 | Payroll accrual — April 2025 | 5110 | 203389.83 |  | Supervision labor April | posted
MBG-PAY-04 | 2025-04-30 | Payroll accrual — April 2025 | 5120 | 101694.92 |  | Field payroll taxes April | posted
MBG-PAY-04 | 2025-04-30 | Payroll accrual — April 2025 | 6000 | 100000.00 |  | Officer salaries April | posted
MBG-PAY-04 | 2025-04-30 | Payroll accrual — April 2025 | 6010 | 75000.00 |  | Office staff April | posted
MBG-PAY-04 | 2025-04-30 | Payroll accrual — April 2025 | 6020 | 35000.00 |  | G&A payroll taxes April | posted
MBG-PAY-04 | 2025-04-30 | Payroll accrual — April 2025 | 2030 |  | 972711.87 | Accrued payroll April | posted
MBG-PDIS-04 | 2025-04-30 | Payroll disbursement — April 2025 | 2030 | 972711.87 |  | Clear accrued payroll April | posted
MBG-PDIS-04 | 2025-04-30 | Payroll disbursement — April 2025 | 1000 |  | 972711.87 | Cash - payroll April | posted
MBG-EQ-04 | 2025-04-30 | Equipment costs — April 2025 | 5200 | 169491.53 |  | Equipment rental April | posted
MBG-EQ-04 | 2025-04-30 | Equipment costs — April 2025 | 5210 | 127118.64 |  | Equipment fuel & maintenance April | posted
MBG-EQ-04 | 2025-04-30 | Equipment costs — April 2025 | 1000 |  | 296610.17 | Cash - equipment costs April | posted
MBG-OH-04 | 2025-04-30 | Overhead expenses — April 2025 | 6030 | 30000.00 |  | Office rent April | posted
MBG-OH-04 | 2025-04-30 | Overhead expenses — April 2025 | 6040 | 150000.00 |  | Insurance & bonding April | posted
MBG-OH-04 | 2025-04-30 | Overhead expenses — April 2025 | 6050 | 40000.00 |  | Professional services April | posted
MBG-OH-04 | 2025-04-30 | Overhead expenses — April 2025 | 6060 | 20000.00 |  | IT & software April | posted
MBG-OH-04 | 2025-04-30 | Overhead expenses — April 2025 | 6070 | 15000.00 |  | Marketing April | posted
MBG-OH-04 | 2025-04-30 | Overhead expenses — April 2025 | 6080 | 15000.00 |  | Travel & entertainment April | posted
MBG-OH-04 | 2025-04-30 | Overhead expenses — April 2025 | 6090 | 20000.00 |  | Utilities & telephone April | posted
MBG-OH-04 | 2025-04-30 | Overhead expenses — April 2025 | 1000 |  | 290000.00 | Cash - overhead April | posted
MBG-INT-04 | 2025-04-30 | Interest expense — April 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes April | posted
MBG-INT-04 | 2025-04-30 | Interest expense — April 2025 | 1000 |  | 50000.00 | Cash - interest April | posted
MBG-PAY-05 | 2025-05-31 | Payroll accrual — May 2025 | 5100 | 503389.83 |  | Field labor May | posted
MBG-PAY-05 | 2025-05-31 | Payroll accrual — May 2025 | 5110 | 223728.81 |  | Supervision labor May | posted
MBG-PAY-05 | 2025-05-31 | Payroll accrual — May 2025 | 5120 | 111864.41 |  | Field payroll taxes May | posted
MBG-PAY-05 | 2025-05-31 | Payroll accrual — May 2025 | 6000 | 100000.00 |  | Officer salaries May | posted
MBG-PAY-05 | 2025-05-31 | Payroll accrual — May 2025 | 6010 | 75000.00 |  | Office staff May | posted
MBG-PAY-05 | 2025-05-31 | Payroll accrual — May 2025 | 6020 | 35000.00 |  | G&A payroll taxes May | posted
MBG-PAY-05 | 2025-05-31 | Payroll accrual — May 2025 | 2030 |  | 1048983.05 | Accrued payroll May | posted
MBG-PDIS-05 | 2025-05-31 | Payroll disbursement — May 2025 | 2030 | 1048983.05 |  | Clear accrued payroll May | posted
MBG-PDIS-05 | 2025-05-31 | Payroll disbursement — May 2025 | 1000 |  | 1048983.05 | Cash - payroll May | posted
MBG-EQ-05 | 2025-05-31 | Equipment costs — May 2025 | 5200 | 186440.68 |  | Equipment rental May | posted
MBG-EQ-05 | 2025-05-31 | Equipment costs — May 2025 | 5210 | 139830.51 |  | Equipment fuel & maintenance May | posted
MBG-EQ-05 | 2025-05-31 | Equipment costs — May 2025 | 1000 |  | 326271.19 | Cash - equipment costs May | posted
MBG-OH-05 | 2025-05-31 | Overhead expenses — May 2025 | 6030 | 30000.00 |  | Office rent May | posted
MBG-OH-05 | 2025-05-31 | Overhead expenses — May 2025 | 6040 | 150000.00 |  | Insurance & bonding May | posted
MBG-OH-05 | 2025-05-31 | Overhead expenses — May 2025 | 6050 | 40000.00 |  | Professional services May | posted
MBG-OH-05 | 2025-05-31 | Overhead expenses — May 2025 | 6060 | 20000.00 |  | IT & software May | posted
MBG-OH-05 | 2025-05-31 | Overhead expenses — May 2025 | 6070 | 15000.00 |  | Marketing May | posted
MBG-OH-05 | 2025-05-31 | Overhead expenses — May 2025 | 6080 | 15000.00 |  | Travel & entertainment May | posted
MBG-OH-05 | 2025-05-31 | Overhead expenses — May 2025 | 6090 | 20000.00 |  | Utilities & telephone May | posted
MBG-OH-05 | 2025-05-31 | Overhead expenses — May 2025 | 1000 |  | 290000.00 | Cash - overhead May | posted
MBG-INT-05 | 2025-05-31 | Interest expense — May 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes May | posted
MBG-INT-05 | 2025-05-31 | Interest expense — May 2025 | 1000 |  | 50000.00 | Cash - interest May | posted
MBG-PAY-06 | 2025-06-30 | Payroll accrual — June 2025 | 5100 | 526271.19 |  | Field labor June | posted
MBG-PAY-06 | 2025-06-30 | Payroll accrual — June 2025 | 5110 | 233898.31 |  | Supervision labor June | posted
MBG-PAY-06 | 2025-06-30 | Payroll accrual — June 2025 | 5120 | 116949.15 |  | Field payroll taxes June | posted
MBG-PAY-06 | 2025-06-30 | Payroll accrual — June 2025 | 6000 | 100000.00 |  | Officer salaries June | posted
MBG-PAY-06 | 2025-06-30 | Payroll accrual — June 2025 | 6010 | 75000.00 |  | Office staff June | posted
MBG-PAY-06 | 2025-06-30 | Payroll accrual — June 2025 | 6020 | 35000.00 |  | G&A payroll taxes June | posted
MBG-PAY-06 | 2025-06-30 | Payroll accrual — June 2025 | 2030 |  | 1087118.65 | Accrued payroll June | posted
MBG-PDIS-06 | 2025-06-30 | Payroll disbursement — June 2025 | 2030 | 1087118.65 |  | Clear accrued payroll June | posted
MBG-PDIS-06 | 2025-06-30 | Payroll disbursement — June 2025 | 1000 |  | 1087118.65 | Cash - payroll June | posted
MBG-EQ-06 | 2025-06-30 | Equipment costs — June 2025 | 5200 | 194915.25 |  | Equipment rental June | posted
MBG-EQ-06 | 2025-06-30 | Equipment costs — June 2025 | 5210 | 146186.44 |  | Equipment fuel & maintenance June | posted
MBG-EQ-06 | 2025-06-30 | Equipment costs — June 2025 | 1000 |  | 341101.69 | Cash - equipment costs June | posted
MBG-OH-06 | 2025-06-30 | Overhead expenses — June 2025 | 6030 | 30000.00 |  | Office rent June | posted
MBG-OH-06 | 2025-06-30 | Overhead expenses — June 2025 | 6040 | 150000.00 |  | Insurance & bonding June | posted
MBG-OH-06 | 2025-06-30 | Overhead expenses — June 2025 | 6050 | 40000.00 |  | Professional services June | posted
MBG-OH-06 | 2025-06-30 | Overhead expenses — June 2025 | 6060 | 20000.00 |  | IT & software June | posted
MBG-OH-06 | 2025-06-30 | Overhead expenses — June 2025 | 6070 | 15000.00 |  | Marketing June | posted
MBG-OH-06 | 2025-06-30 | Overhead expenses — June 2025 | 6080 | 15000.00 |  | Travel & entertainment June | posted
MBG-OH-06 | 2025-06-30 | Overhead expenses — June 2025 | 6090 | 20000.00 |  | Utilities & telephone June | posted
MBG-OH-06 | 2025-06-30 | Overhead expenses — June 2025 | 1000 |  | 290000.00 | Cash - overhead June | posted
MBG-INT-06 | 2025-06-30 | Interest expense — June 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes June | posted
MBG-INT-06 | 2025-06-30 | Interest expense — June 2025 | 1000 |  | 50000.00 | Cash - interest June | posted
MBG-DEP-Q2 | 2025-06-30 | Depreciation — Q2 2025 | 6100 | 225000.00 |  | Depreciation Q2 | posted
MBG-DEP-Q2 | 2025-06-30 | Depreciation — Q2 2025 | 1130 |  | 225000.00 | Accumulated depreciation Q2 | posted
MBG-PAY-07 | 2025-07-31 | Payroll accrual — July 2025 | 5100 | 526271.19 |  | Field labor July | posted
MBG-PAY-07 | 2025-07-31 | Payroll accrual — July 2025 | 5110 | 233898.31 |  | Supervision labor July | posted
MBG-PAY-07 | 2025-07-31 | Payroll accrual — July 2025 | 5120 | 116949.15 |  | Field payroll taxes July | posted
MBG-PAY-07 | 2025-07-31 | Payroll accrual — July 2025 | 6000 | 100000.00 |  | Officer salaries July | posted
MBG-PAY-07 | 2025-07-31 | Payroll accrual — July 2025 | 6010 | 75000.00 |  | Office staff July | posted
MBG-PAY-07 | 2025-07-31 | Payroll accrual — July 2025 | 6020 | 35000.00 |  | G&A payroll taxes July | posted
MBG-PAY-07 | 2025-07-31 | Payroll accrual — July 2025 | 2030 |  | 1087118.65 | Accrued payroll July | posted
MBG-PDIS-07 | 2025-07-31 | Payroll disbursement — July 2025 | 2030 | 1087118.65 |  | Clear accrued payroll July | posted
MBG-PDIS-07 | 2025-07-31 | Payroll disbursement — July 2025 | 1000 |  | 1087118.65 | Cash - payroll July | posted
MBG-EQ-07 | 2025-07-31 | Equipment costs — July 2025 | 5200 | 194915.25 |  | Equipment rental July | posted
MBG-EQ-07 | 2025-07-31 | Equipment costs — July 2025 | 5210 | 146186.44 |  | Equipment fuel & maintenance July | posted
MBG-EQ-07 | 2025-07-31 | Equipment costs — July 2025 | 1000 |  | 341101.69 | Cash - equipment costs July | posted
MBG-OH-07 | 2025-07-31 | Overhead expenses — July 2025 | 6030 | 30000.00 |  | Office rent July | posted
MBG-OH-07 | 2025-07-31 | Overhead expenses — July 2025 | 6040 | 150000.00 |  | Insurance & bonding July | posted
MBG-OH-07 | 2025-07-31 | Overhead expenses — July 2025 | 6050 | 40000.00 |  | Professional services July | posted
MBG-OH-07 | 2025-07-31 | Overhead expenses — July 2025 | 6060 | 20000.00 |  | IT & software July | posted
MBG-OH-07 | 2025-07-31 | Overhead expenses — July 2025 | 6070 | 15000.00 |  | Marketing July | posted
MBG-OH-07 | 2025-07-31 | Overhead expenses — July 2025 | 6080 | 15000.00 |  | Travel & entertainment July | posted
MBG-OH-07 | 2025-07-31 | Overhead expenses — July 2025 | 6090 | 20000.00 |  | Utilities & telephone July | posted
MBG-OH-07 | 2025-07-31 | Overhead expenses — July 2025 | 1000 |  | 290000.00 | Cash - overhead July | posted
MBG-INT-07 | 2025-07-31 | Interest expense — July 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes July | posted
MBG-INT-07 | 2025-07-31 | Interest expense — July 2025 | 1000 |  | 50000.00 | Cash - interest July | posted
MBG-PAY-08 | 2025-08-31 | Payroll accrual — August 2025 | 5100 | 503389.83 |  | Field labor August | posted
MBG-PAY-08 | 2025-08-31 | Payroll accrual — August 2025 | 5110 | 223728.81 |  | Supervision labor August | posted
MBG-PAY-08 | 2025-08-31 | Payroll accrual — August 2025 | 5120 | 111864.41 |  | Field payroll taxes August | posted
MBG-PAY-08 | 2025-08-31 | Payroll accrual — August 2025 | 6000 | 100000.00 |  | Officer salaries August | posted
MBG-PAY-08 | 2025-08-31 | Payroll accrual — August 2025 | 6010 | 75000.00 |  | Office staff August | posted
MBG-PAY-08 | 2025-08-31 | Payroll accrual — August 2025 | 6020 | 35000.00 |  | G&A payroll taxes August | posted
MBG-PAY-08 | 2025-08-31 | Payroll accrual — August 2025 | 2030 |  | 1048983.05 | Accrued payroll August | posted
MBG-PDIS-08 | 2025-08-31 | Payroll disbursement — August 2025 | 2030 | 1048983.05 |  | Clear accrued payroll August | posted
MBG-PDIS-08 | 2025-08-31 | Payroll disbursement — August 2025 | 1000 |  | 1048983.05 | Cash - payroll August | posted
MBG-EQ-08 | 2025-08-31 | Equipment costs — August 2025 | 5200 | 186440.68 |  | Equipment rental August | posted
MBG-EQ-08 | 2025-08-31 | Equipment costs — August 2025 | 5210 | 139830.51 |  | Equipment fuel & maintenance August | posted
MBG-EQ-08 | 2025-08-31 | Equipment costs — August 2025 | 1000 |  | 326271.19 | Cash - equipment costs August | posted
MBG-OH-08 | 2025-08-31 | Overhead expenses — August 2025 | 6030 | 30000.00 |  | Office rent August | posted
MBG-OH-08 | 2025-08-31 | Overhead expenses — August 2025 | 6040 | 150000.00 |  | Insurance & bonding August | posted
MBG-OH-08 | 2025-08-31 | Overhead expenses — August 2025 | 6050 | 40000.00 |  | Professional services August | posted
MBG-OH-08 | 2025-08-31 | Overhead expenses — August 2025 | 6060 | 20000.00 |  | IT & software August | posted
MBG-OH-08 | 2025-08-31 | Overhead expenses — August 2025 | 6070 | 15000.00 |  | Marketing August | posted
MBG-OH-08 | 2025-08-31 | Overhead expenses — August 2025 | 6080 | 15000.00 |  | Travel & entertainment August | posted
MBG-OH-08 | 2025-08-31 | Overhead expenses — August 2025 | 6090 | 20000.00 |  | Utilities & telephone August | posted
MBG-OH-08 | 2025-08-31 | Overhead expenses — August 2025 | 1000 |  | 290000.00 | Cash - overhead August | posted
MBG-INT-08 | 2025-08-31 | Interest expense — August 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes August | posted
MBG-INT-08 | 2025-08-31 | Interest expense — August 2025 | 1000 |  | 50000.00 | Cash - interest August | posted
MBG-PAY-09 | 2025-09-30 | Payroll accrual — September 2025 | 5100 | 457627.12 |  | Field labor September | posted
MBG-PAY-09 | 2025-09-30 | Payroll accrual — September 2025 | 5110 | 203389.83 |  | Supervision labor September | posted
MBG-PAY-09 | 2025-09-30 | Payroll accrual — September 2025 | 5120 | 101694.92 |  | Field payroll taxes September | posted
MBG-PAY-09 | 2025-09-30 | Payroll accrual — September 2025 | 6000 | 100000.00 |  | Officer salaries September | posted
MBG-PAY-09 | 2025-09-30 | Payroll accrual — September 2025 | 6010 | 75000.00 |  | Office staff September | posted
MBG-PAY-09 | 2025-09-30 | Payroll accrual — September 2025 | 6020 | 35000.00 |  | G&A payroll taxes September | posted
MBG-PAY-09 | 2025-09-30 | Payroll accrual — September 2025 | 2030 |  | 972711.87 | Accrued payroll September | posted
MBG-PDIS-09 | 2025-09-30 | Payroll disbursement — September 2025 | 2030 | 972711.87 |  | Clear accrued payroll September | posted
MBG-PDIS-09 | 2025-09-30 | Payroll disbursement — September 2025 | 1000 |  | 972711.87 | Cash - payroll September | posted
MBG-EQ-09 | 2025-09-30 | Equipment costs — September 2025 | 5200 | 169491.53 |  | Equipment rental September | posted
MBG-EQ-09 | 2025-09-30 | Equipment costs — September 2025 | 5210 | 127118.64 |  | Equipment fuel & maintenance September | posted
MBG-EQ-09 | 2025-09-30 | Equipment costs — September 2025 | 1000 |  | 296610.17 | Cash - equipment costs September | posted
MBG-OH-09 | 2025-09-30 | Overhead expenses — September 2025 | 6030 | 30000.00 |  | Office rent September | posted
MBG-OH-09 | 2025-09-30 | Overhead expenses — September 2025 | 6040 | 150000.00 |  | Insurance & bonding September | posted
MBG-OH-09 | 2025-09-30 | Overhead expenses — September 2025 | 6050 | 40000.00 |  | Professional services September | posted
MBG-OH-09 | 2025-09-30 | Overhead expenses — September 2025 | 6060 | 20000.00 |  | IT & software September | posted
MBG-OH-09 | 2025-09-30 | Overhead expenses — September 2025 | 6070 | 15000.00 |  | Marketing September | posted
MBG-OH-09 | 2025-09-30 | Overhead expenses — September 2025 | 6080 | 15000.00 |  | Travel & entertainment September | posted
MBG-OH-09 | 2025-09-30 | Overhead expenses — September 2025 | 6090 | 20000.00 |  | Utilities & telephone September | posted
MBG-OH-09 | 2025-09-30 | Overhead expenses — September 2025 | 1000 |  | 290000.00 | Cash - overhead September | posted
MBG-INT-09 | 2025-09-30 | Interest expense — September 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes September | posted
MBG-INT-09 | 2025-09-30 | Interest expense — September 2025 | 1000 |  | 50000.00 | Cash - interest September | posted
MBG-DEP-Q3 | 2025-09-30 | Depreciation — Q3 2025 | 6100 | 225000.00 |  | Depreciation Q3 | posted
MBG-DEP-Q3 | 2025-09-30 | Depreciation — Q3 2025 | 1130 |  | 225000.00 | Accumulated depreciation Q3 | posted
MBG-PAY-10 | 2025-10-31 | Payroll accrual — October 2025 | 5100 | 434745.76 |  | Field labor October | posted
MBG-PAY-10 | 2025-10-31 | Payroll accrual — October 2025 | 5110 | 193220.34 |  | Supervision labor October | posted
MBG-PAY-10 | 2025-10-31 | Payroll accrual — October 2025 | 5120 | 96610.17 |  | Field payroll taxes October | posted
MBG-PAY-10 | 2025-10-31 | Payroll accrual — October 2025 | 6000 | 100000.00 |  | Officer salaries October | posted
MBG-PAY-10 | 2025-10-31 | Payroll accrual — October 2025 | 6010 | 75000.00 |  | Office staff October | posted
MBG-PAY-10 | 2025-10-31 | Payroll accrual — October 2025 | 6020 | 35000.00 |  | G&A payroll taxes October | posted
MBG-PAY-10 | 2025-10-31 | Payroll accrual — October 2025 | 2030 |  | 934576.27 | Accrued payroll October | posted
MBG-PDIS-10 | 2025-10-31 | Payroll disbursement — October 2025 | 2030 | 934576.27 |  | Clear accrued payroll October | posted
MBG-PDIS-10 | 2025-10-31 | Payroll disbursement — October 2025 | 1000 |  | 934576.27 | Cash - payroll October | posted
MBG-EQ-10 | 2025-10-31 | Equipment costs — October 2025 | 5200 | 161016.95 |  | Equipment rental October | posted
MBG-EQ-10 | 2025-10-31 | Equipment costs — October 2025 | 5210 | 120762.71 |  | Equipment fuel & maintenance October | posted
MBG-EQ-10 | 2025-10-31 | Equipment costs — October 2025 | 1000 |  | 281779.66 | Cash - equipment costs October | posted
MBG-OH-10 | 2025-10-31 | Overhead expenses — October 2025 | 6030 | 30000.00 |  | Office rent October | posted
MBG-OH-10 | 2025-10-31 | Overhead expenses — October 2025 | 6040 | 150000.00 |  | Insurance & bonding October | posted
MBG-OH-10 | 2025-10-31 | Overhead expenses — October 2025 | 6050 | 40000.00 |  | Professional services October | posted
MBG-OH-10 | 2025-10-31 | Overhead expenses — October 2025 | 6060 | 20000.00 |  | IT & software October | posted
MBG-OH-10 | 2025-10-31 | Overhead expenses — October 2025 | 6070 | 15000.00 |  | Marketing October | posted
MBG-OH-10 | 2025-10-31 | Overhead expenses — October 2025 | 6080 | 15000.00 |  | Travel & entertainment October | posted
MBG-OH-10 | 2025-10-31 | Overhead expenses — October 2025 | 6090 | 20000.00 |  | Utilities & telephone October | posted
MBG-OH-10 | 2025-10-31 | Overhead expenses — October 2025 | 1000 |  | 290000.00 | Cash - overhead October | posted
MBG-INT-10 | 2025-10-31 | Interest expense — October 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes October | posted
MBG-INT-10 | 2025-10-31 | Interest expense — October 2025 | 1000 |  | 50000.00 | Cash - interest October | posted
MBG-PAY-11 | 2025-11-30 | Payroll accrual — November 2025 | 5100 | 388983.05 |  | Field labor November | posted
MBG-PAY-11 | 2025-11-30 | Payroll accrual — November 2025 | 5110 | 172881.36 |  | Supervision labor November | posted
MBG-PAY-11 | 2025-11-30 | Payroll accrual — November 2025 | 5120 | 86440.68 |  | Field payroll taxes November | posted
MBG-PAY-11 | 2025-11-30 | Payroll accrual — November 2025 | 6000 | 100000.00 |  | Officer salaries November | posted
MBG-PAY-11 | 2025-11-30 | Payroll accrual — November 2025 | 6010 | 75000.00 |  | Office staff November | posted
MBG-PAY-11 | 2025-11-30 | Payroll accrual — November 2025 | 6020 | 35000.00 |  | G&A payroll taxes November | posted
MBG-PAY-11 | 2025-11-30 | Payroll accrual — November 2025 | 2030 |  | 858305.09 | Accrued payroll November | posted
MBG-PDIS-11 | 2025-11-30 | Payroll disbursement — November 2025 | 2030 | 858305.09 |  | Clear accrued payroll November | posted
MBG-PDIS-11 | 2025-11-30 | Payroll disbursement — November 2025 | 1000 |  | 858305.09 | Cash - payroll November | posted
MBG-EQ-11 | 2025-11-30 | Equipment costs — November 2025 | 5200 | 144067.80 |  | Equipment rental November | posted
MBG-EQ-11 | 2025-11-30 | Equipment costs — November 2025 | 5210 | 108050.85 |  | Equipment fuel & maintenance November | posted
MBG-EQ-11 | 2025-11-30 | Equipment costs — November 2025 | 1000 |  | 252118.65 | Cash - equipment costs November | posted
MBG-OH-11 | 2025-11-30 | Overhead expenses — November 2025 | 6030 | 30000.00 |  | Office rent November | posted
MBG-OH-11 | 2025-11-30 | Overhead expenses — November 2025 | 6040 | 150000.00 |  | Insurance & bonding November | posted
MBG-OH-11 | 2025-11-30 | Overhead expenses — November 2025 | 6050 | 40000.00 |  | Professional services November | posted
MBG-OH-11 | 2025-11-30 | Overhead expenses — November 2025 | 6060 | 20000.00 |  | IT & software November | posted
MBG-OH-11 | 2025-11-30 | Overhead expenses — November 2025 | 6070 | 15000.00 |  | Marketing November | posted
MBG-OH-11 | 2025-11-30 | Overhead expenses — November 2025 | 6080 | 15000.00 |  | Travel & entertainment November | posted
MBG-OH-11 | 2025-11-30 | Overhead expenses — November 2025 | 6090 | 20000.00 |  | Utilities & telephone November | posted
MBG-OH-11 | 2025-11-30 | Overhead expenses — November 2025 | 1000 |  | 290000.00 | Cash - overhead November | posted
MBG-INT-11 | 2025-11-30 | Interest expense — November 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes November | posted
MBG-INT-11 | 2025-11-30 | Interest expense — November 2025 | 1000 |  | 50000.00 | Cash - interest November | posted
MBG-PAY-12 | 2025-12-31 | Payroll accrual — December 2025 | 5100 | 388983.05 |  | Field labor December | posted
MBG-PAY-12 | 2025-12-31 | Payroll accrual — December 2025 | 5110 | 172881.34 |  | Supervision labor December | posted
MBG-PAY-12 | 2025-12-31 | Payroll accrual — December 2025 | 5120 | 86440.66 |  | Field payroll taxes December | posted
MBG-PAY-12 | 2025-12-31 | Payroll accrual — December 2025 | 6000 | 100000.00 |  | Officer salaries December | posted
MBG-PAY-12 | 2025-12-31 | Payroll accrual — December 2025 | 6010 | 75000.00 |  | Office staff December | posted
MBG-PAY-12 | 2025-12-31 | Payroll accrual — December 2025 | 6020 | 35000.00 |  | G&A payroll taxes December | posted
MBG-PAY-12 | 2025-12-31 | Payroll accrual — December 2025 | 2030 |  | 858305.05 | Accrued payroll December | posted
MBG-PDIS-12 | 2025-12-31 | Payroll disbursement — December 2025 | 2030 | 858305.05 |  | Clear accrued payroll December | posted
MBG-PDIS-12 | 2025-12-31 | Payroll disbursement — December 2025 | 1000 |  | 858305.05 | Cash - payroll December | posted
MBG-EQ-12 | 2025-12-31 | Equipment costs — December 2025 | 5200 | 144067.78 |  | Equipment rental December | posted
MBG-EQ-12 | 2025-12-31 | Equipment costs — December 2025 | 5210 | 108050.85 |  | Equipment fuel & maintenance December | posted
MBG-EQ-12 | 2025-12-31 | Equipment costs — December 2025 | 1000 |  | 252118.63 | Cash - equipment costs December | posted
MBG-OH-12 | 2025-12-31 | Overhead expenses — December 2025 | 6030 | 30000.00 |  | Office rent December | posted
MBG-OH-12 | 2025-12-31 | Overhead expenses — December 2025 | 6040 | 150000.00 |  | Insurance & bonding December | posted
MBG-OH-12 | 2025-12-31 | Overhead expenses — December 2025 | 6050 | 40000.00 |  | Professional services December | posted
MBG-OH-12 | 2025-12-31 | Overhead expenses — December 2025 | 6060 | 20000.00 |  | IT & software December | posted
MBG-OH-12 | 2025-12-31 | Overhead expenses — December 2025 | 6070 | 15000.00 |  | Marketing December | posted
MBG-OH-12 | 2025-12-31 | Overhead expenses — December 2025 | 6080 | 15000.00 |  | Travel & entertainment December | posted
MBG-OH-12 | 2025-12-31 | Overhead expenses — December 2025 | 6090 | 20000.00 |  | Utilities & telephone December | posted
MBG-OH-12 | 2025-12-31 | Overhead expenses — December 2025 | 1000 |  | 290000.00 | Cash - overhead December | posted
MBG-INT-12 | 2025-12-31 | Interest expense — December 2025 | 7000 | 50000.00 |  | Interest on LOC & equipment notes December | posted
MBG-INT-12 | 2025-12-31 | Interest expense — December 2025 | 1000 |  | 50000.00 | Cash - interest December | posted
MBG-DEP-Q4 | 2025-12-31 | Depreciation — Q4 2025 | 6100 | 225000.00 |  | Depreciation Q4 | posted
MBG-DEP-Q4 | 2025-12-31 | Depreciation — Q4 2025 | 1130 |  | 225000.00 | Accumulated depreciation Q4 | posted

## Time Entries
contact_name | project_name | entry_date | hours | description | cost_code | status
Barbara Jimenez | Hapeville Distribution Center | 2025-01-07 | 8 | Quality inspection rounds | 01 45 00 | approved
Wayne Perry | Hapeville Distribution Center | 2025-01-07 | 7 | Material handling and staging | 01 60 00 | approved
Joan Roberts | Hapeville Distribution Center | 2025-01-07 | 8 | Rebar tying and placement | 03 20 00 | approved
Richard Cole | Decatur High School Renovation | 2025-01-07 | 10 | Quality inspection rounds | 01 45 00 | approved
Steven Wilson | Peachtree Office Tower | 2025-01-07 | 10 | Quality inspection rounds | 01 45 00 | approved
Barbara Jimenez | Hapeville Distribution Center | 2025-01-09 | 7 | Coordination with subcontractors | 01 31 00 | approved
Barbara Jimenez | Emory Medical Wing Expansion | 2025-01-10 | 7 | Concrete formwork assembly | 03 10 00 | approved
Joan Roberts | Emory Medical Wing Expansion | 2025-01-10 | 8 | Steel connection bolting | 05 12 00 | approved
Amy Green | Peachtree Office Tower | 2025-01-13 | 6 | Coordination with subcontractors | 01 31 00 | approved
Christine Collins | Peachtree Office Tower | 2025-01-13 | 9 | Material handling and staging | 01 60 00 | approved
Bruce Sullivan | Decatur High School Renovation | 2025-01-14 | 8 | Site layout and surveying | 01 71 00 | approved
Helen Burke | Decatur High School Renovation | 2025-01-14 | 8 | Rebar tying and placement | 03 20 00 | approved
Austin Peterson | Emory Medical Wing Expansion | 2025-01-15 | 8 | Punch list corrections | 01 77 00 | approved
Christine Morton | Decatur High School Renovation | 2025-01-15 | 8 | Concrete placement and finishing | 03 30 00 | approved
Dorothy Torres | Peachtree Office Tower | 2025-01-16 | 10 | Material handling and staging | 01 60 00 | approved
Joan Roberts | Hapeville Distribution Center | 2025-01-17 | 6 | Project documentation and photos | 01 33 00 | approved
Gloria Martinez | Decatur High School Renovation | 2025-01-17 | 7 | Grade checking and compaction testing | 31 20 00 | approved
Christine Morton | Emory Medical Wing Expansion | 2025-01-20 | 8 | Temporary enclosure setup | 01 54 00 | approved
Wayne Perry | Emory Medical Wing Expansion | 2025-01-21 | 9 | Steel connection bolting | 05 12 00 | approved
Steven Wilson | Decatur High School Renovation | 2025-01-21 | 10 | Coordination with subcontractors | 01 31 00 | approved
Joseph Wood | Peachtree Office Tower | 2025-01-22 | 8 | Temporary enclosure setup | 01 54 00 | approved
George Johnson | Peachtree Office Tower | 2025-01-23 | 9 | Punch list corrections | 01 77 00 | approved
Barbara Jimenez | Decatur High School Renovation | 2025-01-24 | 10 | Grade checking and compaction testing | 31 20 00 | approved
Richard Cole | Peachtree Office Tower | 2025-01-24 | 9 | Punch list corrections | 01 77 00 | approved
Eugene Stewart | Decatur High School Renovation | 2025-01-27 | 8 | Project documentation and photos | 01 33 00 | approved
Christine Morton | Decatur High School Renovation | 2025-01-27 | 7 | Concrete formwork assembly | 03 10 00 | approved
George Johnson | Peachtree Office Tower | 2025-01-27 | 6 | Punch list corrections | 01 77 00 | approved
Louis Walker | Hapeville Distribution Center | 2025-01-27 | 6 | Rebar tying and placement | 03 20 00 | approved
Cheryl Ellis | Decatur High School Renovation | 2025-01-28 | 6 | Temporary enclosure setup | 01 54 00 | approved
Wayne Perry | Peachtree Office Tower | 2025-01-28 | 9 | Concrete placement and finishing | 03 30 00 | approved
Barbara Jimenez | Peachtree Office Tower | 2025-01-29 | 10 | Scaffold erection | 01 54 00 | approved
Wayne Perry | Emory Medical Wing Expansion | 2025-01-30 | 9 | Excavation support monitoring | 31 50 00 | approved
Eugene Stewart | Hapeville Distribution Center | 2025-01-30 | 8 | Concrete placement and finishing | 03 30 00 | approved
Dylan Adams | Emory Medical Wing Expansion | 2025-01-31 | 9 | Rebar tying and placement | 03 20 00 | approved
Joan Aguilar | Hapeville Distribution Center | 2025-02-03 | 8 | Scaffold erection | 01 54 00 | approved
Jason White | Peachtree Office Tower | 2025-02-03 | 7 | Site layout and surveying | 01 71 00 | approved
Dorothy Torres | Hapeville Distribution Center | 2025-02-03 | 8 | Steel connection bolting | 05 12 00 | approved
Helen Burke | Peachtree Office Tower | 2025-02-05 | 6 | Material handling and staging | 01 60 00 | approved
Cheryl Ellis | Decatur High School Renovation | 2025-02-06 | 9 | Temporary enclosure setup | 01 54 00 | approved
Joan Roberts | Hapeville Distribution Center | 2025-02-07 | 9 | Site layout and surveying | 01 71 00 | approved
Wayne Perry | Decatur High School Renovation | 2025-02-07 | 8 | Excavation support monitoring | 31 50 00 | approved
Dorothy Torres | Peachtree Office Tower | 2025-02-10 | 8 | Project documentation and photos | 01 33 00 | approved
Austin Peterson | Decatur High School Renovation | 2025-02-10 | 6 | Steel connection bolting | 05 12 00 | approved
Cheryl Ellis | Decatur High School Renovation | 2025-02-11 | 9 | Site layout and surveying | 01 71 00 | approved
Cheryl Ellis | Emory Medical Wing Expansion | 2025-02-12 | 8 | Concrete formwork assembly | 03 10 00 | approved
Barbara Jimenez | Decatur High School Renovation | 2025-02-12 | 9 | Temporary enclosure setup | 01 54 00 | approved
Christine Collins | Emory Medical Wing Expansion | 2025-02-12 | 10 | Punch list corrections | 01 77 00 | approved
Austin Peterson | Emory Medical Wing Expansion | 2025-02-12 | 8 | Material handling and staging | 01 60 00 | approved
Dorothy Torres | Peachtree Office Tower | 2025-02-13 | 8 | Rebar tying and placement | 03 20 00 | approved
Joan Aguilar | Emory Medical Wing Expansion | 2025-02-13 | 8 | Concrete formwork assembly | 03 10 00 | approved
Helen Burke | Decatur High School Renovation | 2025-02-17 | 7 | Punch list corrections | 01 77 00 | approved
Louis Walker | Emory Medical Wing Expansion | 2025-02-17 | 7 | Steel connection bolting | 05 12 00 | approved
Steven Wilson | Peachtree Office Tower | 2025-02-20 | 8 | Excavation support monitoring | 31 50 00 | approved
George Johnson | Decatur High School Renovation | 2025-02-20 | 7 | Concrete formwork assembly | 03 10 00 | approved
Austin Peterson | Hapeville Distribution Center | 2025-02-24 | 9 | Project documentation and photos | 01 33 00 | approved
Marilyn Hill | Decatur High School Renovation | 2025-02-25 | 10 | Quality inspection rounds | 01 45 00 | approved
Austin Peterson | Hapeville Distribution Center | 2025-02-26 | 8 | Punch list corrections | 01 77 00 | approved
Louis Walker | Decatur High School Renovation | 2025-02-26 | 7 | Steel connection bolting | 05 12 00 | approved
Gloria Martinez | Hapeville Distribution Center | 2025-02-26 | 8 | Excavation support monitoring | 31 50 00 | approved
Cheryl Ellis | Decatur High School Renovation | 2025-02-28 | 10 | Rebar tying and placement | 03 20 00 | approved
Eugene Stewart | Hapeville Distribution Center | 2025-03-03 | 8 | Safety barricade installation | 01 56 00 | approved
Helen Burke | Emory Medical Wing Expansion | 2025-03-04 | 10 | Rebar tying and placement | 03 20 00 | approved
Christine Collins | Emory Medical Wing Expansion | 2025-03-06 | 6 | Grade checking and compaction testing | 31 20 00 | approved
Wayne Perry | Decatur High School Renovation | 2025-03-06 | 10 | Concrete formwork assembly | 03 10 00 | approved
Austin Peterson | Emory Medical Wing Expansion | 2025-03-07 | 10 | Coordination with subcontractors | 01 31 00 | approved
Jason White | Emory Medical Wing Expansion | 2025-03-07 | 8 | Rebar tying and placement | 03 20 00 | approved
Barbara Jimenez | Peachtree Office Tower | 2025-03-07 | 7 | Coordination with subcontractors | 01 31 00 | approved
Barbara Jimenez | Peachtree Office Tower | 2025-03-10 | 10 | Safety barricade installation | 01 56 00 | approved
Christine Morton | Emory Medical Wing Expansion | 2025-03-11 | 8 | Punch list corrections | 01 77 00 | approved
Gloria Martinez | Decatur High School Renovation | 2025-03-11 | 10 | Material handling and staging | 01 60 00 | approved
Gloria Martinez | Emory Medical Wing Expansion | 2025-03-12 | 8 | Project documentation and photos | 01 33 00 | approved
Richard Cole | Emory Medical Wing Expansion | 2025-03-13 | 7 | Concrete placement and finishing | 03 30 00 | approved
Marilyn Hill | Peachtree Office Tower | 2025-03-13 | 9 | Coordination with subcontractors | 01 31 00 | approved
Bruce Sullivan | Peachtree Office Tower | 2025-03-14 | 9 | Quality inspection rounds | 01 45 00 | approved
Dorothy Torres | Decatur High School Renovation | 2025-03-17 | 8 | Grade checking and compaction testing | 31 20 00 | approved
Bruce Sullivan | Emory Medical Wing Expansion | 2025-03-18 | 10 | Temporary enclosure setup | 01 54 00 | approved
Eugene Stewart | Peachtree Office Tower | 2025-03-18 | 10 | Punch list corrections | 01 77 00 | approved
Eugene Stewart | Decatur High School Renovation | 2025-03-20 | 6 | Safety barricade installation | 01 56 00 | approved
Dylan Adams | Hapeville Distribution Center | 2025-03-20 | 8 | Coordination with subcontractors | 01 31 00 | approved
Wayne Perry | Peachtree Office Tower | 2025-03-21 | 10 | Quality inspection rounds | 01 45 00 | approved
Austin Peterson | Emory Medical Wing Expansion | 2025-03-24 | 10 | Safety barricade installation | 01 56 00 | approved
Joan Roberts | Hapeville Distribution Center | 2025-03-24 | 9 | Coordination with subcontractors | 01 31 00 | approved
Austin Peterson | Decatur High School Renovation | 2025-03-26 | 8 | Rebar tying and placement | 03 20 00 | approved
Cheryl Ellis | Emory Medical Wing Expansion | 2025-03-27 | 10 | Safety barricade installation | 01 56 00 | approved
Helen Burke | Peachtree Office Tower | 2025-03-27 | 9 | Excavation support monitoring | 31 50 00 | approved
Barbara Jimenez | Emory Medical Wing Expansion | 2025-03-28 | 9 | Concrete formwork assembly | 03 10 00 | approved
Bruce Sullivan | Peachtree Office Tower | 2025-03-28 | 8 | Safety barricade installation | 01 56 00 | approved
Wayne Perry | Peachtree Office Tower | 2025-03-31 | 8 | Project documentation and photos | 01 33 00 | approved
Christine Collins | Decatur High School Renovation | 2025-04-01 | 8 | Excavation support monitoring | 31 50 00 | approved
Dorothy Torres | Peachtree Office Tower | 2025-04-01 | 9 | Concrete placement and finishing | 03 30 00 | approved
Amy Green | Hapeville Distribution Center | 2025-04-02 | 10 | Excavation support monitoring | 31 50 00 | approved
Christine Morton | Decatur High School Renovation | 2025-04-03 | 8 | Grade checking and compaction testing | 31 20 00 | approved
Joseph Wood | Peachtree Office Tower | 2025-04-03 | 8 | Concrete placement and finishing | 03 30 00 | approved
Christine Collins | Peachtree Office Tower | 2025-04-04 | 9 | Project documentation and photos | 01 33 00 | approved
Christine Collins | Decatur High School Renovation | 2025-04-04 | 8 | Excavation support monitoring | 31 50 00 | approved
Christine Collins | Emory Medical Wing Expansion | 2025-04-04 | 9 | Concrete placement and finishing | 03 30 00 | approved
Dorothy Torres | Emory Medical Wing Expansion | 2025-04-08 | 8 | Steel connection bolting | 05 12 00 | approved
Austin Peterson | Decatur High School Renovation | 2025-04-08 | 9 | Scaffold erection | 01 54 00 | approved
Jason White | Decatur High School Renovation | 2025-04-08 | 6 | Site layout and surveying | 01 71 00 | approved
Cheryl Ellis | Peachtree Office Tower | 2025-04-09 | 8 | Concrete placement and finishing | 03 30 00 | approved
Dorothy Torres | Emory Medical Wing Expansion | 2025-04-09 | 9 | Concrete placement and finishing | 03 30 00 | approved
Christine Morton | Emory Medical Wing Expansion | 2025-04-09 | 8 | Temporary enclosure setup | 01 54 00 | approved
Barbara Jimenez | Hapeville Distribution Center | 2025-04-10 | 9 | Quality inspection rounds | 01 45 00 | approved
Dylan Adams | Peachtree Office Tower | 2025-04-10 | 6 | Steel connection bolting | 05 12 00 | approved
Austin Peterson | Emory Medical Wing Expansion | 2025-04-10 | 8 | Site layout and surveying | 01 71 00 | approved
Bruce Sullivan | Decatur High School Renovation | 2025-04-10 | 8 | Grade checking and compaction testing | 31 20 00 | approved
Joan Roberts | Decatur High School Renovation | 2025-04-10 | 10 | Concrete formwork assembly | 03 10 00 | approved
Richard Cole | Peachtree Office Tower | 2025-04-11 | 8 | Project documentation and photos | 01 33 00 | approved
Jason White | Hapeville Distribution Center | 2025-04-11 | 8 | Project documentation and photos | 01 33 00 | approved
Austin Peterson | Emory Medical Wing Expansion | 2025-04-14 | 10 | Steel connection bolting | 05 12 00 | approved
Amy Green | Decatur High School Renovation | 2025-04-16 | 8 | Quality inspection rounds | 01 45 00 | approved
Louis Walker | Decatur High School Renovation | 2025-04-16 | 7 | Scaffold erection | 01 54 00 | approved
Louis Walker | Peachtree Office Tower | 2025-04-17 | 8 | Punch list corrections | 01 77 00 | approved
Amy Green | Emory Medical Wing Expansion | 2025-04-17 | 9 | Rebar tying and placement | 03 20 00 | approved
Dylan Adams | Peachtree Office Tower | 2025-04-17 | 6 | Excavation support monitoring | 31 50 00 | approved
George Johnson | Decatur High School Renovation | 2025-04-22 | 8 | Coordination with subcontractors | 01 31 00 | approved
Joseph Wood | Hapeville Distribution Center | 2025-04-23 | 6 | Coordination with subcontractors | 01 31 00 | approved
Steven Wilson | Peachtree Office Tower | 2025-04-25 | 6 | Punch list corrections | 01 77 00 | approved
Dylan Adams | Emory Medical Wing Expansion | 2025-04-28 | 10 | Punch list corrections | 01 77 00 | approved
George Johnson | Decatur High School Renovation | 2025-04-29 | 8 | Scaffold erection | 01 54 00 | approved

## Change Orders
co_number | title | description | amount | status | change_order_type | project_name | cost_code | submitted_date
MBG-CO-001 | Additional structural bracing at elevator shaft | Change order: Additional structural bracing at elevator shaft | 85000.00 | draft | cost | Peachtree Office Tower | 05 12 00 | 2025-03-20
MBG-CO-002 | Owner-requested lobby finish upgrade | Change order: Owner-requested lobby finish upgrade | 220000.00 | draft | owner | Peachtree Office Tower | 09 00 00 | 2025-02-27
MBG-CO-003 | Unforeseen rock removal at foundations | Change order: Unforeseen rock removal at foundations | 145000.00 | draft | cost | Peachtree Office Tower | 31 23 00 | 2025-03-04
MBG-CO-004 | Added isolation room — Emory requirement | Change order: Added isolation room — Emory requirement | 310000.00 | draft | owner | Emory Medical Wing Expansion | 22 00 00 | 2025-03-04
MBG-CO-005 | Asbestos abatement — additional scope | Change order: Asbestos abatement — additional scope | 175000.00 | draft | cost | Emory Medical Wing Expansion | 02 82 00 | 2025-03-14
MBG-CO-006 | Generator upgrade from 500kW to 750kW | Change order: Generator upgrade from 500kW to 750kW | 95000.00 | draft | owner | Emory Medical Wing Expansion | 26 32 00 | 2025-02-09
MBG-CO-007 | Gymnasium bleacher spec change | Change order: Gymnasium bleacher spec change | 68000.00 | draft | owner | Decatur High School Renovation | 12 61 00 | 2025-03-10
MBG-CO-008 | Existing CMU wall reinforcement | Change order: Existing CMU wall reinforcement | 42000.00 | draft | cost | Decatur High School Renovation | 04 21 00 | 2025-02-04
MBG-CO-009 | Additional dock door — west elevation | Change order: Additional dock door — west elevation | 55000.00 | draft | owner | Hapeville Distribution Center | 08 36 00 | 2025-03-07
MBG-CO-010 | Upgraded fire suppression — ESFR sprinklers | Change order: Upgraded fire suppression — ESFR sprinklers | 78000.00 | draft | cost | Hapeville Distribution Center | 21 13 00 | 2025-04-01

## Daily Logs
log_date | weather_conditions | temperature | work_performed | safety_incidents | delays | project_name | status
2025-01-06 | Thunderstorms | 70 | Temporary power upgrade for tower crane TC-2. Transformer delivered and placed by crane. | None | None | Emory Medical Wing Expansion | submitted
2025-01-06 | Sunny | 72 | MEP rough-in coordination meeting. Electrical and mechanical crews on floors 2-3. No conflicts. | None | None | Peachtree Office Tower | submitted
2025-01-07 | Sunny | 75 | Painting crew began primer coat in finished offices. Floor tile layout in lobby area. | Near-miss: unsecured material stack corrected | None | Emory Medical Wing Expansion | submitted
2025-01-07 | Sunny | 75 | MEP rough-in coordination meeting. Electrical and mechanical crews on floors 2-3. No conflicts. | None | Material delivery late — rebar | Peachtree Office Tower | submitted
2025-01-08 | Clear | 58 | HVAC ductwork installation in mechanical penthouse. 3 RTUs set on roof curbs by crane. | None | None | Emory Medical Wing Expansion | submitted
2025-01-08 | Partly Cloudy | 62 | Roofing crew completed 8,000 SF of TPO membrane on flat roof section. Flashing at parapet walls. | None | None | Peachtree Office Tower | submitted
2025-01-09 | Clear | 52 | Structural steel erection floors 5-6. Tower crane TC-1 operational. Ironworkers completed 22 connections. | None | Crane down for maintenance — 3 hours | Emory Medical Wing Expansion | submitted
2025-01-09 | Clear | 60 | Punch list walk-through with owner's rep. 42 items identified, 15 completed same day. | None | None | Peachtree Office Tower | submitted
2025-01-10 | Rain | 48 | Interior framing on floors 1-2. Drywall hung in corridor areas. Fire sprinkler branch lines in ceiling space. | None | None | Emory Medical Wing Expansion | submitted
2025-01-10 | Clear | 58 | Fire alarm device installation floors 1-3. Testing scheduled for next week. | None | None | Peachtree Office Tower | submitted
2025-01-13 | Foggy | 56 | Interior framing on floors 1-2. Drywall hung in corridor areas. Fire sprinkler branch lines in ceiling space. | None | None | Emory Medical Wing Expansion | submitted
2025-01-13 | Partly Cloudy | 65 | HVAC ductwork installation in mechanical penthouse. 3 RTUs set on roof curbs by crane. | None | None | Peachtree Office Tower | submitted
2025-01-14 | Sunny | 68 | Concrete pour for level 3 floor deck. 180 CY placed, pump truck on-site. Steel erection continued on grid lines A-F. | None | Crane down for maintenance — 3 hours | Emory Medical Wing Expansion | submitted
2025-01-14 | Clear | 60 | Structural steel erection floors 5-6. Tower crane TC-1 operational. Ironworkers completed 22 connections. | None | None | Peachtree Office Tower | submitted
2025-01-15 | Partly Cloudy | 65 | Roofing crew completed 8,000 SF of TPO membrane on flat roof section. Flashing at parapet walls. | None | None | Emory Medical Wing Expansion | submitted
2025-01-15 | Clear | 52 | HVAC ductwork installation in mechanical penthouse. 3 RTUs set on roof curbs by crane. | None | None | Peachtree Office Tower | submitted
2025-01-16 | Overcast | 55 | Roofing crew completed 8,000 SF of TPO membrane on flat roof section. Flashing at parapet walls. | None | None | Emory Medical Wing Expansion | submitted
2025-01-16 | Clear | 52 | Structural steel erection floors 5-6. Tower crane TC-1 operational. Ironworkers completed 22 connections. | Near-miss: unsecured material stack corrected | Crane down for maintenance — 3 hours | Peachtree Office Tower | submitted
2025-01-17 | Clear | 58 | HVAC ductwork installation in mechanical penthouse. 3 RTUs set on roof curbs by crane. | None | Material delivery late — rebar | Emory Medical Wing Expansion | submitted
2025-01-17 | Sunny | 75 | MEP rough-in coordination meeting. Electrical and mechanical crews on floors 2-3. No conflicts. | Near-miss: unsecured material stack corrected | None | Peachtree Office Tower | submitted
2025-01-20 | Partly Cloudy | 62 | Plumbing top-out on floors 4-5. Above-ceiling inspection passed by city inspector. | None | Material delivery late — rebar | Emory Medical Wing Expansion | submitted
2025-01-20 | Clear | 58 | Site concrete — sidewalks and curb cuts at main entrance. ADA ramp formed and poured. | None | Crane down for maintenance — 3 hours | Peachtree Office Tower | submitted
2025-01-21 | Sunny | 75 | Plumbing top-out on floors 4-5. Above-ceiling inspection passed by city inspector. | None | None | Emory Medical Wing Expansion | submitted
2025-01-21 | Clear | 58 | Painting crew began primer coat in finished offices. Floor tile layout in lobby area. | None | None | Peachtree Office Tower | submitted
2025-01-22 | Foggy | 56 | Punch list walk-through with owner's rep. 42 items identified, 15 completed same day. | None | None | Emory Medical Wing Expansion | submitted
2025-01-22 | Clear | 52 | HVAC ductwork installation in mechanical penthouse. 3 RTUs set on roof curbs by crane. | None | None | Peachtree Office Tower | submitted
2025-01-23 | Sunny | 68 | Fire alarm device installation floors 1-3. Testing scheduled for next week. | None | None | Emory Medical Wing Expansion | submitted
2025-01-23 | Sunny | 75 | Plumbing top-out on floors 4-5. Above-ceiling inspection passed by city inspector. | None | Crane down for maintenance — 3 hours | Peachtree Office Tower | submitted
2025-01-24 | Clear | 60 | Roofing crew completed 8,000 SF of TPO membrane on flat roof section. Flashing at parapet walls. | None | Crane down for maintenance — 3 hours | Emory Medical Wing Expansion | submitted
2025-01-24 | Foggy | 56 | Temporary power upgrade for tower crane TC-2. Transformer delivered and placed by crane. | None | Material delivery late — rebar | Peachtree Office Tower | submitted
2025-01-27 | Clear | 52 | Temporary power upgrade for tower crane TC-2. Transformer delivered and placed by crane. | None | None | Emory Medical Wing Expansion | submitted
2025-01-27 | Clear | 58 | Structural steel erection floors 5-6. Tower crane TC-1 operational. Ironworkers completed 22 connections. | None | Material delivery late — rebar | Peachtree Office Tower | submitted
2025-01-28 | Thunderstorms | 70 | Fire alarm device installation floors 1-3. Testing scheduled for next week. | None | Crane down for maintenance — 3 hours | Emory Medical Wing Expansion | submitted
2025-01-28 | Thunderstorms | 70 | Elevator shaft framing and guide rail installation. Pit waterproofing completed and inspected. | None | Rain delay — 2 hours | Peachtree Office Tower | submitted
2025-01-29 | Clear | 52 | Elevator shaft framing and guide rail installation. Pit waterproofing completed and inspected. | None | None | Emory Medical Wing Expansion | submitted
2025-01-29 | Clear | 52 | Fire alarm device installation floors 1-3. Testing scheduled for next week. | None | None | Peachtree Office Tower | submitted
2025-01-30 | Clear | 58 | Foundation waterproofing and backfill on east elevation. Excavator grading for parking lot base. | None | None | Emory Medical Wing Expansion | submitted
2025-01-30 | Rain | 48 | Interior framing on floors 1-2. Drywall hung in corridor areas. Fire sprinkler branch lines in ceiling space. | None | None | Peachtree Office Tower | submitted
2025-01-31 | Foggy | 56 | Interior framing on floors 1-2. Drywall hung in corridor areas. Fire sprinkler branch lines in ceiling space. | None | None | Emory Medical Wing Expansion | submitted
2025-01-31 | Partly Cloudy | 62 | Plumbing top-out on floors 4-5. Above-ceiling inspection passed by city inspector. | None | None | Peachtree Office Tower | submitted
2025-02-03 | Thunderstorms | 70 | Punch list walk-through with owner's rep. 42 items identified, 15 completed same day. | None | None | Emory Medical Wing Expansion | submitted
2025-02-03 | Rain | 48 | Masonry veneer installation on north elevation. Scaffold erected to 4th floor height. | None | None | Peachtree Office Tower | submitted
2025-02-04 | Foggy | 56 | HVAC ductwork installation in mechanical penthouse. 3 RTUs set on roof curbs by crane. | None | Rain delay — 2 hours | Emory Medical Wing Expansion | submitted
2025-02-04 | Foggy | 56 | Structural steel erection floors 5-6. Tower crane TC-1 operational. Ironworkers completed 22 connections. | Near-miss: unsecured material stack corrected | None | Peachtree Office Tower | submitted
2025-02-05 | Overcast | 55 | Foundation waterproofing and backfill on east elevation. Excavator grading for parking lot base. | None | None | Emory Medical Wing Expansion | submitted
2025-02-05 | Clear | 58 | Painting crew began primer coat in finished offices. Floor tile layout in lobby area. | None | None | Peachtree Office Tower | submitted
2025-02-06 | Thunderstorms | 70 | MEP rough-in coordination meeting. Electrical and mechanical crews on floors 2-3. No conflicts. | None | None | Emory Medical Wing Expansion | submitted
2025-02-06 | Sunny | 75 | Fire alarm device installation floors 1-3. Testing scheduled for next week. | None | None | Peachtree Office Tower | submitted
2025-02-07 | Clear | 52 | MEP rough-in coordination meeting. Electrical and mechanical crews on floors 2-3. No conflicts. | None | None | Emory Medical Wing Expansion | submitted
2025-02-07 | Sunny | 68 | Fire alarm device installation floors 1-3. Testing scheduled for next week. | None | Crane down for maintenance — 3 hours | Peachtree Office Tower | submitted

## RFIs
rfi_number | title | description | status | priority | submitted_date | required_date | project_name | cost_code
MBG-RFI-001 | Structural steel connection detail at grid B-4 | Requesting clarification on structural steel connection detail at grid b-4. See attached drawing markup. | open | high | 2025-03-11 | 2025-03-25 | Peachtree Office Tower | 05 12 00
MBG-RFI-002 | Concrete floor flatness tolerance — server room | Requesting clarification on concrete floor flatness tolerance — server room. See attached drawing markup. | closed | normal | 2025-02-14 | 2025-02-28 | Peachtree Office Tower | 03 30 00
MBG-RFI-003 | Curtain wall anchor spacing at parapet | Requesting clarification on curtain wall anchor spacing at parapet. See attached drawing markup. | responded | high | 2025-02-18 | 2025-03-04 | Peachtree Office Tower | 08 44 00
MBG-RFI-004 | Electrical panel location conflict with ductwork | Requesting clarification on electrical panel location conflict with ductwork. See attached drawing markup. | open | high | 2025-01-17 | 2025-01-31 | Peachtree Office Tower | 26 24 00
MBG-RFI-005 | Fire sprinkler head placement in ceiling grid | Requesting clarification on fire sprinkler head placement in ceiling grid. See attached drawing markup. | responded | high | 2025-02-28 | 2025-03-14 | Peachtree Office Tower | 21 13 00
MBG-RFI-006 | Waterproofing detail at elevator pit | Requesting clarification on waterproofing detail at elevator pit. See attached drawing markup. | responded | high | 2025-03-18 | 2025-04-01 | Emory Medical Wing Expansion | 07 10 00
MBG-RFI-007 | Medical gas piping routing through fire wall | Requesting clarification on medical gas piping routing through fire wall. See attached drawing markup. | closed | normal | 2025-01-31 | 2025-02-14 | Emory Medical Wing Expansion | 22 63 00
MBG-RFI-008 | Clean room HVAC pressure differential spec | Requesting clarification on clean room hvac pressure differential spec. See attached drawing markup. | responded | urgent | 2025-02-15 | 2025-03-01 | Emory Medical Wing Expansion | 23 81 00
MBG-RFI-009 | Lead abatement scope in existing wall cavities | Requesting clarification on lead abatement scope in existing wall cavities. See attached drawing markup. | open | normal | 2025-03-18 | 2025-04-01 | Emory Medical Wing Expansion | 02 83 00
MBG-RFI-010 | Patient room headwall rough-in dimensions | Requesting clarification on patient room headwall rough-in dimensions. See attached drawing markup. | open | normal | 2025-02-06 | 2025-02-20 | Emory Medical Wing Expansion | 26 27 00
MBG-RFI-011 | Existing foundation condition — classroom wing | Requesting clarification on existing foundation condition — classroom wing. See attached drawing markup. | open | normal | 2025-01-23 | 2025-02-06 | Decatur High School Renovation | 03 10 00
MBG-RFI-012 | ADA ramp slope discrepancy at main entrance | Requesting clarification on ada ramp slope discrepancy at main entrance. See attached drawing markup. | closed | urgent | 2025-01-28 | 2025-02-11 | Decatur High School Renovation | 03 30 00
MBG-RFI-013 | Asbestos abatement sequence with occupied areas | Requesting clarification on asbestos abatement sequence with occupied areas. See attached drawing markup. | responded | high | 2025-03-22 | 2025-04-05 | Decatur High School Renovation | 02 82 00
MBG-RFI-014 | Warehouse slab thickness at dock leveler pits | Requesting clarification on warehouse slab thickness at dock leveler pits. See attached drawing markup. | open | urgent | 2025-03-19 | 2025-04-02 | Hapeville Distribution Center | 03 30 00
MBG-RFI-015 | Fire suppression system type for high-bay storage | Requesting clarification on fire suppression system type for high-bay storage. See attached drawing markup. | closed | normal | 2025-03-06 | 2025-03-20 | Hapeville Distribution Center | 21 13 00

## Safety Incidents
title | description | incident_type | severity | incident_date | project_name | osha_recordable | status
Worker struck by falling bolt — Tower Crane area | Ironworker struck on hard hat by dropped 3/4" bolt during steel erection. Hard hat absorbed impact. No injury. Exclusion zone expanded and enforced. | near_miss | high | 2025-01-15 | Peachtree Office Tower | no | closed
Excavation cave-in near-miss | Small soil collapse at edge of excavation. No workers in trench at time. Trench box was 4ft from collapse point. Competent person assessment conducted. | near_miss | high | 2025-01-28 | Emory Medical Wing Expansion | no | closed
Carpenter laceration — table saw | Carpenter sustained 2cm laceration on left index finger from table saw kickback. First aid on-site. Employee returned to modified duty. | injury | medium | 2025-02-08 | Decatur High School Renovation | yes | closed
Forklift tip-over in staging area | Telehandler tipped onto outrigger while lifting steel beam. Operator was belted in cab, no injury. Overload alarm had been disabled — corrective action taken. | property_damage | high | 2025-02-22 | Peachtree Office Tower | no | closed
Heat exhaustion — concrete crew | Two laborers experienced heat exhaustion during afternoon concrete pour. Treated on-site with shade, water, and cold towels. Both recovered fully. | injury | medium | 2025-03-15 | Hapeville Distribution Center | no | closed
Scaffolding plank failure | One plank cracked under load during masonry work. Worker was tied off and did not fall. Plank inspected — dry rot discovered. All planks on-site inspected. | near_miss | high | 2025-03-22 | Emory Medical Wing Expansion | no | reported
Electrical shock — temporary power panel | Electrician received minor shock from temporary power panel with loose ground. Panel de-energized, repaired, and re-inspected by electrical sub. | injury | medium | 2025-04-02 | Peachtree Office Tower | no | reported
Vehicle backing incident — delivery truck | Concrete delivery truck backed into temporary fence during pour. No personnel in area. Fence repaired same day. Spotter protocol reinforced. | property_damage | low | 2025-04-10 | Decatur High School Renovation | no | reported

## Safety Inspections
inspection_type | inspection_date | score | findings | corrective_actions | status | project_name
site_safety | 2025-01-08 | 93 | Harness inspections, guardrail systems, and hole covers verified. | 2 expired harnesses found — removed from service. | completed | Peachtree Office Tower
site_safety | 2025-01-16 | 85 | All scaffold erection per OSHA 1926.451. Base plates, planking, and guardrails checked. | None — all systems compliant. | completed | Emory Medical Wing Expansion
site_safety | 2025-01-24 | 90 | Pre-operation inspection logs reviewed. Rigging hardware inspected. | 1 shackle at capacity — replaced with next size up. | completed | Decatur High School Renovation
site_safety | 2025-02-01 | 87 | Competent person logs, trench box condition, sloping angles verified. | Spoil pile within 2ft of edge — moved to 5ft minimum. | completed | Hapeville Distribution Center
site_safety | 2025-02-09 | 89 | GFCI protection, temporary power panel condition, lockout/tagout. | 3 GFCIs failed trip test — replaced immediately. | completed | Peachtree Office Tower
site_safety | 2025-02-17 | 85 | Hot work permits, fire extinguisher placement, egress routes clear. | 1 extinguisher past inspection date — replaced. | completed | Emory Medical Wing Expansion
site_safety | 2025-02-25 | 99 | Walking surfaces clear, material stacking heights, dumpster placement. | Wire spool storage area needed reorganization. | completed | Decatur High School Renovation
site_safety | 2025-03-05 | 94 | Hard hats, safety glasses, hi-vis vests, steel-toe boots verified. | 98% compliance. 1 worker missing hi-vis vest — provided. | completed | Hapeville Distribution Center
site_safety | 2025-03-13 | 99 | Pump truck setup, pour area barriers, silica dust controls. | Dust monitors repositioned for better coverage. | completed | Peachtree Office Tower
site_safety | 2025-03-21 | 99 | All ladders tagged and inspected. Setup angles and tie-off verified. | 2 damaged fiberglass ladders removed from service. | completed | Emory Medical Wing Expansion
site_safety | 2025-03-29 | 95 | Pre-operation checklists, seatbelt use, backup alarms, mirrors. | Backup alarm on skid steer inaudible — repaired. | completed | Decatur High School Renovation
site_safety | 2025-04-06 | 92 | Permits, atmospheric testing, rescue equipment, attendant logs. | All entries compliant. New gas monitor calibrated. | completed | Hapeville Distribution Center

## Toolbox Talks
title | topic | description | scheduled_date | attendees_count | project_name | status | notes
Fall Protection — 100% Tie-Off Policy | Fall Protection | Review of company 100% tie-off policy. Proper harness donning. Anchor point selection. | 2025-01-06 | 28 | Peachtree Office Tower | completed | Presented by Cheryl Ellis
Crane Safety & Signal Communication | Crane Safety | Crane hand signals review. Exclusion zones. Load chart awareness for all workers. | 2025-01-13 | 38 | Emory Medical Wing Expansion | completed | Presented by Joseph Wood
Excavation Safety — Competent Person | Excavation | Soil types, protective systems, and competent person responsibilities. | 2025-01-20 | 29 | Decatur High School Renovation | completed | Presented by Louis Walker
Heat Illness Prevention | Environmental | Hydration requirements, shade breaks, buddy system. Signs of heat stroke vs exhaustion. | 2025-01-27 | 28 | Hapeville Distribution Center | completed | Presented by Helen Burke
Silica Dust Exposure Controls | Respiratory | Wet cutting methods, vacuum attachments, and respiratory protection for concrete/masonry work. | 2025-02-03 | 24 | Peachtree Office Tower | completed | Presented by Christine Morton
Housekeeping & Slip/Trip/Fall Prevention | General Safety | Clean as you go policy. Material storage. Walking surface maintenance. | 2025-02-10 | 43 | Emory Medical Wing Expansion | completed | Presented by Joan Roberts
Lockout/Tagout — Electrical Safety | Electrical Safety | Energy isolation procedures. Lock placement. Verification testing. | 2025-02-17 | 39 | Decatur High School Renovation | completed | Presented by Harry Roberts
Scaffolding Safety | Fall Protection | Erection/dismantling by qualified persons. Platform loading limits. Access requirements. | 2025-02-24 | 38 | Hapeville Distribution Center | completed | Presented by Cheryl Ellis
Fire Prevention & Hot Work | Fire Safety | Hot work permit process. Fire watch duties. Extinguisher locations. | 2025-03-03 | 42 | Peachtree Office Tower | completed | Presented by Joseph Wood
Struck-By Hazard Awareness | General Safety | Overhead work, falling objects, vehicle traffic. Hard hat and hi-vis requirements. | 2025-03-10 | 42 | Emory Medical Wing Expansion | completed | Presented by Louis Walker
Personal Protective Equipment | PPE | Required PPE by task. Inspection procedures. Replacement protocols. | 2025-03-17 | 36 | Decatur High School Renovation | completed | Presented by Helen Burke
Confined Space Entry | Confined Space | Permit process. Atmospheric testing. Rescue plan. Never enter without authorization. | 2025-03-24 | 22 | Hapeville Distribution Center | completed | Presented by Christine Morton
Back Injury Prevention | Ergonomics | Proper lifting techniques. Team lifts. Mechanical aids. Stretch and flex program. | 2025-03-31 | 27 | Peachtree Office Tower | completed | Presented by Joan Roberts
Concrete Operations Safety | Concrete | Chemical burns from wet concrete. Silica exposure. Pump truck setup zones. | 2025-04-07 | 42 | Emory Medical Wing Expansion | completed | Presented by Harry Roberts
Emergency Action Plan Review | Emergency | Evacuation routes. Assembly points. Emergency contacts. First aid station locations. | 2025-04-14 | 23 | Decatur High School Renovation | completed | Presented by Cheryl Ellis

## Equipment Assignments
equipment_name | project_name | assigned_date | return_date | status
Tower Crane TC-1 | Peachtree Office Tower | 2024-06-01 | 2025-12-31 | active
Tower Crane TC-2 | Emory Medical Wing Expansion | 2024-09-01 | 2026-03-31 | active
Boom Lift 80ft | Peachtree Office Tower | 2025-01-15 | 2025-06-30 | active
Boom Lift 60ft | Emory Medical Wing Expansion | 2025-01-15 | 2025-08-31 | active
Scissor Lift 40ft | Peachtree Office Tower | 2025-02-01 | 2025-09-30 | active
Telehandler 10K | Peachtree Office Tower | 2024-06-01 | 2025-10-31 | active
Telehandler 12K | Emory Medical Wing Expansion | 2024-09-01 | 2025-12-31 | active
Crawler Excavator | Hapeville Distribution Center | 2025-03-01 | 2025-08-31 | active
Backhoe Loader | Decatur High School Renovation | 2025-01-15 | 2025-06-30 | active
Skid Steer Loader | Hapeville Distribution Center | 2025-03-01 | 2025-09-30 | active
Concrete Pump Truck | Peachtree Office Tower | 2025-01-01 | 2025-04-30 | active
Concrete Pump Truck | Emory Medical Wing Expansion | 2025-05-01 | 2025-09-30 | active
Generator 100kW | Peachtree Office Tower | 2024-06-01 | 2025-12-31 | active
Generator 60kW | Decatur High School Renovation | 2025-01-15 | 2025-12-31 | active
Pickup Truck #1 | Peachtree Office Tower | 2024-06-01 | 2025-12-31 | active
Pickup Truck #2 | Emory Medical Wing Expansion | 2024-09-01 | 2026-06-30 | active
Pickup Truck #3 | Decatur High School Renovation | 2025-01-15 | 2025-12-31 | active
Pickup Truck #4 | Hapeville Distribution Center | 2025-03-01 | 2025-11-30 | active
Flatbed Truck | Peachtree Office Tower | 2025-01-01 | 2025-06-30 | active
Flatbed Truck | Emory Medical Wing Expansion | 2025-07-01 | 2025-12-31 | active

## Equipment Maintenance
equipment_name | maintenance_type | description | scheduled_date | completed_date | status | cost
Tower Crane TC-1 | preventive | Annual inspection & load test | 2025-01-15 | 2025-01-15 | completed | 0
Tower Crane TC-2 | preventive | Annual inspection & load test | 2025-02-10 | 2025-02-10 | completed | 0
Crawler Excavator | preventive | Hydraulic system service — 500hr | 2025-03-05 | 2025-03-05 | completed | 0
Boom Lift 80ft | preventive | Annual certification inspection | 2025-01-22 | 2025-01-22 | completed | 0
Boom Lift 60ft | preventive | Annual certification inspection | 2025-01-22 | 2025-01-22 | completed | 0
Telehandler 10K | preventive | Engine oil & filter change — 250hr | 2025-02-18 | 2025-02-18 | completed | 0
Telehandler 12K | preventive | Brake inspection & adjustment | 2025-03-15 | 2025-03-15 | completed | 0
Concrete Pump Truck | preventive | Boom wear pad replacement | 2025-02-28 | 2025-02-28 | completed | 0
Generator 100kW | preventive | Fuel system flush & filter replace | 2025-03-20 | 2025-03-20 | completed | 0
Pickup Truck #1 | preventive | Oil change & tire rotation — 7500mi | 2025-01-10 | 2025-01-10 | completed | 0
Pickup Truck #3 | preventive | Brake pad replacement | 2025-03-01 | 2025-03-01 | completed | 0
Flatbed Truck | preventive | DOT annual safety inspection | 2025-02-05 | 2025-02-05 | completed | 0

## Submittals
submittal_number | title | description | status | submitted_date | project_name | cost_code
MBG-SUB-001 | Structural steel shop drawings — Floors 1-6 | Submittal for structural steel shop drawings — floors 1-6 | approved | 2025-01-13 | Peachtree Office Tower | 05 12 00
MBG-SUB-002 | Curtain wall system — mock-up review | Submittal for curtain wall system — mock-up review | revise_resubmit | 2025-02-17 | Peachtree Office Tower | 08 44 00
MBG-SUB-003 | Concrete mix design — 5000 PSI | Submittal for concrete mix design — 5000 psi | approved | 2025-01-31 | Peachtree Office Tower | 03 30 00
MBG-SUB-004 | Elevator cab finishes & fixtures | Submittal for elevator cab finishes & fixtures | revise_resubmit | 2025-02-25 | Peachtree Office Tower | 14 21 00
MBG-SUB-005 | LED light fixtures — Type A/B/C | Submittal for led light fixtures — type a/b/c | approved | 2025-02-03 | Peachtree Office Tower | 26 51 00
MBG-SUB-006 | Fire sprinkler shop drawings | Submittal for fire sprinkler shop drawings | approved | 2025-02-21 | Emory Medical Wing Expansion | 21 13 00
MBG-SUB-007 | Medical gas system components | Submittal for medical gas system components | approved_as_noted | 2025-02-03 | Emory Medical Wing Expansion | 22 63 00
MBG-SUB-008 | HVAC equipment — air handling units | Submittal for hvac equipment — air handling units | approved | 2025-02-17 | Emory Medical Wing Expansion | 23 73 00
MBG-SUB-009 | Flooring — vinyl sheet for patient rooms | Submittal for flooring — vinyl sheet for patient rooms | revise_resubmit | 2025-02-19 | Emory Medical Wing Expansion | 09 65 00
MBG-SUB-010 | Epoxy resin flooring — lab areas | Submittal for epoxy resin flooring — lab areas | approved | 2025-03-09 | Emory Medical Wing Expansion | 09 67 00
MBG-SUB-011 | Masonry veneer samples & mortar color | Submittal for masonry veneer samples & mortar color | revise_resubmit | 2025-03-08 | Decatur High School Renovation | 04 21 00
MBG-SUB-012 | Gymnasium floor system — maple hardwood | Submittal for gymnasium floor system — maple hardwood | revise_resubmit | 2025-03-02 | Decatur High School Renovation | 09 64 00
MBG-SUB-013 | Roofing TPO membrane & insulation | Submittal for roofing tpo membrane & insulation | approved | 2025-01-31 | Decatur High School Renovation | 07 54 00
MBG-SUB-014 | Pre-engineered metal building system | Submittal for pre-engineered metal building system | approved | 2025-03-11 | Hapeville Distribution Center | 13 34 00
MBG-SUB-015 | Dock levelers & overhead doors | Submittal for dock levelers & overhead doors | approved | 2025-02-23 | Hapeville Distribution Center | 08 36 00

## Tasks
name | code | start_date | end_date | status | project_name | phase_name
Mobilization & site setup | 01 50 00 | 2024-02-15 | 2024-03-21 | in_progress | Peachtree Office Tower | Preconstruction
Demolition & site clearing | 02 41 00 | 2024-03-21 | 2024-05-17 | in_progress | Peachtree Office Tower | Preconstruction
Excavation & earthwork | 31 20 00 | 2024-05-17 | 2024-07-27 | in_progress | Peachtree Office Tower | Preconstruction
Foundations & footings | 03 30 00 | 2024-07-27 | 2024-10-20 | in_progress | Peachtree Office Tower | Site Work & Foundations
Structural steel erection | 05 12 00 | 2024-10-20 | 2025-02-04 | in_progress | Peachtree Office Tower | Structural
Concrete floors & decks | 03 30 00 | 2025-02-04 | 2025-04-30 | in_progress | Peachtree Office Tower | Structural
Exterior wall framing | 05 40 00 | 2025-04-30 | 2025-07-10 | pending | Peachtree Office Tower | Building Envelope
Roofing & waterproofing | 07 50 00 | 2025-07-10 | 2025-09-05 | pending | Peachtree Office Tower | MEP Rough-In
Window & curtain wall install | 08 44 00 | 2025-09-05 | 2025-11-15 | pending | Peachtree Office Tower | MEP Rough-In
Mechanical rough-in | 23 05 00 | 2025-11-15 | 2026-01-31 | pending | Peachtree Office Tower | Finishes & Closeout
Electrical rough-in | 26 05 00 | 2026-03-02 | 2026-01-31 | pending | Peachtree Office Tower | Finishes & Closeout
Plumbing rough-in | 22 05 00 | 2026-06-17 | 2026-01-31 | pending | Peachtree Office Tower | Finishes & Closeout
Drywall & interior finishes | 09 29 00 | 2026-09-10 | 2026-01-31 | pending | Peachtree Office Tower | Finishes & Closeout
Painting & floor coverings | 09 90 00 | 2026-12-04 | 2026-01-31 | pending | Peachtree Office Tower | Finishes & Closeout
Punch list & closeout | 01 77 00 | 2027-01-30 | 2026-01-31 | pending | Peachtree Office Tower | Finishes & Closeout
Mobilization & site setup | 01 50 00 | 2024-05-01 | 2024-06-09 | in_progress | Emory Medical Wing Expansion | Preconstruction
Demolition & site clearing | 02 41 00 | 2024-06-09 | 2024-08-11 | in_progress | Emory Medical Wing Expansion | Preconstruction
Excavation & earthwork | 31 20 00 | 2024-08-11 | 2024-10-29 | in_progress | Emory Medical Wing Expansion | Preconstruction
Foundations & footings | 03 30 00 | 2024-10-29 | 2025-01-31 | in_progress | Emory Medical Wing Expansion | Site Work & Foundations
Structural steel erection | 05 12 00 | 2025-01-31 | 2025-05-29 | in_progress | Emory Medical Wing Expansion | Structural
Concrete floors & decks | 03 30 00 | 2025-05-29 | 2025-08-31 | in_progress | Emory Medical Wing Expansion | Structural
Exterior wall framing | 05 40 00 | 2025-08-31 | 2025-11-18 | pending | Emory Medical Wing Expansion | Building Envelope
Roofing & waterproofing | 07 50 00 | 2025-11-18 | 2026-01-20 | pending | Emory Medical Wing Expansion | MEP Rough-In
Window & curtain wall install | 08 44 00 | 2026-01-20 | 2026-04-09 | pending | Emory Medical Wing Expansion | MEP Rough-In
Mechanical rough-in | 23 05 00 | 2026-04-09 | 2026-06-30 | pending | Emory Medical Wing Expansion | Finishes & Closeout
Electrical rough-in | 26 05 00 | 2026-08-05 | 2026-06-30 | pending | Emory Medical Wing Expansion | Finishes & Closeout
Plumbing rough-in | 22 05 00 | 2026-12-01 | 2026-06-30 | pending | Emory Medical Wing Expansion | Finishes & Closeout
Drywall & interior finishes | 09 29 00 | 2027-03-05 | 2026-06-30 | pending | Emory Medical Wing Expansion | Finishes & Closeout
Painting & floor coverings | 09 90 00 | 2027-06-07 | 2026-06-30 | pending | Emory Medical Wing Expansion | Finishes & Closeout
Punch list & closeout | 01 77 00 | 2027-08-09 | 2026-06-30 | pending | Emory Medical Wing Expansion | Finishes & Closeout
Mobilization & site setup | 01 50 00 | 2025-01-15 | 2025-02-01 | in_progress | Decatur High School Renovation | Preconstruction
Demolition & site clearing | 02 41 00 | 2025-02-01 | 2025-03-01 | in_progress | Decatur High School Renovation | Preconstruction
Excavation & earthwork | 31 20 00 | 2025-03-01 | 2025-04-05 | in_progress | Decatur High School Renovation | Preconstruction
Foundations & footings | 03 30 00 | 2025-04-05 | 2025-05-17 | in_progress | Decatur High School Renovation | Site Work & Foundations
Structural steel erection | 05 12 00 | 2025-05-17 | 2025-07-08 | in_progress | Decatur High School Renovation | Structural
Concrete floors & decks | 03 30 00 | 2025-07-08 | 2025-08-19 | in_progress | Decatur High School Renovation | Structural
Exterior wall framing | 05 40 00 | 2025-08-19 | 2025-09-23 | pending | Decatur High School Renovation | Building Envelope
Roofing & waterproofing | 07 50 00 | 2025-09-23 | 2025-10-21 | pending | Decatur High School Renovation | MEP Rough-In
Window & curtain wall install | 08 44 00 | 2025-10-21 | 2025-11-25 | pending | Decatur High School Renovation | MEP Rough-In
Mechanical rough-in | 23 05 00 | 2025-11-25 | 2025-12-31 | pending | Decatur High School Renovation | Finishes & Closeout
Electrical rough-in | 26 05 00 | 2026-01-16 | 2025-12-31 | pending | Decatur High School Renovation | Finishes & Closeout
Plumbing rough-in | 22 05 00 | 2026-03-09 | 2025-12-31 | pending | Decatur High School Renovation | Finishes & Closeout
Drywall & interior finishes | 09 29 00 | 2026-04-20 | 2025-12-31 | pending | Decatur High School Renovation | Finishes & Closeout
Painting & floor coverings | 09 90 00 | 2026-06-01 | 2025-12-31 | pending | Decatur High School Renovation | Finishes & Closeout
Punch list & closeout | 01 77 00 | 2026-06-29 | 2025-12-31 | pending | Decatur High School Renovation | Finishes & Closeout
Mobilization & site setup | 01 50 00 | 2025-03-01 | 2025-03-14 | in_progress | Hapeville Distribution Center | Preconstruction
Demolition & site clearing | 02 41 00 | 2025-03-14 | 2025-04-04 | in_progress | Hapeville Distribution Center | Preconstruction
Excavation & earthwork | 31 20 00 | 2025-04-04 | 2025-05-01 | in_progress | Hapeville Distribution Center | Preconstruction
Foundations & footings | 03 30 00 | 2025-05-01 | 2025-06-02 | in_progress | Hapeville Distribution Center | Site Work & Foundations
Structural steel erection | 05 12 00 | 2025-06-02 | 2025-07-13 | in_progress | Hapeville Distribution Center | Structural
Concrete floors & decks | 03 30 00 | 2025-07-13 | 2025-08-14 | in_progress | Hapeville Distribution Center | Structural
Exterior wall framing | 05 40 00 | 2025-08-14 | 2025-09-10 | pending | Hapeville Distribution Center | Building Envelope
Roofing & waterproofing | 07 50 00 | 2025-09-10 | 2025-10-01 | pending | Hapeville Distribution Center | MEP Rough-In
Window & curtain wall install | 08 44 00 | 2025-10-01 | 2025-10-28 | pending | Hapeville Distribution Center | MEP Rough-In
Mechanical rough-in | 23 05 00 | 2025-10-28 | 2025-11-30 | pending | Hapeville Distribution Center | Finishes & Closeout
Electrical rough-in | 26 05 00 | 2025-12-08 | 2025-11-30 | pending | Hapeville Distribution Center | Finishes & Closeout
Plumbing rough-in | 22 05 00 | 2026-01-18 | 2025-11-30 | pending | Hapeville Distribution Center | Finishes & Closeout
Drywall & interior finishes | 09 29 00 | 2026-02-19 | 2025-11-30 | pending | Hapeville Distribution Center | Finishes & Closeout
Painting & floor coverings | 09 90 00 | 2026-03-23 | 2025-11-30 | pending | Hapeville Distribution Center | Finishes & Closeout
Punch list & closeout | 01 77 00 | 2026-04-13 | 2025-11-30 | pending | Hapeville Distribution Center | Finishes & Closeout

## Estimates
estimate_number | title | description | total_amount | status | estimate_date | project_name
MBG-EST-001 | Peachtree Office Tower — Conceptual Estimate | Conceptual budget estimate for Peachtree Office Tower | 26600000.00 | approved | 2023-11-17 | Peachtree Office Tower
MBG-EST-002 | Peachtree Office Tower — GMP Estimate | Guaranteed Maximum Price estimate for Peachtree Office Tower | 28000000.00 | approved | 2024-01-16 | Peachtree Office Tower
MBG-EST-003 | Emory Medical Wing Expansion — Conceptual Estimate | Conceptual budget estimate for Emory Medical Wing Expansion | 30400000.00 | approved | 2024-02-01 | Emory Medical Wing Expansion
MBG-EST-004 | Emory Medical Wing Expansion — GMP Estimate | Guaranteed Maximum Price estimate for Emory Medical Wing Expansion | 32000000.00 | approved | 2024-04-01 | Emory Medical Wing Expansion
MBG-EST-005 | Decatur High School Renovation — Conceptual Estimate | Conceptual budget estimate for Decatur High School Renovation | 14250000.00 | approved | 2024-10-17 | Decatur High School Renovation
MBG-EST-006 | Decatur High School Renovation — GMP Estimate | Guaranteed Maximum Price estimate for Decatur High School Renovation | 15000000.00 | approved | 2024-12-16 | Decatur High School Renovation
MBG-EST-007 | Hapeville Distribution Center — Conceptual Estimate | Conceptual budget estimate for Hapeville Distribution Center | 9500000.00 | approved | 2024-12-01 | Hapeville Distribution Center
MBG-EST-008 | Hapeville Distribution Center — GMP Estimate | Guaranteed Maximum Price estimate for Hapeville Distribution Center | 10000000.00 | approved | 2025-01-30 | Hapeville Distribution Center

## Certifications
contact_name | cert_name | cert_type | issuing_authority | cert_number | issued_date | expiry_date | status
Christine Collins | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-824767 | 2023-06-01 |  | active
Dorothy Torres | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-959969 | 2022-10-22 |  | active
Bruce Sullivan | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-311519 | 2022-12-08 |  | active
Austin Peterson | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-702155 | 2022-09-20 |  | active
Harry Roberts | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-955709 | 2022-06-21 |  | active
Cheryl Ellis | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-436323 | 2022-05-04 |  | active
Joseph Wood | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-264378 | 2022-08-17 |  | active
Louis Walker | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-765536 | 2021-04-08 |  | active
Helen Burke | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-453759 | 2021-07-16 |  | active
Christine Morton | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-590881 | 2021-07-12 |  | active
Joan Roberts | OSHA 30-Hour Construction Safety | certification | OSHA Training Institute | OSHA30-791470 | 2021-12-21 |  | active
Donna Hamilton | Project Management Professional (PMP) | certification | Project Management Institute | PMP-850274 | 2019-10-08 | 2022-10-08 | active
Louis Powell | Project Management Professional (PMP) | certification | Project Management Institute | PMP-608170 | 2020-05-27 | 2023-05-27 | active
Andrea Lewis | Project Management Professional (PMP) | certification | Project Management Institute | PMP-718749 | 2020-09-21 | 2023-09-21 | active
Elijah Morton | Project Management Professional (PMP) | certification | Project Management Institute | PMP-132118 | 2020-10-11 | 2023-10-11 | active
Harry Roberts | First Aid / CPR / AED | certification | American Red Cross | FA-59991 | 2024-06-15 | 2026-06-15 | active
Nathan Nguyen | First Aid / CPR / AED | certification | American Red Cross | FA-91632 | 2024-06-15 | 2026-06-15 | active
Christine Collins | First Aid / CPR / AED | certification | American Red Cross | FA-60553 | 2024-06-15 | 2026-06-15 | active
Dorothy Torres | First Aid / CPR / AED | certification | American Red Cross | FA-83486 | 2024-06-15 | 2026-06-15 | active
Donna Hamilton | LEED AP BD+C | certification | US Green Building Council | LEED-546656 | 2021-03-10 | 2027-03-10 | active