## 01_chart_of_accounts
account_number | name | account_type | sub_type | description
1000 | Cash & Equivalents | asset | Current Asset | Operating cash and short-term deposits
1010 | Accounts Receivable | asset | Current Asset | Amounts owed by clients for completed work
1020 | Retainage Receivable | asset | Current Asset | Retainage held by clients pending project completion
1030 | Work in Progress | asset | Current Asset | Costs incurred on uncompleted contracts
1040 | Prepaid Expenses | asset | Current Asset | Insurance premiums and deposits paid in advance
1100 | Equipment & Vehicles | asset | Fixed Asset | Construction equipment and fleet vehicles
1110 | Accumulated Depreciation - Equipment | asset | Fixed Asset | Depreciation on equipment and vehicles
1200 | Office Furniture & Fixtures | asset | Fixed Asset | Office equipment and furnishings
2000 | Accounts Payable | liability | Current Liability | Amounts owed to vendors and subcontractors
2010 | Retainage Payable | liability | Current Liability | Retainage held from subcontractors
2020 | Accrued Payroll | liability | Current Liability | Wages and salaries earned but not yet paid
2030 | Accrued Taxes | liability | Current Liability | Payroll taxes and income taxes payable
2040 | Short-Term Loans | liability | Current Liability | Line of credit and short-term borrowings
2100 | Long-Term Debt | liability | Long-Term Liability | Equipment loans and mortgages
3000 | Owner's Equity | equity | Owner's Equity | Capital contributed by company owners
3010 | Retained Earnings | equity | Retained Earnings | Accumulated net income from prior years
4000 | Contract Revenue | revenue | Operating Revenue | Revenue earned from construction contracts
4010 | Change Order Revenue | revenue | Operating Revenue | Revenue from approved change orders
4020 | T&M Revenue | revenue | Operating Revenue | Time and materials billing revenue
5000 | Direct Labor | expense | Cost of Revenue | Wages for field workers and tradespeople
5010 | Subcontractor Costs | expense | Cost of Revenue | Payments to subcontractors
5020 | Materials | expense | Cost of Revenue | Lumber cement steel and supplies
5030 | Equipment Costs | expense | Cost of Revenue | Equipment rental fuel and maintenance
5040 | Permits & Fees | expense | Cost of Revenue | Building permits and inspection fees
6000 | Office Salaries | expense | Operating Expense | Administrative and office staff wages
6010 | Rent & Utilities | expense | Operating Expense | Office rent and utility bills
6020 | Insurance | expense | Operating Expense | General liability and workers compensation
6030 | Professional Fees | expense | Operating Expense | Legal and accounting services
6040 | Vehicle Expense | expense | Operating Expense | Fleet fuel maintenance and insurance
6050 | Office Supplies | expense | Operating Expense | General office supplies and software
7000 | Interest Expense | expense | Other Expense | Interest on loans and credit lines
7010 | Depreciation Expense | expense | Other Expense | Monthly depreciation on fixed assets

## 02_contacts
first_name | last_name | contact_type | email | phone | company_name | job_title
Marcus | Thompson | employee | marcus.thompson@email.com | 512-555-0101 |  | Project Manager
Elena | Rodriguez | employee | elena.rodriguez@email.com | 512-555-0102 |  | Superintendent
James | Mitchell | employee | james.mitchell@email.com | 512-555-0103 |  | Site Foreman
Sarah | Chen | employee | sarah.chen@email.com | 512-555-0104 |  | Safety Director
David | Williams | employee | david.williams@email.com | 512-555-0105 |  | Estimator
Karen | Foster | employee | karen.foster@email.com | 512-555-0106 |  | Project Coordinator
Robert | Jackson | employee | robert.jackson@email.com | 512-555-0107 |  | Equipment Manager
Lisa | Nguyen | employee | lisa.nguyen@email.com | 512-555-0108 |  | Office Manager
Carlos | Ramirez | subcontractor | carlos@ramirez-concrete.com | 512-555-0201 | Ramirez Concrete Inc | Owner
Mike | O'Brien | subcontractor | mike@obrien-framing.com | 512-555-0202 | O'Brien Framing LLC | President
Tony | Vasquez | subcontractor | tony@vasquez-electric.com | 512-555-0203 | Vasquez Electrical Services | Owner
Patricia | Hawkins | subcontractor | pat@hawkins-plumbing.com | 512-555-0204 | Hawkins Plumbing Co | Owner
Frank | Doyle | subcontractor | frank@doyle-hvac.com | 512-555-0205 | Doyle Mechanical HVAC | Operations Manager
Steve | Kowalski | subcontractor | steve@kowalski-steel.com | 512-555-0206 | Kowalski Structural Steel | Project Manager
Nina | Santos | subcontractor | nina@santos-paving.com | 512-555-0207 | Santos Paving & Grading | Owner
Rick | Turner | subcontractor | rick@turner-demo.com | 512-555-0208 | Turner Demolition Group | President
Angela | Morrison | vendor | angela@hill-country-lumber.com | 512-555-0301 | Hill Country Lumber Supply | Sales Rep
Brian | Caldwell | vendor | brian@texasreadymix.com | 512-555-0302 | Texas Ready Mix Concrete | Account Manager
Diane | Fletcher | vendor | diane@lonestar-supply.com | 512-555-0303 | Lone Star Building Supply | Sales Manager
Tom | Henderson | vendor | tom@safetyfirst-equip.com | 512-555-0304 | SafetyFirst Equipment Rental | Branch Manager
Richard | Westbrook | client | richard@riverside-dev.com | 512-555-0401 | Riverside Development Group | VP of Development
Catherine | Monroe | client | catherine@metro-commercial.com | 512-555-0402 | Metro Commercial Properties | Director of Construction
Howard | Phillips | client | howard@txdot-region4.gov | 512-555-0403 | Texas DOT Region 4 | Project Engineer
Jennifer | Blake | client | jennifer@riverside-dev.com | 512-555-0404 | Riverside Development Group | Project Coordinator
Michael | Grant | client | michael@metro-commercial.com | 512-555-0405 | Metro Commercial Properties | Facilities Manager

## 03_bank_accounts
name | bank_name | account_type | account_number_last4 | routing_number_last4 | current_balance
Operating Account | First National Bank | checking | 4521 | 7890 | 1285000
Payroll Account | First National Bank | checking | 4522 | 7890 | 342000
Reserve Fund | Texas Capital Bank | savings | 8834 | 4456 | 750000

## 04_equipment
name | equipment_type | make | model | serial_number | purchase_cost | hourly_rate | purchase_date
CAT 320 Excavator | excavator | Caterpillar | 320 GC | CAT320GC-48291 | 285000 | 185 | 2023-03-15
CAT 950 Wheel Loader | loader | Caterpillar | 950 GC | CAT950GC-33012 | 310000 | 165 | 2023-06-20
Liebherr LTM 1060 Crane | crane | Liebherr | LTM 1060-3.1 | LH1060-72841 | 425000 | 350 | 2022-11-10
Kenworth T880 Dump Truck | truck | Kenworth | T880 | KW-T880-55129 | 165000 | 95 | 2024-01-08
John Deere 310SL Backhoe | excavator | John Deere | 310SL | JD310SL-44820 | 115000 | 125 | 2023-09-12
Generac 100kW Generator | generator | Generac | MD100 | GEN-MD100-9921 | 42000 | 55 | 2024-04-01
Atlas Copco XAS 185 Compressor | compressor | Atlas Copco | XAS 185 | AC-XAS185-6612 | 35000 | 45 | 2023-07-18
Genie GS-2632 Scissor Lift | scaffold | Genie | GS-2632 | GN-2632-81204 | 18500 | 35 | 2024-02-25
CAT D6 Dozer | excavator | Caterpillar | D6 XE | CATD6XE-29104 | 340000 | 195 | 2022-08-30
Ford F-350 Service Truck | truck | Ford | F-350 Super Duty | 1FT8W3BT-90122 | 68000 | 45 | 2024-06-15
Wacker Neuson Plate Compactor | tools | Wacker Neuson | BPU 4045A | WN-4045A-1192 | 8500 | 25 | 2024-03-10
Hilti TE 3000 Breaker | tools | Hilti | TE 3000-AVR | HI-3000AVR-5503 | 6200 | 30 | 2024-05-22

## 05_projects
name | code | status | project_type | address | city | state | zip | client_name | client_email | client_phone | budget | estimated_cost | start_date | end_date | description | completion_pct
Riverside Luxury Apartments | RLA-2025 | active | Residential | 4200 Riverside Drive | Austin | TX | 78741 | Riverside Development LLC | info@riversidedev.com | 512-555-0101 | 12500000 | 11800000 | 2025-06-15 | 2026-12-30 | Luxury 200-unit apartment complex with amenities | 15
Downtown Office Tower Renovation | DOT-2025 | active | Commercial | 800 Congress Avenue | Austin | TX | 78701 | Capitol Properties Inc | contact@capitolprops.com | 512-555-0202 | 8750000 | 8200000 | 2025-08-01 | 2026-09-15 | Full renovation of 12-story Class A office building | 32
Highway 35 Bridge Repair | H35-2026 | pre_construction | Infrastructure | IH-35 & Oltorf St Overpass | Austin | TX | 78704 | Texas DOT | projects@txdot.gov | 512-555-0303 | 4200000 | 3900000 | 2026-03-15 | 2026-11-30 | Bridge deck replacement and structural reinforcement | 0

## 06_opportunities
name | client_name | stage | estimated_value | probability_pct | expected_close_date | source
Medical Center Parking Garage | St. David's Healthcare | proposal | 6500000 | 65 | 2026-04-15 | referral
Lakeway Resort Pool Complex | Lakeway Resort & Spa | qualification | 3200000 | 40 | 2026-05-30 | website
Mueller Mixed-Use Development | Catellus Austin LLC | negotiation | 18500000 | 80 | 2026-03-20 | existing_client
South Congress Retail Build-Out | SoCo Ventures | lead | 1800000 | 20 | 2026-07-01 | cold_call
Round Rock ISD Elementary School | Round Rock ISD | proposal | 9200000 | 55 | 2026-06-15 | trade_show

## 07_bids
project_name | client_name | bid_amount | due_date | bid_type | notes
Medical Center Parking Garage | St. David's Healthcare | 6850000 | 2026-03-01 | Lump Sum | 4-story precast parking structure with 450 spaces. Includes elevator and stair towers.
Mueller Mixed-Use Development | Catellus Austin LLC | 19200000 | 2026-02-28 | GMP | Phase 1: 3-story mixed-use with ground floor retail and 80 residential units above.
Round Rock ISD Elementary School | Round Rock ISD | 9450000 | 2026-04-01 | Lump Sum | 42000 SF elementary school with gymnasium and cafeteria. Must meet TEA design standards.
South Congress Retail Build-Out | SoCo Ventures | 1950000 | 2026-05-15 | T&M | Interior build-out of 8 retail spaces in existing shell. Tenant improvement allowances vary.

## 08_vendors
company_name | first_name | last_name | email | phone | job_title
Hill Country Lumber Supply | Angela | Morrison | angela@hill-country-lumber.com | 512-555-0301 | Sales Rep
Texas Ready Mix Concrete | Brian | Caldwell | brian@texasreadymix.com | 512-555-0302 | Account Manager
Lone Star Building Supply | Diane | Fletcher | diane@lonestar-supply.com | 512-555-0303 | Sales Manager
SafetyFirst Equipment Rental | Tom | Henderson | tom@safetyfirst-equip.com | 512-555-0304 | Branch Manager
Austin Rebar & Wire | Greg | Simmons | greg@austinrebar.com | 512-555-0305 | Operations Manager
Central Texas Drywall Supply | Maria | Delgado | maria@ctxdrywall.com | 512-555-0306 | Account Rep
Bluebonnet Pipe & Fittings | Wayne | Barrett | wayne@bluebonnetpipe.com | 512-555-0307 | Sales Engineer
Capitol City Electrical Supply | Linda | Park | linda@capitolcityelectric.com | 512-555-0308 | Branch Manager

## 09_contracts
title | contract_type | party_name | party_email | contract_amount | start_date | end_date | payment_terms
Riverside Apartments - Concrete Foundation & Structure | subcontractor | Ramirez Concrete Inc | carlos@ramirez-concrete.com | 1850000 | 2025-06-15 | 2026-04-30 | net_30
Riverside Apartments - Framing Package | subcontractor | O'Brien Framing LLC | mike@obrien-framing.com | 1420000 | 2025-09-01 | 2026-06-15 | net_30
Downtown Office Tower - Electrical Rough-In & Finish | subcontractor | Vasquez Electrical Services | tony@vasquez-electric.com | 980000 | 2025-10-01 | 2026-07-30 | net_45
Downtown Office Tower - HVAC System Install | subcontractor | Doyle Mechanical HVAC | frank@doyle-hvac.com | 1250000 | 2025-09-15 | 2026-08-15 | net_45
Highway 35 Bridge - Structural Steel | subcontractor | Kowalski Structural Steel | steve@kowalski-steel.com | 890000 | 2026-03-15 | 2026-09-30 | net_30
Lumber Supply Agreement 2025-2026 | vendor | Hill Country Lumber Supply | angela@hill-country-lumber.com | 650000 | 2025-01-01 | 2026-12-31 | net_30

## 10_daily_logs_riverside
log_date | weather_conditions | temperature | work_performed | safety_incidents | delays
2026-01-06 | partly_cloudy | 52 | Continued forming and pouring grade beams on Building B south wing. Rebar crew tied 48 footings. Concrete pump arrived at 7AM and poured 85 cubic yards. | None | None
2026-01-07 | sunny | 55 | Stripped forms on Building A west footings. Backfill and compaction on completed foundation sections. Survey crew verified elevations on grid lines A through F. | None | None
2026-01-08 | cloudy | 48 | Framing crew began first floor wall layout on Building A. Delivered and staged 22000 board feet of lumber. Bottom plates installed on sections 1 through 8. | None | Lumber delivery delayed 2 hours due to traffic on I-35
2026-01-09 | rain | 44 | Rain day - limited outdoor work. Interior layout and material staging only. Safety meeting held in job trailer. Reviewed fall protection plan for upcoming second floor framing. | None | Full day rain delay - no concrete or framing work
2026-01-10 | sunny | 50 | Resumed framing on Building A first floor. Completed wall sections 1 through 12. Plumbing rough-in crew began underground waste lines in Building B. MEP coordination meeting at 2PM. | None | None
2026-01-13 | sunny | 54 | Second floor deck sheathing started on Building A sections 1-4. Concrete crew poured remaining grade beams on Building B north side - 62 cubic yards. Compaction testing passed at 98%. | None | None
2026-01-14 | partly_cloudy | 58 | Framing crew completed first floor walls Building A. Began setting second floor joists. Electrical crew pulled permits and began underground conduit runs in Building B. | None | None
2026-01-15 | sunny | 61 | Second floor framing 40% complete on Building A. Plumbing top-out in Building B first floor complete. HVAC ductwork layout started. Inspector approved Building B foundation. | None | None
2026-01-16 | cloudy | 46 | Continued second floor framing Building A. Steel beam delivery for parking structure received and staged. Ramirez Concrete crew mobilized forms for parking deck. | None | None
2026-01-17 | sunny | 53 | Building A second floor framing 75% complete. Tilt-up panel forms started for parking structure. Safety walk-through with client - no issues noted. Weekly progress photos taken. | None | None

## 11_daily_logs_downtown
log_date | weather_conditions | temperature | work_performed | safety_incidents | delays
2026-01-06 | partly_cloudy | 52 | Demolition complete on floors 8-10. Debris removal ongoing. New elevator cab framing started in shaft 2. HVAC duct rough-in on floors 3-4. | None | None
2026-01-07 | sunny | 55 | Drywall hanging on floors 1-2 at 60%. Electrical panel installation floor 5 complete. Fire sprinkler rough-in floors 6-7 started. Glass curtain wall measurement crew on site. | None | None
2026-01-08 | cloudy | 48 | Continued drywall floors 1-2. Taping and mudding started on floor 1 south wing. Elevator #2 rail installation in progress. MEP coordination for floors 8-10 ductwork routing. | None | Elevator parts shipment delayed - expected Thursday
2026-01-09 | rain | 44 | Interior work continued despite rain. Drywall floor 1 complete. Floor 2 at 80%. Electrical rough-in floors 6-7. Paint primer applied floor 1 south wing conference rooms. | None | None
2026-01-10 | sunny | 50 | Drywall floor 2 complete. Started floor 3. Elevator parts received and installation resumed. Lobby marble tile layout approved by architect. Curtain wall shop drawings reviewed. | None | None
2026-01-13 | sunny | 54 | Floor 3 drywall 50%. Ceiling grid installation floors 1-2. HVAC test and balance started floor 1. Lobby reception desk millwork delivered. Restroom tile work floors 1-2. | None | None
2026-01-14 | partly_cloudy | 58 | Floor 3 drywall complete. Floor 4 started. Curtain wall mock-up panel installed for architect review. Elevator #1 operational for construction use. Fire alarm wiring floors 1-4. | None | None
2026-01-15 | sunny | 61 | Floors 4-5 drywall in progress. Painting floors 1-2 at 70%. Carpet measurement for floors 1-3. Lobby stone installation began. Building automation system programming started. | One worker minor cut from metal stud - first aid applied on site | None

## 12_rfis
subject | question | priority | due_date
Foundation drain tile routing conflict | Structural drawings show grade beam at grid B-4 conflicting with civil storm drain pipe routing. Please clarify which takes priority and provide revised detail. | high | 2026-02-01
Window header size clarification | Architectural plans call for 4x12 headers at all window openings but structural shows LVL beams at openings wider than 6 feet. Which spec governs for the 8-foot openings on Building A east elevation? | medium | 2026-02-15
Elevator pit waterproofing specification | Spec section 07 11 00 references two different waterproofing products for below-grade applications. Which product should be used for the elevator pit specifically? | high | 2026-01-30
HVAC diffuser substitution request | Specified diffuser model TDC-400 has 16-week lead time. Requesting approval to substitute with AirTech AT-400S which has equivalent CFM rating and is available immediately. | urgent | 2026-01-25
Lobby floor finish transition detail | No detail shown for transition between marble tile in lobby and carpet tile in corridor at floor 1. Please provide transition strip detail and material specification. | low | 2026-03-01
Bridge deck rebar spacing discrepancy | Structural plan sheet S-201 shows #5 bars at 6 inch spacing but the typical section on S-001 shows #5 at 8 inch spacing for the same deck area. Please confirm correct spacing. | high | 2026-03-15
Fire rating at shaft penetrations | MEP drawings show multiple penetrations through the 2-hour fire-rated elevator shaft wall. Please confirm acceptable firestop assembly for grouped conduit penetrations. | medium | 2026-02-20
Parking structure expansion joint location | Civil drawings show expansion joints at 60-foot intervals but structural notes call for joints at 90-foot max. Parking structure spans are 65 feet. Which governs? | medium | 2026-02-28

## 13_change_orders
title | description | reason | amount | schedule_impact_days
Additional electrical outlets - Building A units | Owner requested 2 additional duplex outlets per bedroom and dedicated 20A circuit for kitchen island in all 120 units. Includes panel upgrades. | owner_request | 145000 | 8
Unforeseen rock removal - Building B foundation | Encountered limestone shelf at 4 feet below grade across Building B footprint requiring rock hammering and removal. Geotechnical report did not indicate rock at this depth. | unforeseen_condition | 87500 | 12
Upgraded lobby finishes - Office Tower | Architect revised lobby design to include full-height marble walls and custom reception desk. Replaces original drywall and paint specification. | design_change | 215000 | 5
HVAC system upsizing - Office Tower floors 8-10 | Mechanical engineer determined original equipment undersized for floors 8-10 due to revised tenant occupancy loads. Upgrading 3 AHUs from 15-ton to 20-ton. | design_error | 68000 | 3
Bridge approach guardrail upgrade | TxDOT revised standard to require TL-4 rated barrier instead of original TL-3 specification. Heavier steel sections and modified anchorage required. | scope_change | 42000 | 0
Value engineering - substitute roofing system | Replace specified modified bitumen roof with TPO single-ply membrane on Buildings A and B. Equivalent warranty with reduced material and labor cost. | value_engineering | -95000 | 0

## 14_safety_incidents
title | description | incident_type | severity | incident_date | location | osha_recordable
Slip and fall on wet concrete | Worker slipped on freshly washed concrete surface near Building A foundation. Minor abrasion on left knee. Worker returned to duty same day after first aid treatment. | first_aid | low | 2025-11-12 | Riverside Apartments - Building A Foundation | no
Struck by falling lumber | 2x6 board fell from second floor scaffolding and struck worker on hard hat. No injury sustained. Hard hat cracked and replaced. Secured lumber staging area immediately. | near_miss | medium | 2026-01-08 | Riverside Apartments - Building A 2nd Floor | no
Electrical shock - live wire contact | Electrician contacted live 120V circuit that was not properly locked out during panel work on floor 5. Received minor shock to right hand. Sent to clinic for evaluation. No burns or lasting effects. | recordable | high | 2026-01-10 | Downtown Office Tower - Floor 5 Electrical Room | yes
Caught between - scissor lift and column | Operator's hand was briefly caught between scissor lift railing and concrete column while positioning lift in tight corridor. Minor bruising. No fracture. | first_aid | medium | 2025-12-18 | Downtown Office Tower - Floor 3 Corridor | no
Heat illness - dehydration | Concrete finisher showed signs of heat exhaustion during summer foundation pour. Moved to shade and administered fluids. Transported to urgent care as precaution. Returned to work next day. | recordable | medium | 2025-08-15 | Riverside Apartments - Building B Slab Pour | yes

## 15_safety_inspections
inspection_type | inspection_date | score | findings | corrective_actions | status
site_safety | 2026-01-06 | 92 | Fall protection in place on all elevated work areas. Two workers missing high-visibility vests on ground level. Housekeeping excellent. | Issued replacement vests and reminded crew of PPE requirements. Posted updated PPE signage at site entrance. | completed
fire_safety | 2026-01-08 | 88 | Fire extinguishers inspected and current on floors 1-4. Floor 5 extinguisher past monthly inspection date. Hot work permit for welding was properly posted. | Replaced floor 5 extinguisher with newly inspected unit. Updated inspection log. | completed
equipment | 2026-01-10 | 95 | All equipment pre-operation inspection logs current. Excavator daily checklist complete. Crane annual certification valid through August 2026. One frayed sling identified and removed. | Tagged and removed damaged sling from service. Ordered replacement. Conducted crew briefing on rigging inspection. | completed
site_safety | 2026-01-13 | 85 | Guardrails on second floor deck complete and secure. Open stairwell penetration missing cover. Electrical cords properly routed on ground level. Trench box in place for utility work. | Installed plywood cover over stairwell opening and marked with warning tape. Added to daily inspection checklist. | completed
equipment | 2026-01-15 | 90 | Generator grounding verified. Compressor pressure relief valve tested and functional. Scissor lift operator certifications current. One ladder missing safety feet. | Removed defective ladder from site. Replaced with inspected unit from equipment yard. | completed
site_safety | 2026-01-17 | 94 | Excellent housekeeping across all work areas. PPE compliance 100%. Fall protection systems properly installed. Emergency evacuation routes clearly posted. First aid kits fully stocked. | No corrective actions required. Commended site superintendent and crew leads for safety culture. | completed

## 16_toolbox_talks
title | description | topic | scheduled_date | attendees_count | notes
Fall Protection Awareness | Reviewed OSHA 1926 Subpart M requirements for fall protection above 6 feet. Demonstrated proper harness fit and lanyard inspection. Covered anchor point selection and rescue planning. | Fall Protection | 2026-01-06 | 18 | All framing and roofing crew attended. Distributed new harness inspection pocket cards.
Excavation and Trenching Safety | Covered soil classification and protective systems. Reviewed sloping and shoring requirements for utility trenches. Demonstrated how to identify cave-in warning signs. | Excavation Safety | 2026-01-08 | 12 | Foundation crew and utility contractors attended. Reviewed competent person responsibilities.
Electrical Safety on the Jobsite | Discussed lockout/tagout procedures and energized work permits. Covered GFCI requirements for temporary power. Reviewed recent shock incident and lessons learned. | Electrical Safety | 2026-01-10 | 22 | All trades attended following electrical incident. Reinforced LOTO procedures.
Scaffolding Erection and Use | Reviewed scaffold assembly requirements including base plates and mud sills. Covered guardrail and access requirements. Discussed load capacity limits and plank inspection. | Scaffolding | 2026-01-13 | 15 | Interior finishing crews attended. Demonstrated proper scaffold tagging system.
Heat Illness Prevention | Covered recognition of heat exhaustion and heat stroke symptoms. Reviewed company hydration policy and shade requirements. Discussed acclimatization schedule for new workers. | Heat Illness Prevention | 2026-01-15 | 20 | Mandatory for all field personnel. Distributed electrolyte packets and water bottle refill schedule.
Crane and Rigging Safety | Reviewed hand signals and communication protocols for crane operations. Covered sling angle factors and load weight estimation. Discussed swing radius barricading requirements. | Crane Safety | 2026-01-17 | 14 | All workers in crane operation zones attended. Posted updated crane signal chart in job trailer.

## 17_certifications
cert_name | cert_type | issuing_authority | cert_number | issued_date | expiry_date | contact_name
OSHA 30-Hour Construction Safety | safety | OSHA Training Institute | OSHA30-2024-44812 | 2024-03-15 | 2029-03-15 | Marcus Thompson
OSHA 10-Hour Construction Safety | safety | OSHA Training Institute | OSHA10-2025-18923 | 2025-01-20 | 2030-01-20 | James Mitchell
CDL Class A Commercial Driver License | license | Texas DPS | TX-CDL-A-889201 | 2024-06-01 | 2028-06-01 | James Mitchell
NCCCO Mobile Crane Operator | certification | NCCCO | NCCCO-MCO-55218 | 2023-11-01 | 2028-11-01 | Robert Jackson
First Aid / CPR / AED | safety | American Red Cross | ARC-FA-2025-33104 | 2025-06-15 | 2027-06-15 | Sarah Chen
AWS Certified Welding Inspector | certification | American Welding Society | AWS-CWI-28841 | 2024-09-01 | 2027-09-01 | Elena Rodriguez
HAZWOPER 40-Hour | safety | OSHA Training Institute | HAZ40-2024-11209 | 2024-04-20 | 2025-04-20 | Sarah Chen
EPA Lead Renovator (RRP) | certification | EPA | EPA-LR-TX-44210 | 2024-07-10 | 2029-07-10 | David Williams
Texas Master Electrician License | license | TDLR | TDLR-ME-102844 | 2023-08-01 | 2025-08-01 | Tony Vasquez
Texas Master Plumber License | license | TSBPE | TSBPE-MP-78551 | 2024-01-15 | 2027-01-15 | Patricia Hawkins

## 18_time_entries
entry_date | hours | overtime_hours | description | cost_code
2026-02-09 | 8 | 2 | Foundation forming and rebar tying Building B south wing. Concrete pour coordination. | 3300
2026-02-09 | 8 | 0 | Site safety inspection and daily log preparation. Subcontractor coordination meeting. | 1000
2026-02-10 | 8 | 1.5 | Stripped forms Building A west footings. Supervised backfill and compaction operations. | 3300
2026-02-10 | 8 | 0 | Framing material takeoff and staging. Reviewed shop drawings for Building A. | 6100
2026-02-11 | 8 | 0 | First floor wall framing Building A sections 1-8. Bottom plate installation and layout. | 6100
2026-02-11 | 8 | 0 | Electrical underground conduit installation Building B. Permit coordination with city inspector. | 16000
2026-02-12 | 4 | 0 | Rain day - interior material staging and organization. Safety meeting facilitation. | 1000
2026-02-13 | 8 | 2 | Wall framing Building A sections 9-12. Plumbing rough-in coordination. | 6100
2026-02-13 | 8 | 0 | Underground waste line installation Building B. Slope verification and testing. | 15100
2026-02-09 | 8 | 1 | Second floor deck sheathing Building A. Concrete pour Building B grade beams. | 6100
2026-02-09 | 8 | 0 | Office Tower drywall installation floors 1-2. Ceiling grid layout floor 1. | 9250
2026-02-10 | 8 | 0 | Framing first floor completion Building A. Joist setting second floor. | 6100
2026-02-10 | 8 | 2 | Elevator rail installation shaft 2. Cab framing and electrical connection. | 14200
2026-02-11 | 8 | 0 | Second floor framing Building A continued. Plumbing top-out inspection coordination. | 6100
2026-02-11 | 8 | 1.5 | Lobby stone installation and reception desk millwork. Painting floors 1-2 progress. | 9300

## 19_equipment_maintenance
equipment_name | title | maintenance_type | description | maintenance_date | cost | performed_by | vendor_name | next_due_date
CAT 320 Excavator | CAT 320 Excavator - 500 Hour Service | preventive | Engine oil and filter change. Hydraulic filter replacement. Undercarriage inspection and track tension adjustment. Greased all pivot points. Checked coolant level and condition. | 2026-01-05 | 1850 | James Mitchell | Central Texas Equipment Service | 2026-04-05
Liebherr LTM 1060 Crane | Liebherr LTM 1060 Crane - Annual Inspection | inspection | Annual OSHA/ANSI crane inspection. Load test at 100% and 125% capacity. Wire rope inspection - no defects found. All safety devices functional. Boom condition satisfactory. Certification renewed. | 2025-12-15 | 4200 | Tom Henderson | SafetyFirst Equipment Rental | 2026-12-15
Generac 100kW Generator | Generac 100kW Generator - Fuel System Repair | corrective | Fuel injector replacement on cylinders 2 and 4 due to rough running and black smoke. Replaced fuel filters. Tested under load for 2 hours - running smooth. Checked transfer switch operation. | 2026-01-12 | 2800 | Robert Jackson | Generac Authorized Service Center | 2026-07-12
Genie GS-2632 Scissor Lift | Genie GS-2632 Scissor Lift - Hydraulic Leak | corrective | Hydraulic cylinder seal replacement on main lift cylinder. Flushed hydraulic system and refilled with new fluid. Function tested all controls. Platform leveling checked. | 2025-11-20 | 950 | Robert Jackson |  | 2026-05-20
John Deere 310SL Backhoe | John Deere 310SL Backhoe - 250 Hour Service | preventive | Engine oil and filter change. Transmission fluid check. Air filter replacement. Battery terminals cleaned. Bucket teeth inspected - 2 replaced due to wear. Tire pressure adjusted. | 2026-01-08 | 1200 | James Mitchell |  | 2026-04-08
Ford F-350 Service Truck | Ford F-350 Service Truck - Brake Replacement | corrective | Front and rear brake pad replacement. Rotors resurfaced. Brake fluid flush. Parking brake adjustment. Road test completed satisfactory. | 2026-01-14 | 680 | Robert Jackson | Austin Fleet Services | 2027-01-14

## 20_invoices
invoice_type | amount | tax_amount | due_date | description | status | vendor_name | client_name | project_name
receivable | 485000 | 0 | 2026-02-15 | Progress Payment #7 - Foundation and framing through January 2026 | pending |  | Riverside Development Group | Riverside Luxury Apartments
receivable | 312000 | 0 | 2026-02-15 | Progress Payment #5 - Interior build-out floors 1-5 January 2026 | pending |  | Metro Commercial Properties | Downtown Office Tower Renovation
receivable | 125000 | 0 | 2026-02-28 | Change Order #1 - Additional electrical outlets approved | approved |  | Riverside Development Group | Riverside Luxury Apartments
payable | 185000 | 0 | 2026-02-05 | Payment Application #4 - Grade beams Building B and parking structure forms | approved | Ramirez Concrete Inc |  | Riverside Luxury Apartments
payable | 142000 | 0 | 2026-02-05 | Payment Application #3 - Building A first floor framing complete | approved | O'Brien Framing LLC |  | Riverside Luxury Apartments
payable | 48500 | 4122.5 | 2026-01-30 | Invoice #LBR-28841 - January lumber delivery 22000 BF plus hardware | paid | Hill Country Lumber Supply |  | Riverside Luxury Apartments
payable | 32000 | 2720 | 2026-01-30 | Invoice #TRM-9921 - 147 cubic yards concrete January pours | paid | Texas Ready Mix Concrete |  | Riverside Luxury Apartments
payable | 68000 | 0 | 2026-02-10 | Payment Application #2 - Underground conduit and panel installation | pending | Vasquez Electrical Services |  | Riverside Luxury Apartments
receivable | 210000 | 0 | 2026-03-15 | Mobilization payment - 5% of contract value upon NTP | draft |  | Texas DOT | Highway 35 Bridge Repair
payable | 18500 | 1572.5 | 2026-02-01 | January crane and scissor lift rental | approved | SafetyFirst Equipment Rental |  | Riverside Luxury Apartments

## 21_journal_entries
entry_number | entry_date | description | reference | account_number | debit | credit | line_description
JE-001 | 2026-01-06 | Ramirez Concrete - Progress Payment #4 | AP-RC-004 | 5010 | 185000 |  | Subcontractor costs - concrete
JE-001 | 2026-01-06 | Ramirez Concrete - Progress Payment #4 | AP-RC-004 | 2000 |  | 185000 | Accounts payable - Ramirez Concrete
JE-002 | 2026-01-08 | Hill Country Lumber - January delivery | PO-LBR-28841 | 5020 | 48500 |  | Materials - lumber delivery
JE-002 | 2026-01-08 | Hill Country Lumber - January delivery | PO-LBR-28841 | 2030 | 4122.5 |  | Tax payable on materials
JE-002 | 2026-01-08 | Hill Country Lumber - January delivery | PO-LBR-28841 | 1000 |  | 52622.5 | Cash payment - Hill Country Lumber
JE-003 | 2026-01-15 | Riverside Apartments - Progress billing #7 | AR-RLA-007 | 1010 | 485000 |  | Accounts receivable - Riverside Dev
JE-003 | 2026-01-15 | Riverside Apartments - Progress billing #7 | AR-RLA-007 | 4000 |  | 485000 | Contract revenue - Riverside Apartments
JE-004 | 2026-01-15 | Downtown Office Tower - Progress billing #5 | AR-DOT-005 | 1010 | 312000 |  | Accounts receivable - Metro Commercial
JE-004 | 2026-01-15 | Downtown Office Tower - Progress billing #5 | AR-DOT-005 | 4000 |  | 312000 | Contract revenue - Downtown Office Tower
JE-005 | 2026-01-15 | Bi-weekly payroll | PR-2026-02 | 5000 | 86000 |  | Direct labor - field workers
JE-005 | 2026-01-15 | Bi-weekly payroll | PR-2026-02 | 6000 | 42000 |  | Office salaries - admin staff
JE-005 | 2026-01-15 | Bi-weekly payroll | PR-2026-02 | 2020 |  | 128000 | Accrued payroll
JE-006 | 2026-01-20 | Monthly equipment depreciation | DEP-2026-01 | 7010 | 8500 |  | Depreciation expense - January
JE-006 | 2026-01-20 | Monthly equipment depreciation | DEP-2026-01 | 1110 |  | 8500 | Accumulated depreciation - equipment
JE-007 | 2026-01-30 | Monthly office rent and utilities | RENT-2026-01 | 6010 | 12500 |  | Rent and utilities - January
JE-007 | 2026-01-30 | Monthly office rent and utilities | RENT-2026-01 | 1000 |  | 12500 | Cash payment - rent
JE-008 | 2026-01-30 | Insurance premium - monthly | INS-2026-01 | 6020 | 8200 |  | Workers comp and GL insurance
JE-008 | 2026-01-30 | Insurance premium - monthly | INS-2026-01 | 1040 |  | 8200 | Prepaid insurance - monthly amortization

## 22_accounts_receivable
amount | tax_amount | due_date | description | status | client_name | project_name
485000 | 0 | 2026-02-15 | Progress Payment #7 - Foundation and framing through January 2026 | pending | Riverside Development Group | Riverside Luxury Apartments
312000 | 0 | 2026-02-15 | Progress Payment #5 - Interior build-out floors 1-5 January 2026 | pending | Metro Commercial Properties | Downtown Office Tower Renovation
125000 | 0 | 2026-02-28 | Change Order #1 - Additional electrical outlets approved | approved | Riverside Development Group | Riverside Luxury Apartments
210000 | 0 | 2026-03-15 | Mobilization payment - 5% of contract value upon NTP | draft | Texas DOT | Highway 35 Bridge Repair
95000 | 0 | 2026-03-01 | Retainage release - Building A foundation complete | draft | Riverside Development Group | Riverside Luxury Apartments
175000 | 0 | 2026-03-15 | Milestone 3 - Floors 1-5 substantial completion | draft | Metro Commercial Properties | Downtown Office Tower Renovation

## 23_accounts_payable
amount | tax_amount | due_date | description | status | vendor_name | project_name
185000 | 0 | 2026-02-05 | Payment Application #4 - Grade beams Building B and parking structure forms | approved | Ramirez Concrete Inc | Riverside Luxury Apartments
142000 | 0 | 2026-02-05 | Payment Application #3 - Building A first floor framing complete | approved | O'Brien Framing LLC | Riverside Luxury Apartments
48500 | 4122.5 | 2026-01-30 | Invoice #LBR-28841 - January lumber delivery 22000 BF plus hardware | paid | Hill Country Lumber Supply | Riverside Luxury Apartments
32000 | 2720 | 2026-01-30 | Invoice #TRM-9921 - 147 cubic yards concrete January pours | paid | Texas Ready Mix Concrete | Riverside Luxury Apartments
68000 | 0 | 2026-02-10 | Payment Application #2 - Underground conduit and panel installation | pending | Vasquez Electrical Services | Riverside Luxury Apartments
18500 | 1572.5 | 2026-02-01 | January crane and scissor lift rental | approved | SafetyFirst Equipment Rental | Riverside Luxury Apartments
24000 | 2040 | 2026-02-10 | Invoice #LSB-4410 - Drywall and finishing materials floors 1-4 | pending | Lone Star Building Supply | Downtown Office Tower Renovation
15800 | 0 | 2026-02-15 | Payment Application #1 - Ductwork rough-in floors 3-4 | draft | Doyle Mechanical HVAC | Downtown Office Tower Renovation

## 24_properties
name | property_type | address_line1 | city | state | zip | year_built | total_sqft | total_units | purchase_price | current_value
Sunset Ridge Apartments | residential | 1200 Sunset Ridge Dr | Austin | TX | 78701 | 2018 | 48000 | 24 | 4200000 | 5100000
Congress Avenue Office Park | commercial | 500 Congress Ave Suite 100 | Austin | TX | 78701 | 2010 | 32000 | 8 | 6800000 | 7500000
Eastside Industrial Complex | industrial | 2800 East 7th St | Austin | TX | 78702 | 2005 | 75000 | 6 | 3500000 | 4200000
Lamar Mixed-Use Development | mixed_use | 1450 S Lamar Blvd | Austin | TX | 78704 | 2022 | 55000 | 18 | 8900000 | 9800000
Cedar Park Family Homes | residential | 300 Cypress Creek Rd | Cedar Park | TX | 78613 | 2015 | 36000 | 12 | 2800000 | 3400000

## 25_leases
tenant_name | property_name | tenant_email | tenant_phone | monthly_rent | security_deposit | lease_start | lease_end
John & Sarah Mitchell | Sunset Ridge Apartments | jmitchell@email.com | 512-555-0101 | 2400 | 4800 | 2025-06-01 | 2026-06-01
Acme Construction Supply LLC | Congress Avenue Office Park | leasing@acmesupply.com | 512-555-0202 | 4500 | 9000 | 2025-03-01 | 2028-03-01
Maria Garcia | Sunset Ridge Apartments | mgarcia@email.com | 512-555-0303 | 1850 | 3700 | 2025-09-15 | 2026-09-15
Southwest Engineering Group | Congress Avenue Office Park | admin@sweg.com | 512-555-0404 | 6200 | 12400 | 2025-01-01 | 2028-01-01
David Chen | Cedar Park Family Homes | dchen@email.com | 512-555-0505 | 2100 | 4200 | 2026-01-01 | 2027-01-01
Thompson Family Trust | Lamar Mixed-Use Development | info@thompsontrust.com | 512-555-0606 | 3200 | 6400 | 2025-07-01 | 2026-07-01
Lone Star Realty Inc | Lamar Mixed-Use Development | office@lonestarrealty.com | 512-555-0707 | 5800 | 11600 | 2025-04-01 | 2028-04-01
Patricia Williams | Cedar Park Family Homes | pwilliams@email.com | 512-555-0808 | 1950 | 3900 | 2025-11-01 | 2026-11-01

## 26_maintenance
title | property_name | description | priority | category | scheduled_date | estimated_cost
HVAC Filter Replacement - Building A | Sunset Ridge Apartments | Replace all HVAC filters in Building A units 101-112 | medium | HVAC | 2026-02-20 | 350
Roof Leak Repair - Unit 204 | Sunset Ridge Apartments | Water intrusion at northeast corner near skylight after heavy rain | high | Roofing | 2026-02-15 | 1200
Parking Lot Striping | Congress Avenue Office Park | Re-stripe all parking spaces and handicap zones in main lot | low | Exterior | 2026-03-01 | 800
Water Heater Replacement - Unit 308 | Cedar Park Family Homes | 50-gallon water heater failed. Needs full replacement | high | Plumbing | 2026-02-18 | 1500
Elevator Annual Inspection | Lamar Mixed-Use Development | Annual safety inspection and maintenance for passenger elevator | medium | General | 2026-03-10 | 2200
Broken Window - Unit 115 | Sunset Ridge Apartments | Tenant reported cracked window pane in bedroom | medium | Structural | 2026-02-22 | 450
Fire Alarm System Test | Congress Avenue Office Park | Quarterly fire alarm and sprinkler system testing | high | General | 2026-02-25 | 650
Exterior Paint Touch-Up | Eastside Industrial Complex | Touch up peeling paint on north-facing exterior wall | low | Exterior | 2026-04-01 | 1800
Garbage Disposal Repair - Unit 201 | Cedar Park Family Homes | Disposal unit jammed and making grinding noise | medium | Plumbing | 2026-02-19 | 175
Landscape Maintenance | Lamar Mixed-Use Development | Monthly landscaping including mowing trimming and irrigation check | low | Exterior | 2026-03-05 | 400

## 27_submittals
title | project_name | spec_section | due_date
Structural Steel Shop Drawings | Riverside Luxury Apartments | 05 12 00 | 2026-03-01
HVAC Equipment Submittals | Riverside Luxury Apartments | 23 05 00 | 2026-03-15
Curtain Wall System | Downtown Office Tower Renovation | 08 44 00 | 2026-04-01
Concrete Mix Design | Riverside Luxury Apartments | 03 30 00 | 2026-02-28
Electrical Panel Schedule | Downtown Office Tower Renovation | 26 24 00 | 2026-03-20
Waterproofing Membrane | Riverside Luxury Apartments | 07 10 00 | 2026-03-10
Elevator Equipment | Downtown Office Tower Renovation | 14 20 00 | 2026-04-15
Fire Suppression System | Riverside Luxury Apartments | 21 00 00 | 2026-03-25
Precast Concrete Panels | Highway 35 Bridge Repair | 03 40 00 | 2026-04-10
Reinforcing Steel Placement | Highway 35 Bridge Repair | 03 20 00 | 2026-03-30
Roofing Materials | Downtown Office Tower Renovation | 07 50 00 | 2026-04-05
Plumbing Fixtures | Riverside Luxury Apartments | 22 40 00 | 2026-03-18

## phases_BCM-2026
name | color | start_date | end_date
Temporary Barriers & Demolition | #ef4444 | 2026-01-15 | 2026-02-28
Structural & Plumbing Modifications | #f59e0b | 2026-02-15 | 2026-03-31
Electrical & HVAC Upgrades | #8b5cf6 | 2026-03-15 | 2026-04-30
Finishes & Tenant Build-Out | #10b981 | 2026-04-15 | 2026-06-15
Health Inspection & Opening | #06b6d4 | 2026-06-01 | 2026-06-30

## tasks_BCM-2026
name | phase_name | priority | start_date | end_date | completion_pct | is_milestone | is_critical_path
Temporary Barriers Installed | Temporary Barriers & Demolition | high | 2026-01-15 | 2026-01-31 | 100 | FALSE | FALSE
Selective Interior Demolition | Temporary Barriers & Demolition | high | 2026-02-01 | 2026-02-15 | 100 | FALSE | TRUE
Demolition Complete | Temporary Barriers & Demolition | critical | 2026-02-15 | 2026-02-28 | 100 | TRUE | TRUE
Grease Trap & Plumbing Rough-In | Structural & Plumbing Modifications | high | 2026-02-15 | 2026-03-15 | 90 | FALSE | TRUE
Structural Modifications Complete | Structural & Plumbing Modifications | high | 2026-03-01 | 2026-03-31 | 60 | TRUE | TRUE
Electrical Panel & Circuit Rough-In | Electrical & HVAC Upgrades | high | 2026-03-15 | 2026-04-15 | 30 | FALSE | FALSE
HVAC & Exhaust Duct Install | Electrical & HVAC Upgrades | medium | 2026-03-20 | 2026-04-30 | 15 | FALSE | FALSE
Vendor Stall Framing & Counters | Finishes & Tenant Build-Out | critical | 2026-04-15 | 2026-05-31 | 0 | FALSE | TRUE
Kitchen Equipment Installation | Finishes & Tenant Build-Out | high | 2026-05-15 | 2026-06-10 | 0 | FALSE | TRUE
Flooring & Ceiling Tile Install | Finishes & Tenant Build-Out | medium | 2026-05-20 | 2026-06-15 | 0 | FALSE | FALSE
Health Department Inspection | Health Inspection & Opening | critical | 2026-06-15 | 2026-06-25 | 0 | TRUE | TRUE
Grand Opening Ready | Health Inspection & Opening | high | 2026-06-30 | 2026-06-30 | 0 | TRUE | TRUE

## projects_import
name | code | status | project_type | address | city | state | zip | client_name | client_email | client_phone | budget | estimated_cost | start_date | end_date | description | completion_pct
Lakewood Medical Center Expansion | LMC-2026 | active | Commercial | 1500 Lake Austin Blvd | Austin | TX | 78703 | St. David's Healthcare | expansion@stdavids.com | 512-555-1100 | 18500000 | 17200000 | 2025-11-01 | 2027-03-15 | Three-story wing addition with 48 patient rooms and surgical suite | 22
Mueller District Townhomes Phase 2 | MDT-2026 | active | Residential | 2800 Mueller Blvd | Austin | TX | 78723 | Mueller Development Corp | info@muellerdev.com | 512-555-1201 | 9200000 | 8650000 | 2026-01-10 | 2026-11-30 | 32-unit luxury townhome community with shared amenities | 8
South Congress Parking Garage | SCP-2026 | pre_construction | Infrastructure | 1200 South Congress Ave | Austin | TX | 78704 | City of Austin Transportation | parking@austintexas.gov | 512-555-1302 | 6800000 | 6400000 | 2026-04-01 | 2027-01-15 | Five-level parking structure with 450 spaces and EV charging | 0
Barton Creek Mall Food Court Remodel | BCM-2026 | active | Renovation | 2901 Capital of Texas Hwy | Austin | TX | 78746 | Brookfield Properties | leasing@brookfield.com | 512-555-1403 | 3100000 | 2850000 | 2026-01-15 | 2026-06-30 | Complete food court renovation with 12 vendor stalls and seating for 400 | 35
East Riverside Mixed-Use Development | ERM-2026 | pre_construction | Mixed Use | 2400 East Riverside Dr | Austin | TX | 78741 | Greystar Real Estate | dev@greystar.com | 512-555-1504 | 28000000 | 26500000 | 2026-06-01 | 2028-02-28 | 18-story tower with 280 apartments and 15000 sqft ground-floor retail | 0
Round Rock ISD Elementary School #47 | RRS-2026 | active | Institutional | 4500 University Blvd | Round Rock | TX | 78665 | Round Rock ISD | facilities@roundrockisd.org | 512-555-1605 | 14200000 | 13800000 | 2025-09-15 | 2026-08-01 | New 72000 sqft elementary school for 650 students | 45
Domain Tech Campus Building C | DTC-2026 | active | Commercial | 11800 Domain Blvd | Austin | TX | 78758 | Apple Inc | construction@apple.com | 512-555-1706 | 42000000 | 39500000 | 2025-07-01 | 2027-06-30 | Six-story Class A office building with underground parking | 28
Pflugerville Water Treatment Upgrade | PWT-2026 | active | Infrastructure | 700 Pecan St | Pflugerville | TX | 78660 | City of Pflugerville Utilities | water@pflugervilletx.gov | 512-555-1807 | 7500000 | 7100000 | 2025-12-01 | 2026-10-15 | Upgrade filtration capacity from 8MGD to 12MGD | 18
Historic Sixth Street Hotel Conversion | HSH-2026 | pre_construction | Renovation | 400 East 6th St | Austin | TX | 78701 | Bunkhouse Group | projects@bunkhousehotels.com | 512-555-1908 | 11000000 | 10200000 | 2026-05-01 | 2027-04-30 | Convert 1920s warehouse into 85-room boutique hotel | 0
Cedar Park Fire Station #7 | CPF-2026 | active | Institutional | 1800 Cypress Creek Rd | Cedar Park | TX | 78613 | City of Cedar Park | fire@cedarparktexas.gov | 512-555-2009 | 5400000 | 5100000 | 2026-01-05 | 2026-09-30 | New 12000 sqft fire station with 3 bays and training facility | 12